# 10. PRIORITY 06: RECEPTION & REINTEGRATION CENTRE

## 10.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Reception & Reintegration Centre |
| Description | A dedicated reception and reintegration centre providing dignified support, counselling and livelihood opportunities for migrants returning through Tog-Wajaale |
| Indicative Investment | USD 7,000,000 (Birr 1,120,223,300)* |
| Sector | Migration & Social Services |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Grant |
| Ranking Rationale | Social Protection - Addresses returnee needs; supports vulnerable population; complements other investments |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 10.2 Strategic Rationale

### 10.2.1 The Challenge

As Ethiopia's busiest land crossing to Somaliland, Tog-Wajaale receives significant numbers of returning migrants with no dedicated reception facility. Returnees currently lack accommodation, psychosocial support or a structured pathway to reintegration.

| Issue | Description | Impact |
| --- | --- | --- |
| No Dedicated Reception Facility | Returnees currently lack accommodation, psychosocial support, or a structured pathway to reintegration | Returnees left vulnerable; no coordinated support |
| Significant Returnee Numbers | As Ethiopia's busiest land crossing to Somaliland, Tog-Wajaale receives significant numbers of returning migrants | Overwhelmed existing services; unmet needs |
| Vulnerable Returnees | Many returnees are in vulnerable conditions requiring immediate support | Protection risks; health and safety concerns |
| No Structured Reintegration | Absence of formal support for sustainable reintegration | Returnees may re-migrate irregularly; limited livelihood opportunities |

### 10.2.2 Why This is Priority #6

| Reason | Description |
| --- | --- |
| Humanitarian Need | Addresses immediate needs of vulnerable returnees |
| Social Protection | Provides essential services to vulnerable population |
| Complementary | Complements Youth Centre and other investments |
| Existing Programmes | Leverages IOM MRC, IGAD RMF, and Cities Alliance |
| Reasonable Cost | USD 7 million investment with significant social impact |

### 10.2.3 Tog-Wajaale as a Migration Corridor

Tog-Wajaale is a critical transit location for migrants from various parts of Ethiopia travelling to Middle East countries. It serves as a key node along the Eastern Migration Route, one of the busiest migration pathways in the region.

Key Migration Facts:

| Element | Description |
| --- | --- |
| Route | Eastern Migration Route to Middle East |
| Key Destination | Saudi Arabia (employment and remittances) |
| Transit Role | Primary land crossing between Ethiopia and Somaliland |
| Return Flow | Significant numbers of returnees pass through Tog-Wajaale |
| Vulnerability | Returnees often in vulnerable conditions |
| Protection Needs | Psychosocial support, accommodation, livelihood support |

### 10.2.4 Existing Programmes and Partnerships

| Programme | Details | Relevance |
| --- | --- | --- |
| IOM Migration Response Centre (MRC) | Operates in Tog-Wajaale, providing protection and assistance to vulnerable migrants; includes awareness raising, protection assistance, and coordination | Existing infrastructure and expertise |
| Save the Children International (SCI) & OWDA | Implement protection-related activities including child protection, legal assistance, psychosocial support, shelter/NFI assistance, and family tracing and reunification | Protection services for vulnerable returnees |
| IGAD Regional Migration Fund (RMF) | Officially launched RMF project activities in Tog-Wajaale in May 2026; Germany signed an €8 million grant agreement to scale up the RMF | Foundation for migration-related investments |
| Cities Alliance Programme | Supports sustainable and inclusive urban growth in cities along migration corridors | Strategic framework for migration management |
| National Migration Policy | Adopted by the Government of Ethiopia, providing a framework for managing migration and protecting migrants' rights | Policy framework and support |

### 10.2.5 IOM Migration Response Centre (MRC) Details

| Element | Details |
| --- | --- |
| Location | Tog-Wajaale |
| Purpose | Protection and assistance to vulnerable migrants |
| Services | Awareness raising; protection assistance; coordination |
| Partner Implementation | SCI and OWDA implement protection activities |
| Protection Services | Child protection; legal assistance; psychosocial support; shelter/NFI assistance; family tracing and reunification |
| Coordination | Regional and national actors engagement |

### 10.2.6 IGAD Regional Migration Fund (RMF) Details

| Element | Details |
| --- | --- |
| Purpose | Create economic opportunities and improve living conditions of migrants, refugees, and host communities |
| Approved Projects | Upgrading livestock market center, construction of two Community Development Centers, new vegetable market |
| Funding | Germany €8 million grant to scale up RMF |
| Focus Corridors | Key corridors including Togwajale (Ethiopia–Somaliland) |
| Investment Planning | Missions conducted identifying thematic areas including livestock, agriculture, water source development, and youth entrepreneurship development |
| Endorsement | Consultations with Ethiopian and Somali government officials endorsed Tog-Wajaale as a key RMF location |

### 10.2.7 National and Regional Policy Context

| Element | Details |
| --- | --- |
| National Migration Policy | Adopted by the Government of Ethiopia, providing a framework for managing migration and protecting migrants' rights |
| Safe Migration | Recognizes the importance of safe, orderly, and regular migration |
| Protection of Migrants' Rights | Emphasizes protection of migrants' rights |
| Sustainable Reintegration | Recognizes the importance of sustainable reintegration of returnees |
| Somali Regional State | Actively involved in migration management, serving as a member of the IGAD RMF National Steering Committee |
| Collaboration | Commitment to managing the challenges and opportunities of migration and displacement |

## 10.3 Project Scope

### 10.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Reception & Accommodation Facilities | Welcome centre and temporary accommodation | 2,000,000 | 320,063,800 |
| Counselling & Psychosocial Support | Mental health and psychosocial services | 1,500,000 | 240,047,850 |
| Skills Training & Livelihood Programmes | Vocational training and livelihood support | 1,500,000 | 240,047,850 |
| Reintegration Grants & Business Support | Grants and business development support | 1,000,000 | 160,031,900 |
| Monitoring, Follow-up & Case Management | Ongoing support and case management | 1,000,000 | 160,031,900 |
| TOTAL |  | 7,000,000 | 1,120,223,300 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 10.3.2 Component Details

1. Reception & Accommodation Facilities (USD 2,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Reception Centre | Welcoming and registration of returnees | Intake and assessment area |
| Temporary Accommodation | Short-term housing for returnees | 50+ beds capacity |
| Basic Amenities | Water, sanitation, hygiene facilities | WASH facilities |
| Medical Check-up | Basic health screening and first aid | Medical examination room |
| Nutrition Support | Food and nutrition assistance | Kitchen and dining area |
| Recreation | Recreational and social spaces | Common areas |

2. Counselling & Psychosocial Support (USD 1,500,000)

| Element | Description | Specification |
| --- | --- | --- |
| Individual Counselling | One-on-one counselling sessions | 5+ counsellors |
| Group Counselling | Group therapy and support groups | Group spaces |
| Psychosocial Support | Mental health and psychosocial support | MHPSS programming |
| Trauma Support | Trauma-informed care and support | Trauma specialists |
| Crisis Intervention | Emergency support for crisis situations | 24/7 support |
| Referral System | Referral to specialised services | Referral pathways |

3. Skills Training & Livelihood Programmes (USD 1,500,000)

| Element | Description | Specification |
| --- | --- | --- |
| Vocational Training | Market-aligned skills training | Construction; agriculture; trades |
| Livelihood Support | Support for income-generating activities | 200+ returnees/year |
| Agriculture Support | Agricultural skills and inputs | Farming and livestock |
| Digital Skills | Digital literacy and ICT training | Basic ICT skills |
| Business Skills | Basic business and financial literacy | Entrepreneurial skills |
| Life Skills | Life skills and resilience training | Essential life skills |

4. Reintegration Grants & Business Support (USD 1,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Reintegration Grants | Financial support for reintegration | 200+ grants/year |
| Business Support | Business planning and advisory services | Business mentors |
| Access to Finance | Linkages to microfinance and business loans | Financial institution partnerships |
| Market Linkages | Market access and linkages | Market connections |
| Startup Kits | Equipment and materials for startups | 100+ startup kits/year |
| Business Mentoring | Ongoing business mentoring | 12-month mentoring programme |

5. Monitoring, Follow-up & Case Management (USD 1,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Case Management | Personalized support and case management | 5+ case managers |
| Follow-up | Ongoing monitoring and follow-up | 12-month follow-up |
| Documentation | Proper documentation and reporting | Electronic case management system |
| Referral Pathways | Linkages to other service providers | Comprehensive referral system |
| Outcome Monitoring | Monitoring of reintegration outcomes | Outcome tracking |
| Impact Evaluation | Impact assessment of interventions | Regular evaluations |

## 10.4 Value Creation

### 10.4.1 Expected Outcomes

| Outcome | Target | Measurement |
| --- | --- | --- |
| Returnees Served / Year | Pending assessment | Registration records |
| Successfully Reintegrated | 80%+ successful reintegration | Follow-up surveys |
| Livelihood Support | 500+ returnees supported | Programme records |
| Psychosocial Support | All returnees receive support | Service records |
| Jobs Created | ~100 construction + case management | Employment records |
| Beneficiaries | Returnees, women & youth | Beneficiary tracking |

### 10.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Dignified Reception | Dignified and respectful reception for returnees |
| Trauma Support | Psychological and emotional support for traumatised returnees |
| Sustainable Reintegration | Livelihood opportunities for sustainable reintegration |
| Community Acceptance | Improved community acceptance of returnees |
| Reduced Irregular Migration | Addressing root causes through livelihood support |
| Social Cohesion | Strengthened social cohesion and stability |
| Protection | Protection for vulnerable returnees |
| Family Reunification | Support for family reunification |

### 10.4.3 Protection Impact

| Indicator | Target |
| --- | --- |
| Child Protection | All child returnees receive protection support |
| Women's Protection | All women returnees receive targeted support |
| Psychosocial Support | All returnees receive psychosocial support |
| Legal Assistance | Legal support for returnees in need |
| Shelter/NFI Assistance | Shelter and non-food items for returnees in need |
| Family Tracing | Family tracing and reunification support |

## 10.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | Cities Alliance Cities & Migration Programme active in Tog-Wajaale; city is a key return corridor; IOM MRC operating; IGAD RMF active | Formal returnee flow and needs assessment |
| Site / Land & Approvals | Gap | — | Site identification and titling |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & design |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 7M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | — | Social safeguard screening |
| Revenue, O&M & Delivery Model | Gap | — | O&M and case-management financing plan |
| Procurement / Transaction Plan | Gap | — | Implementing partner sounding |

### 10.5.1 Bankability Strengths

| Strength | Description |
| --- | --- |
| Strong Humanitarian Need | Clear justification based on returnee flows |
| Existing Programmes | IOM MRC, IGAD RMF, and Cities Alliance programmes active |
| Policy Support | National Migration Policy framework |
| Protection Framework | Strong protection rationale |
| Partnership Potential | Strong potential for UN and NGO partnerships |
| Complementary | Complements other investments in the portfolio |

### 10.5.2 Bankability Gaps

| Gap | Description | Required Action |
| --- | --- | --- |
| Returnee Flow Data | No formal returnee flow data | Conduct returnee flow and needs assessment |
| Site Identification | No site identified | Identify and secure site |
| Feasibility Study | No detailed analysis | Commission feasibility study |
| O&M Plan | No operations and maintenance plan | Develop O&M and financing plan |
| Partner Engagement | Limited partner sounding | Engage potential partners |

## 10.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | Public delivery with NGO/donor-funded programme partner |
| Operator & O&M | Municipal social affairs office with contracted implementing partner |
| Revenue / Cost Recovery | Municipal budget + donor/grant programme funding |
| Funding Mix | Grant-funded capital + programme co-financing from migration-focused partners; municipal budget for facility O&M |

### 10.6.1 Recommended Partnership Structure

text

┌─────────────────────────────────────────────────────────────┐

│                       PROJECT OVERSIGHT                      │

│                  Tog-Wajaale City Administration            │

│              (Mayor's Office / City Manager)                │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────────────┴────────────────────────────────────┐

│                    PROJECT MANAGEMENT                        │

│              Municipal Social Affairs Office                 │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────┼────────────────┐

│                │                │

▼                ▼                ▼

┌───────────────┐ ┌───────────────┐ ┌───────────────┐

│   RECEPTION   │ │   PSYCHOSOCIAL│ │   LIVELIHOOD  │

│   SERVICES    │ │   SERVICES    │ │   PROGRAMMES  │

│  (IOM/NGO)    │ │  (IOM/NGO)    │ │  (NGO/Partner)│

└───────────────┘ └───────────────┘ └───────────────┘

### 10.6.2 Programme Partners

| Partner Type | Potential Partners | Role |
| --- | --- | --- |
| Migration Partner | IOM; UNHCR; Migration-focused NGOs | Reception and protection services |
| Psychosocial Partner | Mental health organisations; NGOs | Psychosocial support |
| Training Provider | Vocational training institutions | Skills training |
| Livelihood Partner | NGOs; Microfinance institutions | Livelihood support |
| Protection Partner | SCI; OWDA; Child protection NGOs | Protection services |
| Government Partner | Regional Social Affairs Office; Ministry of Labour | Policy support |

## 10.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 05 (Youth Centre) | Skills training for returnees |
| With Priority 01 (Urban Expansion) | Housing and services for returnees |
| With Priority 03 (FTZ) | Employment opportunities for returnees |
| With IGAD RMF | Alignment with IGAD Regional Migration Fund programmes |
| With IOM MRC | Complement IOM Migration Response Centre services |
| With Cities Alliance EACC | Strategic framework for migration management |
| With National Migration Policy | Policy framework implementation |

## 10.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| Fluctuating returnee volumes affecting planning | Flexible facility design; phased capacity scaling |
| Programme funding sustainability beyond capital phase | Multi-year donor agreements; municipal budget line for O&M |
| Coordination across humanitarian & development actors | Formal MOU with IOM/UNHCR-affiliated actors and Cities Alliance programme |
| Community acceptance of returnees | Community engagement and awareness programmes; benefit-sharing |
| Returnee protection concerns | Safeguarding protocols; protection-focused programming |
| Staff capacity and turnover | Competitive compensation; training; professional development |
| Political sensitivity of migration | Clear guidelines; professional service delivery; policy alignment |

## 10.9 Implementation Phasing

### 10.9.1 Phase 1: Feasibility & Planning (2025-2026)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Returnee Flow & Needs Assessment | Months 1-4 | Consultant/IOM | 80,000 |
| Feasibility Study | Months 3-8 | Consultant | 120,000 |
| Programme Design | Months 4-9 | Project Team | 100,000 |
| Partner Engagement | Ongoing | Project Director | 50,000 |
| Social Safeguard Screening | Months 2-5 | Social Development Specialist | 60,000 |
| TOTAL |  |  | 410,000 |

### 10.9.2 Phase 2: Construction (2026-2028)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Site Development | Months 1-6 | Contractor | 500,000 |
| Reception & Accommodation Facilities | Months 3-12 | Contractor | 2,000,000 |
| Counselling & Psychosocial Facilities | Months 6-12 | Contractor | 1,500,000 |
| Skills Training & Livelihood Facilities | Months 9-15 | Contractor | 1,500,000 |
| Administration & Case Management Facilities | Months 12-18 | Contractor | 1,000,000 |
| TOTAL |  |  | 6,500,000 |

### 10.9.3 Phase 3: Operationalization (2028-2029)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Staff Recruitment | Months 14-16 | HR Department | 80,000 |
| Partner Agreements | Months 14-18 | Project Director | - |
| Programme Launch | Month 18 | Implementing Partner | - |
| Returnee Intake Commencement | Month 18+ | Operator | - |
| Community Awareness Campaign | Months 12-18 | Engagement Team | 50,000 |
| TOTAL |  |  | 130,000 |

## 10.10 Next Steps

### 10.10.1 Priority Action

Conduct a Returnee Flow & Needs Assessment

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / Urban Expansion Team |
| Estimated Cost | USD 80,000 - 120,000 |
| Expected Outcome | Evidence base for programme design and partner engagement |

### 10.10.2 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Finalise returnee flow assessment TOR | Week 1-3 | Project Director | Consultant procurement ready |
| Identify potential site for centre | Week 2-6 | Urban Expansion Team | Site shortlist |
| Engage IOM on partnership and coordination | Week 2-8 | Project Director | MOU for services |
| Engage IGAD on RMF alignment | Week 2-6 | City Manager | RMF programme alignment |
| Contact SCI and OWDA for protection partnership | Week 2-8 | Project Director | Partner interest assessment |
| Engage community on the project | Week 4-12 | Engagement Team | Community acceptance |
| Develop preliminary cost estimates | Week 8-12 | Infrastructure Specialist | Indicative project costs |

### 10.10.3 Immediate Actions

| Action | Responsible | Timeline |
| --- | --- | --- |
| Identify and secure site for centre | Urban Expansion Team | 0-45 days |
| Engage IOM for partnership discussions | Project Director | 0-30 days |
| Engage IGAD RMF and Cities Alliance | City Manager | 0-30 days |
| Prepare returnee flow assessment procurement | Project Director | 0-30 days |
| Consult community stakeholders | Engagement Team | 0-60 days |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418

Project Website: www.twuep.com.et