# 6. PRIORITY 02: CORRIDOR & ARTERIAL ROAD UPGRADE

## 6.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Corridor & Arterial Road Upgrade |
| Description | A 20 km programme of arterial and corridor road upgrades across Tog-Wajaale |
| Indicative Investment | USD 40,000,000 (Birr 6,401,276,000)* |
| Sector | Transport Infrastructure |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Concessional loan / grant |
| Ranking Rationale | Connectivity - Essential for access to FTZ, urban expansion areas, and trade corridor; addresses immediate infrastructure deficit |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 6.2 Strategic Rationale

### 6.2.1 Current Infrastructure Challenges

Much of Tog-Wajaale's road network is unpaved, undrained or unfit, and cannot support the city's rapid growth or its role as a trade corridor. Poor drainage causes flooding on several routes, constraining safe movement for residents and traders.

| Challenge | Description | Impact |
| --- | --- | --- |
| Unpaved Roads | Significant portions of the road network remain unpaved, limiting accessibility | Reduced mobility; increased transport costs |
| Poor Drainage | Inadequate drainage causes flooding on several routes, particularly during rainy seasons | Flood damage; road closures; safety risks |
| Congestion | Increasing traffic volumes from cross-border trade strain existing road capacity | Travel delays; reduced economic efficiency |
| Safety Concerns | Lack of proper lighting, signage, and pedestrian facilities creates safety risks | Accidents; injuries; fatalities |
| Limited Accessibility | Poor road conditions constrain safe movement for residents and traders | Reduced economic activity; social exclusion |

### 6.2.2 Why This is Priority #2

| Reason | Description |
| --- | --- |
| Connectivity | Provides access to FTZ, urban expansion areas, and trade corridor |
| Trade Facilitation | Reduces transport costs and transit times |
| Safety | Improves road safety through proper infrastructure |
| Flood Management | Addresses critical drainage and flooding issues |
| Enabling Investment | Creates conditions for economic development |

### 6.2.3 Recent Infrastructure Developments

| Initiative | Details | Relevance |
| --- | --- | --- |
| Togwajaale Border Bridge Reconstruction | TradeMark Africa launched reconstruction in May 2026 with Sweden funding; includes structural reinforcement, wadi river drainage, and flood wall barriers | Enhanced cross-border connectivity |
| One-Stop Border Post (OSBP) | Feasibility study recommends a juxtaposed model for Tog-Wajaale OSBP; ongoing upgrades aim to streamline procedures | Streamlined customs; reduced delays |
| Jigjiga-Tog Wajaale Power Transmission Line | 73.1 km 400kV double circuit transmission line proposed | Reliable power supply for infrastructure |
| Berbera Corridor Road Upgrades | UK funding of over USD 16.6 million channelled through TradeMark Africa; EU has invested in Berbera-Hargeisa-Togwajaale highway | Regional connectivity; trade facilitation |
| Togwajaale Weighbridge Project | Underway to facilitate transit and transport between Ethiopia and Somaliland | Regulated transport; road protection |

### 6.2.4 Population Growth Driving Demand

The city's population is projected to grow from 82,064 to 119,000 by 2030 and 554,700 by 2055, placing increasing demands on the transport network. The urban area is expected to expand 12.6-fold by 2055, requiring planned road infrastructure to support this growth.

| Year | Population | Travel Demand (Est.) |
| --- | --- | --- |
| 2024 | 82,064 | Baseline |
| 2030 | 119,000 | +45% |
| 2055 | 554,700 | +576% |

## 6.3 Project Scope

### 6.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Arterial Road Development | Construction and upgrade of 20 km priority roads | 20,000,000 | 3,200,638,000 |
| Drainage & Stormwater Systems | Comprehensive drainage infrastructure | 6,000,000 | 960,191,400 |
| Sidewalks & Pedestrian Facilities | Safe pedestrian infrastructure | 5,000,000 | 800,159,500 |
| Street Lighting & Traffic Safety | Lighting, signage, and safety features | 5,000,000 | 800,159,500 |
| Landscaping & Green Buffers | Green infrastructure and environmental integration | 4,000,000 | 640,127,600 |
| TOTAL |  | 40,000,000 | 6,401,276,000 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 6.3.2 Component Details

1. Arterial Road Development (USD 20,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Road Construction | 20 km of new and upgraded arterial roads | 4-6 lane standard with BRT integration |
| Pavement Design | Durable pavement for heavy vehicle traffic | Designed for 20-30 year lifespan |
| Geometric Design | Improved road geometry for safety and efficiency | International road design standards |
| Intersection Improvements | Upgraded intersections with traffic controls | Signalized intersections where needed |
| Right-of-Way | 50m corridor width | Adequate for road, BRT, and NMT |

2. Drainage & Stormwater Systems (USD 6,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Stormwater Drainage | Comprehensive drainage systems | 1-in-10-year and 1-in-50-year flood design |
| Culverts & Crossings | Crossings for water flow | Adequate capacity for seasonal flows |
| Flood Protection | Climate-resilient flood protection measures | Elevated segments where needed |
| Permeable Pavements | Sustainable drainage solutions | Where geotechnically suitable |

3. Sidewalks & Pedestrian Facilities (USD 5,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Pedestrian Walkways | Safe sidewalks along upgraded routes | 2-3m wide walkways |
| Crossings | Safe pedestrian crossings | At-grade and elevated crossings |
| Accessibility | Accessible design for persons with disabilities | Universal design principles |
| Shaded Walkways | Protection from sun in hot semi-arid climate | Shade structures and trees |

4. Street Lighting & Traffic Safety (USD 5,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Street Lighting | Adequate lighting for safety and security | LED lighting; solar where feasible |
| Traffic Signs | Comprehensive signage | International standard signage |
| Road Markings | Clear road markings | Durable, reflective markings |
| Safety Barriers | Physical safety measures | Where needed for safety |
| Traffic Signals | Signalized intersections where needed | Modern traffic signal systems |

5. Landscaping & Green Buffers (USD 4,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Green Buffers | Landscaping along roads | Native, drought-resistant species |
| Tree Planting | Shade trees and vegetation | 1-2 rows of trees per road |
| Aesthetic Improvement | Enhanced visual appeal | Integrated landscape design |
| Environmental Integration | Integration with natural environment | Ecological considerations |

## 6.4 Value Creation

### 6.4.1 Expected Outcomes

| Outcome | Target |
| --- | --- |
| People/Businesses Served | 82,064+ (growing to 554,700 by 2055) |
| Jobs Created | ~900 construction jobs |
| Travel Time | 30% reduction in travel time |
| Safety | 50% reduction in road accidents |
| Flood Risk | Reduced flooding on priority routes |
| Accessibility | Improved access to economic zones |

### 6.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Trade Facilitation | Improved road conditions reduce transport costs and transit times |
| Market Access | Enhanced connectivity to markets during rainy seasons |
| Safety | Reduced road accidents through improved infrastructure |
| Urban Mobility | Improved movement for residents and businesses |
| Economic Growth | Better roads attract investment and support economic activity |
| Emergency Access | Improved access for emergency services |
| Climate Resilience | Flood-resistant design protects infrastructure |

### 6.4.3 Cost-Benefit Indicators

| Indicator | Estimated Impact |
| --- | --- |
| Transport Cost Reduction | 20-30% reduction in vehicle operating costs |
| Travel Time Savings | USD 5-10 million annually in time savings |
| Accident Reduction | 50% reduction in accident costs |
| Flood Damage Reduction | Significant reduction in flood-related damages |

## 6.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | TWUEP road network maps identify priority corridors; population growing 82,064 → 554,700 | Formal prioritisation & traffic study |
| Site / Land & Approvals | In progress | Existing & expansion road network mapped citywide | ROW survey and titling per route |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & design |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 40M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | Flood-risk zones mapped (TWUEP Ch.4) | ESIA and resettlement action plan |
| Revenue, O&M & Delivery Model | Gap | — | O&M budget and maintenance plan |
| Procurement / Transaction Plan | Gap | — | Transaction strategy & contractor sourcing |

### 6.5.1 Bankability Strengths

| Strength | Description |
| --- | --- |
| Strong Policy Support | Aligned with TWUEP and regional development plans |
| Clear Demand | Population growth and trade volumes demonstrate clear need |
| Strategic Location | Supports the Berbera corridor trade route |
| Climate Resilience | Addresses flood risks through improved drainage |
| Social Benefits | Improved safety and accessibility for all residents |

### 6.5.2 Bankability Gaps

| Gap | Description | Required Action |
| --- | --- | --- |
| Feasibility Study | No detailed feasibility study completed | Commission full feasibility study |
| Traffic Data | No formal traffic survey conducted | Conduct traffic and demand study |
| ESIA | Environmental assessment not completed | Commission ESIA and RAP |
| O&M Plan | No maintenance plan developed | Develop O&M budget and plan |

## 6.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | Public delivery — TWCA capital works programme |
| Operator & O&M | Municipal roads authority |
| Revenue / Cost Recovery | Municipal budget allocation; potential road-user fees |
| Funding Mix | Public capital budget + donor grant/concessional debt; TWCA own-source revenue supports O&M, not earmarked as capital |

### 6.6.1 Project Implementation Structure

text

┌─────────────────────────────────────────────────────────────┐

│                       PROJECT OVERSIGHT                      │

│                  Tog-Wajaale City Administration            │

│              (Mayor's Office / City Manager)                │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────────────┴────────────────────────────────────┐

│                    PROJECT MANAGEMENT                        │

│                 Project Director / Manager                   │

│           Urban Expansion Team / Technical Team             │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────┼────────────────┐

│                │                │

▼                ▼                ▼

┌───────────────┐ ┌───────────────┐ ┌───────────────┐

│  FEASIBILITY  │ │   DESIGN &    │ │  CONSTRUCTION │

│   & DESIGN    │ │   PLANNING    │ │  CONTRACTOR   │

│   CONSULTANT  │ │   CONSULTANT  │ │               │

└───────────────┘ └───────────────┘ └───────────────┘

## 6.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 01 (Urban Expansion) | Road network supports planned expansion areas |
| With Priority 03 (FTZ) | Access roads connect FTZ to the Berbera corridor and city centre |
| With Border Bridge | Complementary infrastructure for cross-border connectivity |
| With OSBP Implementation | Improved road access supports streamlined border procedures |
| With Priority 04 (Solid Waste) | Road access enables waste collection in expanded areas |
| With BRT Corridor | Road upgrade integrates with proposed BRT system |

## 6.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| Land acquisition & right-of-way clearance delays | Early land-use mapping; engage kebele and clan elders (Ugaas); transparent compensation |
| Flash flooding on riverbed-adjacent routes | Climate-resilient drainage, permeable pavements, elevated segments |
| Delay in detailed engineering | Early appointment of design consultant; dedicated feasibility budget line |
| Coordination with border infrastructure projects | Align with Togwajaale Bridge reconstruction and OSBP implementation timelines |
| Cost escalation | Phased implementation; fixed-price contracts; contingency provisions |
| Community opposition | Participatory planning; benefit-sharing; transparent communication |
| Inadequate maintenance funding | Dedicated O&M budget line; performance-based maintenance contracts |

## 6.9 Implementation Phasing

### 6.9.1 Phase 1: Feasibility & Design (2025-2026)

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Road Prioritisation Study | Months 1-3 | Project Director |
| Traffic Survey and Analysis | Months 2-5 | Transport Consultant |
| Feasibility Study | Months 3-8 | Feasibility Consultant |
| ESIA and RAP | Months 4-9 | Environmental Consultant |
| Detailed Design | Months 6-12 | Design Consultant |
| Procurement Preparation | Months 10-12 | Procurement Team |

### 6.9.2 Phase 2: Construction (2026-2029)

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Site Preparation | Months 1-3 | Contractor |
| Drainage Works | Months 3-9 | Contractor |
| Road Construction | Months 6-24 | Contractor |
| Sidewalks and NMT | Months 18-30 | Contractor |
| Lighting and Safety | Months 24-33 | Contractor |
| Landscaping | Months 30-36 | Contractor |

### 6.9.3 Phase 3: Commissioning & Handover (2029-2030)

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Testing and Commissioning | Months 34-36 | Contractor |
| Training | Months 34-36 | Contractor/Operator |
| Handover | Month 36 | Contractor/Project Team |
| Post-Implementation Review | Month 38 | Project Team |

## 6.10 Next Steps

### 6.10.1 Priority Action

Commission a Road Prioritisation & Feasibility Study

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / Urban Expansion Team |
| Estimated Cost | USD 300,000 - 500,000 |
| Expected Outcome | Prioritised road upgrade plan with detailed feasibility and cost estimates |

### 6.10.2 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Finalise road prioritisation criteria | Week 1-2 | Project Director | Clear prioritisation framework |
| Conduct preliminary traffic surveys | Week 2-6 | Transport Consultant | Traffic volume and demand data |
| Identify priority road sections | Week 4-8 | Urban Expansion Team | Prioritised road list |
| Prepare feasibility study TOR | Week 4-8 | Project Director | Consultant procurement ready |
| Engage stakeholders | Ongoing | Engagement Team | Community input and buy-in |
| Develop preliminary cost estimates | Week 8-12 | Infrastructure Specialist | Indicative project costs |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418
Mohammed Muhumed Ahmed – Infrastructure Development Specialist

Project Website: www.twuep.com.et