# 7. PRIORITY 03: INLAND SPECIAL TRADE ZONE & LOGISTICS HUB

## 7.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Inland Special Trade Zone & Logistics Hub |
| Description | A 50-hectare special trade zone and dry port adjacent to the border crossing |
| Indicative Investment | USD 250,000,000 (Birr 40,007,975,000)* |
| Sector | Trade & Industrial Infrastructure |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | PPP / Concession |
| Ranking Rationale | Economic Engine - Largest economic impact; leverages strategic location; creates 6,000+ jobs; catalytic for private investment |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 7.2 Strategic Rationale

### 7.2.1 The Opportunity

Cross-border traders and manufacturers at Tog-Wajaale lack a dedicated dry port, warehousing and customs-facilitation infrastructure. An informal FTZ has traded livestock, textiles and electronics since 2015, but rising bilateral trade with Somaliland has outpaced its unserviced footprint.

| Issue | Description |
| --- | --- |
| No Dedicated Dry Port | No formal container handling or logistics infrastructure |
| Limited Warehousing | Inadequate storage and distribution facilities |
| Customs Bottlenecks | No on-site customs facilitation |
| Informal Operations | Trade conducted without formal infrastructure |
| Growing Demand | Trade volumes increasing but infrastructure not keeping pace |

### 7.2.2 Why This is Priority #3

| Reason | Description |
| --- | --- |
| Economic Impact | Largest investment and job creation potential (~6,000 jobs) |
| Strategic Location | Leverages Tog-Wajaale's position on the Berbera corridor |
| Catalytic Effect | Attracts private investment and anchor tenants |
| Trade Facilitation | Enhances cross-border trade and regional integration |
| Revenue Generation | Significant revenue through land lease, service charges, and customs |

### 7.2.3 Strategic Location Benefits

| Element | Description |
| --- | --- |
| Distance from Hargeisa | ~90 km |
| Distance from Port of Berbera | ~249 km |
| Distance from Jigjiga | ~70 km |
| Distance from Harar | ~175 km |
| Corridor Role | Key node on the Berbera-to-Ethiopia economic corridor |
| Trade Volume | Handles approximately 95% of eastern Ethiopia's imports and exports |

### 7.2.4 Recent Major Infrastructure Developments

| Infrastructure Project | Details | Impact on FTZ |
| --- | --- | --- |
| Berbera-Tog-Wajaale Railway | UAE confirmed plans to finance a 250 km railway linking Tog-Wajaale to Berbera, project valued at USD 3 billion | Enhanced logistics connectivity; reduced transport costs |
| Togwajaale Border Bridge Reconstruction | TradeMark Africa launched reconstruction in May 2026 with Sweden funding through SWIFT Programme | Improved cross-border connectivity; facilitated trade |
| One-Stop Border Post (OSBP) | Feasibility study recommends a juxtaposed model for Tog-Wajaale OSBP; ongoing upgrades | Streamlined customs procedures; reduced delays |
| Berbera Corridor Road Upgrades | UAE pledged additional USD 100 million to upgrade the 250 km road connecting Berbera to Tog-Wajaale | Improved road access; reduced transport costs |
| Jigjiga-Tog Wajaale Power Transmission Line | 73.1 km 400kV double circuit transmission line proposed | Reliable power supply for industrial operations |

### 7.2.5 Trade Significance

| Element | Description |
| --- | --- |
| Market Operations | 24 hours a day, 7 days a week |
| Trade Types | Formal and informal trade |
| Key Commodities | Livestock, textiles, electronics, agricultural products |
| Cross-Border Trade | Increasing bilateral trade with Somaliland |
| Regional Hub | Serves as a gateway for trade in the Horn of Africa |

### 7.2.6 Investment Context

| Investment | Details | Relevance |
| --- | --- | --- |
| UAE Railway Investment | USD 3 billion for 250 km railway linking Tog-Wajaale to Berbera | Transformative connectivity; anchor for FTZ development |
| Berbera Corridor Road Investment | USD 100 million for road upgrades | Improved transport access; reduced logistics costs |
| UK/EU Corridor Funding | USD 16.6 million (UK) + EU investment in Berbera-Hargeisa-Togwajaale highway | Enhanced regional connectivity |
| IGAD RMF Investment | Germany €8 million grant for migration corridor infrastructure | Complementary development; community benefits |

## 7.3 Project Scope

### 7.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Dry Port & Logistics Hub | Container handling, customs clearance, logistics | 70,000,000 | 11,202,233,000 |
| Warehousing & Distribution Parks | Storage and distribution facilities | 50,000,000 | 8,001,595,000 |
| Industrial Parks & Manufacturing Zones | Production and processing facilities | 60,000,000 | 9,601,914,000 |
| Customs & Trade Facilitation | On-site customs clearance and trade services | 30,000,000 | 4,800,957,000 |
| Commercial & Business Services | Office space, retail, and support services | 20,000,000 | 3,200,638,000 |
| Supporting Utilities | Power, water, telecommunications | 20,000,000 | 3,200,638,000 |
| TOTAL |  | 250,000,000 | 40,007,975,000 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 7.3.2 Component Details

1. Dry Port & Logistics Hub (USD 70,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Container Handling | Container yard and handling equipment | 20,000+ TEU capacity |
| Customs Clearance | On-site customs clearance facilities | Integrated customs services |
| Logistics Services | Logistics and freight forwarding services | Full-service logistics hub |
| Storage Facilities | General and specialized storage | 50,000+ sqm storage |
| Container Yard | Container storage and handling | 5+ ha container yard |

2. Warehousing & Distribution Parks (USD 50,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| General Warehousing | Standard warehousing facilities | 100,000+ sqm |
| Cold Storage | Temperature-controlled storage | 20,000+ sqm cold storage |
| Distribution Centre | Central distribution facilities | Full logistics services |
| Value-Added Services | Packaging, labelling, processing | Value-added logistics |

3. Industrial Parks & Manufacturing Zones (USD 60,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Manufacturing Facilities | Production and assembly facilities | 50,000+ sqm factory space |
| Agro-Processing | Agricultural processing facilities | Food processing; livestock |
| Textile & Garment | Textile and garment production | Garment manufacturing |
| Light Manufacturing | Light industrial facilities | Electronics; assembly |

4. Customs & Trade Facilitation (USD 30,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Customs Facilities | Customs clearance offices | Full-service customs |
| Trade Services | Trade facilitation services | One-stop trade services |
| Inspection Facilities | Quality control and inspection | Quality assurance |
| Administration | Administrative offices | FTZ management |

5. Commercial & Business Services (USD 20,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Office Buildings | Business and administrative offices | 20,000+ sqm |
| Retail Spaces | Commercial and retail areas | 10,000+ sqm |
| Banking Services | Financial services | Full banking services |
| Business Support | Business advisory and support | Business incubation |

6. Supporting Utilities (USD 20,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Power Supply | Reliable electricity supply | 20+ MW capacity |
| Water Supply | Clean water for industrial use | 5,000+ m³/day |
| Telecommunications | High-speed connectivity | Fiber optic connectivity |
| Waste Management | Industrial waste management | Treatment facilities |

## 7.4 Value Creation

### 7.4.1 Expected Outcomes

| Outcome | Target | Measurement |
| --- | --- | --- |
| Jobs Created | ~6,000 direct and indirect jobs | Employment records |
| Companies Established | 100+ companies | FTZ registration |
| Trade Volume | USD 500 million+ annually | Customs records |
| Tax Revenue | USD 50 million+ annually | Revenue records |
| Economic Growth | 5%+ contribution to city GDP | Economic analysis |
| Projected City Population Served (2055) | 554,700 | Census data |

### 7.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Economic Diversification | Diversifies economy beyond traditional trade and agriculture |
| Regional Integration | Strengthens Ethiopia-Somaliland trade ties |
| Investment Attraction | Attracts domestic and foreign direct investment |
| Technology Transfer | Facilitates technology transfer and skills development |
| Value Addition | Promotes value addition to local products |
| Foreign Exchange | Generates foreign exchange through exports |

### 7.4.3 Social Impact

| Impact | Description |
| --- | --- |
| Women's Employment | 40% target for women in employment |
| Youth Employment | Significant youth employment opportunities |
| Host Community Benefits | Benefits for displaced persons and host communities |
| Skills Development | Training and skills development for local workforce |
| Community Investment | Infrastructure and services benefiting local communities |

## 7.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | Informal FTZ trading since 2015; TWUEP names cross-border SEZs a priority; pop. growing 82,064 → 554,700 | Formal market / tenant demand study |
| Site / Land & Approvals | In progress | Indicative 50 ha site identified adjacent to border crossing | Land survey, titling and zoning approval |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & master plan |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 250M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | — | ESIA and safeguard instruments |
| Revenue, O&M & Delivery Model | Gap | — | Financial model, lease/tariff structure |
| Procurement / Transaction Plan | Gap | — | Transaction strategy & investor/operator sounding |

### 7.5.1 Bankability Strengths

| Strength | Description |
| --- | --- |
| Strategic Location | Prime position on the Berbera trade corridor |
| Demand Evidence | Informal FTZ trading since 2015 demonstrates demand |
| Infrastructure Pipeline | Confirmed investments in railway, road, and bridge |
| Policy Support | TWUEP prioritizes cross-border SEZs |
| Revenue Potential | Significant revenue through land lease and customs |
| PPP Suitability | Attractive for private sector investment |

### 7.5.2 Bankability Gaps

| Gap | Description | Required Action |
| --- | --- | --- |
| Market Study | No formal tenant demand study | Commission market and demand study |
| Feasibility Study | No detailed feasibility analysis | Commission full feasibility study |
| ESIA | Environmental assessment not completed | Commission ESIA and safeguards |
| Financial Model | No detailed financial model | Develop financial model |
| PPP Structure | No PPP framework developed | Engage PPP advisor |

## 7.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | PPP / concession via a dedicated Special Purpose Vehicle (SPV) |
| Operator & O&M | Private concessionaire responsible for zone operations & maintenance |
| Revenue / Cost Recovery | Land lease, service charges and tenant fees |
| Funding Mix | Private equity/debt + government land as equity-in-kind; TWCA own-source revenue (ETB 144M FY2018EC - ETB 195M FY2019EC - USD 0.9-1.2M) supports capacity, not zone capital |

### 7.6.1 Recommended PPP Structure

text

┌─────────────────────────────────────────────────────────────┐

│                       PROJECT OVERSIGHT                      │

│                  Tog-Wajaale City Administration            │

│              (Mayor's Office / City Manager)                │

└────────────────────────┬────────────────────────────────────┘

│

│ Concession Agreement

▼

┌─────────────────────────────────────────────────────────────┐

│                    CONCESSIONAIRE (SPV)                      │

│              Private Consortium (Equity Investors)           │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────┼────────────────┐

│                │                │

▼                ▼                ▼

┌───────────────┐ ┌───────────────┐ ┌───────────────┐

│    DESIGN     │ │ CONSTRUCTION  │ │  OPERATIONS   │

│   CONTRACTOR  │ │  CONTRACTOR   │ │    & O&M      │

└───────────────┘ └───────────────┘ └───────────────┘

### 7.6.2 Revenue Streams

| Revenue Source | Description | Estimated Annual Revenue (USD) |
| --- | --- | --- |
| Land Leases | Lease payments for industrial/commercial plots | 5,000,000 |
| Infrastructure Fees | Fees for utilities and infrastructure services | 3,000,000 |
| Service Charges | Management and service fees | 2,000,000 |
| Customs Revenue | Import/export duties (government share) | 10,000,000 |
| Tax Revenue | Corporate and income tax (government share) | 15,000,000 |
| Rental Income | Building and facility rentals | 5,000,000 |
| TOTAL |  | 40,000,000 |

## 7.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 01 (Urban Expansion) | New housing and services for FTZ workers |
| With Priority 02 (Corridor Upgrade) | Access roads connect FTZ to the Berbera corridor |
| With Priority 04 (Solid Waste) | Waste services for FTZ and industrial facilities |
| With Priority 05 (Youth Centre) | Skilled workforce for FTZ industries |
| With Priority 06 (Reception Centre) | Employment opportunities for returnees |
| With Border Bridge | Enhanced connectivity and trade facilitation |
| With OSBP Implementation | Streamlined customs procedures for FTZ operations |
| With Berbera Railway | Enhanced logistics connectivity |

## 7.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| FTZ investor / tenant demand uptake | Anchor tenant pre-agreements; phased development from a serviced first phase; market sounding study |
| Cross-border customs & bilateral coordination | Formal MOU with customs and border authorities; phased licensing aligned with bilateral trade talks |
| Land acquisition & resettlement within zone footprint | Early resettlement action plan (RAP); TWCA/regional coordination ahead of construction |
| Competition from other FTZs | Unique value proposition; competitive incentives |
| Infrastructure delivery delays | Phased implementation; experienced developers |
| Political instability in border region | Strong bilateral framework; diplomatic engagement |
| Currency fluctuation | Currency hedging; indexation mechanisms |
| Financial viability | Anchor tenants; diversified revenue streams |

## 7.9 Implementation Phasing

### 7.9.1 Phase 1: Feasibility & Planning (2025-2026)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Market & Tenant Demand Study | Months 1-6 | Consultant | 200,000 |
| Feasibility Study & Master Plan | Months 3-9 | Consultant | 400,000 |
| ESIA and Safeguards | Months 4-9 | Consultant | 250,000 |
| PPP Structuring | Months 6-12 | PPP Advisor | 300,000 |
| Financial Model | Months 6-12 | Consultant | 200,000 |
| TOTAL |  |  | 1,350,000 |

### 7.9.2 Phase 2: Site Development (2027-2029)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Land Acquisition | Months 1-6 | Legal Team | 15,000,000 |
| Site Preparation | Months 3-9 | Contractor | 20,000,000 |
| Infrastructure Development | Months 6-24 | Contractor | 50,000,000 |
| Dry Port & Logistics Hub | Months 12-24 | Contractor | 40,000,000 |
| TOTAL |  |  | 125,000,000 |

### 7.9.3 Phase 3: Facility Development (2029-2031)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Warehousing & Distribution | Months 18-30 | Contractor | 30,000,000 |
| Industrial Parks | Months 24-36 | Contractor | 40,000,000 |
| Commercial Facilities | Months 24-36 | Contractor | 20,000,000 |
| Supporting Utilities | Months 18-30 | Contractor | 15,000,000 |
| TOTAL |  |  | 105,000,000 |

### 7.9.4 Phase 4: Operationalization (2031-2035)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Tenant Acquisition | Ongoing | Operator | - |
| Full Operations | 2033+ | Operator | - |
| Phased Expansion | 2031-2035 | Developer | 18,650,000 |
| TOTAL |  |  | 18,650,000 |

## 7.10 Next Steps

### 7.10.1 Priority Action

Launch a Formal Market & Tenant Demand Study

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / Urban Expansion Team |
| Estimated Cost | USD 150,000 - 250,000 |
| Expected Outcome | Evidence base for investor engagement and PPP structuring |

### 7.10.2 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Finalise market study TOR | Week 1-3 | Project Director | Consultant procurement ready |
| Engage potential anchor tenants | Week 2-8 | Investment Specialist | Letters of intent from tenants |
| Conduct preliminary investor sounding | Week 4-10 | Project Director | Investor interest assessment |
| Identify PPP advisor | Week 4-8 | Procurement Team | PPP advisor engaged |
| Develop preliminary financial model | Week 8-12 | Financial Specialist | Initial financial projections |
| Engage stakeholders | Ongoing | Engagement Team | Community and business input |

### 7.10.3 Immediate Actions

| Action | Responsible | Timeline |
| --- | --- | --- |
| Formalise MOU with customs and border authorities | Mayor's Office | 0-60 days |
| Confirm 50 ha site location and zoning | GIS Department | 0-45 days |
| Engage TradeMark Africa for corridor coordination | Project Director | 0-30 days |
| Launch market study procurement | Procurement Team | 0-30 days |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418

Project Website: www.twuep.com.et