TOG-WAJAALE EACC PRIORITY INVESTMENT PROJECT

Final Comprehensive Project Report

Prepared For:
Mahamud Yusuf Adan
Mayor, Tog-Wajaale City Administration
+251 915 330528

Abdikarim Hassen Yusuf
City Manager, Tog-Wajaale City Administration
+251 915 074535

Project Team:

- Shemshedin Hassen Yusuf – Project Director / Manager

- Mohammed Muhumed Ahmed – Infrastructure Development Specialist

- Mohammed Isse Muhumed – Environmental Compliance Officer

- Abdiwasac Khaliif Muhumed – GIS & Surveying Department

Project Website: www.twuep.com.et

Submitted By:
Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

# Table of Contents

LIST OF ACRONYMS AND ABBREVIATIONS
Executive Summary
CHAPTER ONE: INTRODUCTION
    1.1 BACKGROUND AND CONTEXT
    1.2 PROBLEM STATEMENT
    1.3 PROJECT RATIONALE
    1.4 PROJECT OBJECTIVES
    1.5 SCOPE OF THE REPORT
    1.6 STRUCTURE OF THE REPORT
CHAPTER TWO: PROJECT CONTEXT AND STRATEGIC FRAMEWORK
    2.1 TOG-WAJAALE CITY OVERVIEW
    2.2 DEMOGRAPHIC PROFILE AND GROWTH TRENDS
    2.3 ECONOMIC CONTEXT AND TRADE SIGNIFICANCE
    2.4 URBAN INFRASTRUCTURE CHALLENGES
    2.5 THE ETHIO-BERBERA CORRIDOR OPPORTUNITY
    2.6 STRATEGIC ALIGNMENT WITH URBAN EXPANSION PLAN
    2.7 LEGAL AND POLICY FRAMEWORK
CHAPTER THREE: PROJECT DESCRIPTION AND TECHNICAL SCOPE
    3.1 PORTFOLIO OVERVIEW
    3.2 PRIORITY 01: PLANNED URBAN EXPANSION PROGRAMME
    3.3 PRIORITY 02: CORRIDOR & ARTERIAL ROAD UPGRADE
    3.4 PRIORITY 03: INLAND SPECIAL TRADE ZONE & LOGISTICS HUB
    3.5 PRIORITY 04: SOLID WASTE MANAGEMENT SYSTEM
    3.6 PRIORITY 05: YOUTH SKILLS, ENTERPRISE & MIGRATION CENTRE
    3.7 PRIORITY 06: RECEPTION & REINTEGRATION CENTRE
    3.8 PROJECT SYNERGIES AND INTEGRATION
CHAPTER FOUR: PRIORITIZATION METHODOLOGY AND DETAILED PROJECT PROFILES
    4.1 Prioritization Framework
    4.2 Project Scoring Matrix
    4.3 Ranking Summary
    4.4 Classification System
    4.5 Detailed Ranking Rationale
    4.6 Implementation Sequencing Rationale
    4.7 Summary of Prioritization
    4.8 PRIORITY 01: PLANNED URBAN EXPANSION PROGRAMME — DETAILED PROFILE
    4.9 PRIORITY 02: CORRIDOR & ARTERIAL ROAD UPGRADE — DETAILED PROFILE
    4.10 PRIORITY 03: INLAND SPECIAL TRADE ZONE & LOGISTICS HUB — DETAILED PROFILE
    4.11 PRIORITY 04: SOLID WASTE MANAGEMENT SYSTEM — DETAILED PROFILE
    4.12 PRIORITY 05: YOUTH SKILLS, ENTERPRISE & MIGRATION CENTRE — DETAILED PROFILE
    4.13 PRIORITY 06: RECEPTION & REINTEGRATION CENTRE — DETAILED PROFILE
CHAPTER FIVE: INVESTMENT REQUIREMENTS AND FINANCIAL ANALYSIS
    5.1 TOTAL PORTFOLIO COST ESTIMATE
    5.2 FINANCING REQUIREMENTS
    5.3 MUNICIPAL REVENUE CONTEXT
    5.4 POTENTIAL REVENUE SOURCES
    5.5 FINANCIAL MODEL FRAMEWORK
    5.6 COST-BENEFIT ANALYSIS
CHAPTER SIX: READINESS ASSESSMENT AND BANKABILITY ANALYSIS
    6.1 CURRENT READINESS STAGE
    6.2 STRENGTHS AND OPPORTUNITIES
    6.3 WEAKNESSES AND GAPS
    6.4 BANKABILITY ASSESSMENT
    6.5 GAP ANALYSIS AND REQUIREMENTS FOR BANKABILITY
CHAPTER SEVEN: RISK ASSESSMENT AND MITIGATION STRATEGIES
    7.1 RISK MANAGEMENT FRAMEWORK
    7.2 POLITICAL AND REGULATORY RISKS
    7.3 FINANCIAL RISKS
    7.4 TECHNICAL AND OPERATIONAL RISKS
    7.5 ENVIRONMENTAL RISKS
    7.6 SOCIAL AND COMMUNITY RISKS
    7.7 INSTITUTIONAL AND CAPACITY RISKS
    7.8 RISK ALLOCATION IN PPP STRUCTURE
CHAPTER EIGHT: FINANCING AND PARTNERSHIP STRUCTURE
    8.1 RECOMMENDED DELIVERY MODEL
    8.2 RECOMMENDED FINANCING STRUCTURE
    8.3 POTENTIAL PARTNERS
    8.4 PARTNERSHIP ENGAGEMENT STRATEGY
CHAPTER NINE: IMPLEMENTATION ROADMAP
    9.1 IMPLEMENTATION TIMELINE
    9.2 PHASE 0: PROJECT PREPARATION (2024-2025)
    9.3 PHASE 1: FOUNDATION AND DESIGN (2025-2027)
    9.4 PHASE 2: IMPLEMENTATION AND GROWTH (2028-2030)
    9.5 PHASE 3: CONSOLIDATION AND EXPANSION (2031-2035)
    9.6 CRITICAL PATH MILESTONES
CHAPTER TEN: NEXT STEPS AND 90-DAY ACTION PLAN
    10.1 PRIORITY ACTIONS
    10.2 ACTION 1: COMMISSION FEASIBILITY STUDIES
    10.3 ACTION 2: INITIATE ENVIRONMENTAL IMPACT ASSESSMENTS
    10.4 ACTION 3: ENGAGE POTENTIAL FINANCIERS
    10.5 ACTION 4: ENGAGE POTENTIAL PRIVATE OPERATORS AND PARTNERS
    10.6 ACTION 5: UPDATE PROJECT BRIEFS
    10.7 ACTION 6: ESTABLISH PROJECT IMPLEMENTATION UNIT
    10.8 MONITORING AND REPORTING FRAMEWORK
CHAPTER ELEVEN: CONCLUSION AND RECOMMENDATIONS
    11.1 SUMMARY OF FINDINGS
    11.2 KEY RECOMMENDATIONS
    11.3 CONCLUSION
References
Appendices
APPENDIX A: PROJECT CONTACT INFORMATION
APPENDIX B: KEY REFERENCE DOCUMENTS
APPENDIX C: DETAILED COST ESTIMATES (UPDATED)
APPENDIX D: STAKEHOLDER ENGAGEMENT PLAN
APPENDIX E: MONITORING AND EVALUATION FRAMEWORK

# LIST OF ACRONYMS AND ABBREVIATIONS

| Acronym | Full Form |
| --- | --- |
| AfDB | African Development Bank |
| BOQ | Bill of Quantities |
| BRT | Bus Rapid Transit |
| CBA | Cost-Benefit Analysis |
| CBO | Community-Based Organization |
| CSA | Central Statistical Agency |
| DFI | Development Finance Institution |
| EACC | East Africa City Corridor |
| E.C. | Ethiopian Calendar |
| EIA | Environmental Impact Assessment |
| ESIA | Environmental and Social Impact Assessment |
| ETB | Ethiopian Birr |
| EU | European Union |
| FTZ | Free Trade Zone |
| G.C. | Gregorian Calendar |
| GDP | Gross Domestic Product |
| GIS | Geographic Information Systems |
| ha | Hectare |
| IDP | Internally Displaced Person |
| IFC | International Finance Corporation |
| IGAD | Intergovernmental Authority on Development |
| IOM | International Organization for Migration |
| ITS | Intelligent Transport Systems |
| km | Kilometer |
| M&E | Monitoring and Evaluation |
| MOU | Memorandum of Understanding |
| MRC | Migration Response Centre |
| NGO | Non-Governmental Organization |
| NMT | Non-Motorized Transport |
| O&M | Operations and Maintenance |
| OSBP | One-Stop Border Post |
| OWDA | Organization for Welfare and Development in Action |
| p/ha | People per Hectare |
| PPP | Public-Private Partnership |
| RAP | Resettlement Action Plan |
| RMF | Regional Migration Fund |
| ROW | Right-of-Way |
| SCI | Save the Children International |
| SDC | Swiss Agency for Development and Cooperation |
| SDG | Sustainable Development Goal |
| SEZ | Special Economic Zone |
| SPV | Special Purpose Vehicle |
| TWCA | Tog-Wajaale City Administration |
| TWUEP | Tog-Wajaale Urban Expansion Plan |
| UAE | United Arab Emirates |
| UNDP | United Nations Development Programme |
| UNHCR | United Nations High Commissioner for Refugees |
| USD | United States Dollar |

# Executive Summary

## E.1 Portfolio Overview

The Tog-Wajaale EACC Priority Investment Project comprises six strategic infrastructure and development projects identified through the East Africa City Corridor (EACC) Dialogue. These investments are designed to transform Tog-Wajaale into a regional economic hub, enhance urban livability, create employment opportunities, and support sustainable urban development.

All projects are aligned with the Tog-Wajaale Urban Expansion Plan (TWUEP) 2025-2055, a 30-year urban framework endorsed by the Tog-Wajaale City Administration, Somali Regional State, Cities Alliance, and UNDP. The plan guides three decades of infrastructure, housing, and economic growth for this critical trade gateway in the Somali Regional State of Ethiopia.

## E.2 Portfolio Summary

| Priority | Project | Investment (USD) | Investment (Birr)* | Classification |
| --- | --- | --- | --- | --- |
| 01 | Planned Urban Expansion Programme | 63,000,000 | 10,082,009,700 | Foundation |
| 02 | Corridor & Arterial Road Upgrade | 40,000,000 | 6,401,276,000 | Connectivity |
| 03 | Inland Special Trade Zone & Logistics Hub | 250,000,000 | 40,007,975,000 | Economic Engine |
| 04 | Solid Waste Management System | 10,000,000 | 1,600,319,000 | Livability |
| 05 | Youth Skills, Enterprise & Migration Centre | 10,000,000 | 1,600,319,000 | Human Capital |
| 06 | Reception & Reintegration Centre | 7,000,000 | 1,120,223,300 | Social Protection |
| TOTAL |  | 380,000,000 | 60,812,122,000 |  |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## E.3 Key Findings

| Finding | Description |
| --- | --- |
| Foundation First | Urban Expansion (Priority 01) must precede other investments to create serviced land and framework |
| Connectivity Second | Road upgrades (Priority 02) are essential for access to all other investments |
| Economic Engine Third | FTZ (Priority 03) delivers largest economic impact but requires foundation and connectivity |
| Livability Fourth | Solid waste (Priority 04) addresses immediate public health and environmental needs |
| Human Capital Fifth | Youth Centre (Priority 05) develops workforce for FTZ and other opportunities |
| Social Protection Sixth | Reception Centre (Priority 06) supports vulnerable returnees |

## E.4 Strategic Importance

Tog-Wajaale serves as the primary border crossing for goods moving between Ethiopia and Somaliland along the Berbera Corridor. The corridor links the Port of Berbera to eastern Ethiopia via Hargeisa and Tog-Wajaale, providing landlocked Ethiopia with a critical trade route alternative to Djibouti.

Recent major infrastructure developments have reinforced the strategic importance of Tog-Wajaale:

| Infrastructure Project | Details |
| --- | --- |
| Berbera-Tog-Wajaale Railway | UAE confirmed plans to finance a 250 km railway linking Tog-Wajaale to Berbera, project valued at USD 3 billion |
| Tog-Wajaale Border Bridge Reconstruction | TradeMark Africa launched reconstruction in May 2026 with Sweden funding through SWIFT Programme |
| One-Stop Border Post (OSBP) | Feasibility study recommends a juxtaposed model for Tog-Wajaale OSBP; ongoing upgrades |
| Berbera Corridor Road Upgrades | UAE pledged additional USD 100 million to upgrade the 250 km road connecting Berbera to Tog-Wajaale |
| Jigjiga-Tog-Wajaale Power Transmission Line | 73.1 km 400kV double circuit transmission line proposed |

## E.5 Key Recommendations

| Recommendation | Priority | Timeline |
| --- | --- | --- |
| Commission feasibility studies for all projects | Critical | 0-6 months |
| Prioritize Urban Expansion (Priority 01) as Phase 1 foundation | High | Immediate |
| Pursue road upgrade (Priority 02) as Phase 1 connectivity | High | Immediate |
| Develop PPP framework for FTZ (Priority 03) | High | 0-12 months |
| Engage development partners for solid waste (Priority 04) | Medium | 0-12 months |
| Leverage IGAD RMF and Cities Alliance for social projects (Priority 05, 06) | Medium | 0-12 months |
| Establish Project Implementation Unit | Critical | Immediate |

# CHAPTER ONE: INTRODUCTION

## 1.1 BACKGROUND AND CONTEXT

Tog-Wajaale City, located in the Somali Regional State of Ethiopia, has experienced remarkable transformation over the past three decades. Evolving from a small trading Kebele into a dynamic urban administrative center, the city now serves as a critical node on the Ethio-Berbera trade corridor, connecting landlocked Ethiopia to the Port of Berbera in Somaliland.

The city's strategic location, approximately 90 kilometers from Hargeisa and 249 kilometers from the Port of Berbera, positions it as a key gateway for regional trade. This has fueled rapid population growth, with the city's population increasing from 8,000 in 1994 to 82,064 in 2024—a growth of over 1,000% in three decades. Projections indicate this trend will continue, with the population expected to reach 119,000 by 2030 and 554,700 by 2055.

This rapid urbanization has created significant opportunities for economic development but has also placed immense strain on the city's infrastructure. Current road networks, public transport systems, and utilities are insufficient to meet the needs of the growing population. The absence of a formalized public transport system has led to reliance on informal, inefficient private transportation, contributing to congestion along the critical Ethio-Berbera corridor and undermining its potential to reduce logistics costs.

Recognizing these challenges, the Tog-Wajaale City Administration, in collaboration with the Somali Regional Government and supported by international partners, has developed the Tog-Wajaale Urban Expansion Plan (TWUEP) 2025-2055. This comprehensive plan provides a framework for sustainable urban development, addressing infrastructure deficits, promoting economic growth, and enhancing quality of life for residents.

The Tog-Wajaale EACC Priority Investment Project represents the next phase of this planning process—a comprehensive set of six strategic projects identified through the East Africa City Corridor (EACC) Dialogue. These investments are designed to transform Tog-Wajaale into a regional economic hub, enhance urban livability, create employment opportunities, and support sustainable urban development.

## 1.2 PROBLEM STATEMENT

Tog-Wajaale faces critical development challenges that threaten to undermine its economic potential and quality of life:

### 1.2.1 Unmanaged Urban Growth

Tog-Wajaale's built-up area is projected to grow 12.6-fold by 2055, with population rising from 82,064 to 554,700. Without planned expansion, this growth risks repeating the overcrowded informal settlement pattern seen in the city's past growth. The city lacks serviced land, adequate housing, and planned infrastructure to accommodate this growth.

### 1.2.2 Infrastructure Deficits

The city's road network, while relatively developed in the city center, is outdated and insufficient for anticipated population growth. The connecting roads to Awbare and Hartishekh remain unpaved, limiting accessibility and economic opportunities. The lack of a formalized public transport system results in heavy reliance on private vehicles, contributing to congestion and environmental degradation.

### 1.2.3 Limited Economic Infrastructure

Cross-border traders and manufacturers at Tog-Wajaale lack a dedicated dry port, warehousing and customs-facilitation infrastructure. An informal FTZ has traded livestock, textiles and electronics since 2015, but rising bilateral trade with Somaliland has outpaced its unserviced footprint. The city lacks the industrial infrastructure to add value to local products and create sustainable employment.

### 1.2.4 Environmental and Health Challenges

Tog-Wajaale has no engineered landfill, formal collection fleet or recycling capacity. Uncollected waste accumulates in open sites and waterways, posing health and environmental risks that will intensify as population grows toward 554,700 by 2055.

### 1.2.5 Social and Human Capital Gaps

With a young and fast-growing population and Tog-Wajaale a key migration corridor, young people lack access to formal skills training, enterprise support and safe migration information - pushing many toward irregular, high-risk migration routes. Additionally, as Ethiopia's busiest land crossing to Somaliland, Tog-Wajaale receives significant numbers of returning migrants with no dedicated reception facility. Returnees currently lack accommodation, psychosocial support or a structured pathway to reintegration.

## 1.3 PROJECT RATIONALE

The Tog-Wajaale EACC Priority Investment Project addresses these challenges through an integrated approach that:

### 1.3.1 Manages Urban Growth

By developing a planned urban expansion programme, the portfolio provides serviced land, housing, and infrastructure to accommodate the city's 576% population increase. This prevents unplanned sprawl and informal settlements.

### 1.3.2 Enhances Connectivity

By upgrading 20 km of arterial roads, the portfolio provides access to the FTZ, urban expansion areas, and the Ethio-Berbera trade corridor. This reduces transport costs and transit times.

### 1.3.3 Drives Economic Development

By developing a 50-hectare Inland Special Trade Zone and Logistics Hub, the portfolio creates a regional trade and logistics hub that attracts investment, creates jobs (6,000+), and diversifies the local economy.

### 1.3.4 Ensures Environmental Sustainability

By establishing a citywide solid waste management system, the portfolio addresses public health and environmental challenges, creating a clean and livable city.

### 1.3.5 Builds Human Capital

By establishing a Youth Skills, Enterprise & Migration Centre, the portfolio addresses youth unemployment and irregular migration, building the workforce needed for the FTZ and other economic opportunities.

### 1.3.6 Supports Vulnerable Populations

By establishing a Reception & Reintegration Centre, the portfolio provides dignified support and livelihood opportunities for returning migrants, supporting social protection and stability.

## 1.4 PROJECT OBJECTIVES

### 1.4.1 Overall Objective

To transform Tog-Wajaale into a vibrant, sustainable, and inclusive city by delivering six strategic infrastructure and development projects that create economic opportunities, enhance urban livability, and support sustainable development.

### 1.4.2 Specific Objectives

| Objective | Description |
| --- | --- |
| Foundation | Deliver Planned Urban Expansion Programme to create serviced land and framework for all other investments |
| Connectivity | Deliver Corridor & Arterial Road Upgrade to provide access and mobility |
| Economic Development | Deliver Inland Special Trade Zone & Logistics Hub to drive growth and job creation |
| Environmental Sustainability | Deliver Solid Waste Management System to ensure a clean and healthy city |
| Human Capital Development | Deliver Youth Skills, Enterprise & Migration Centre to build workforce and address migration |
| Social Protection | Deliver Reception & Reintegration Centre to support vulnerable returnees |

## 1.5 SCOPE OF THE REPORT

This comprehensive report provides a detailed analysis of the Tog-Wajaale EACC Priority Investment Project, covering:

| Chapter | Content |
| --- | --- |
| Chapter One | Introduction and background |
| Chapter Two | Project context and strategic framework |
| Chapter Three | Project description and technical scope for all six projects |
| Chapter Four | Prioritization methodology and detailed project profiles |
| Chapter Five | Investment requirements and financial analysis |
| Chapter Six | Readiness assessment and bankability analysis |
| Chapter Seven | Risk assessment and mitigation strategies |
| Chapter Eight | Financing and partnership structure |
| Chapter Nine | Implementation roadmap |
| Chapter Ten | Next steps and 90-day action plan |
| Chapter Eleven | Conclusion and recommendations |

## 1.6 STRUCTURE OF THE REPORT

The report is organized into eleven chapters:

| Chapter | Title | Description |
| --- | --- | --- |
| 1 | Introduction | Provides background, problem statement, rationale, objectives, and report scope |
| 2 | Project Context and Strategic Framework | Analyzes Tog-Wajaale’s demographic, economic, and infrastructural context and alignment with strategic plans |
| 3 | Project Description and Technical Scope | Details all six portfolio projects, their components, and expected outcomes |
| 4 | Prioritization Methodology and Detailed Project Profiles | Presents the weighted scoring methodology, project ranking, and a full detailed profile for each of the six priority projects |
| 5 | Investment Requirements and Financial Analysis | Presents cost estimates, financing requirements, revenue sources, and financial analysis |
| 6 | Readiness and Bankability Assessment | Evaluates project readiness and identifies gaps and requirements for bankability |
| 7 | Risk Assessment and Mitigation Strategies | Provides comprehensive risk analysis and mitigation strategies |
| 8 | Financing and Partnership Structure | Recommends delivery models, financing structures, and potential partners |
| 9 | Implementation Roadmap | Outlines phased implementation and critical milestones |
| 10 | Next Steps and 90-Day Action Plan | Details priority actions for advancing all projects |
| 11 | Conclusion and Recommendations | Summarizes findings and provides key recommendations |

# CHAPTER TWO: PROJECT CONTEXT AND STRATEGIC FRAMEWORK

## 2.1 TOG-WAJAALE CITY OVERVIEW

### 2.1.1 Location and Geography

Tog-Wajaale City is located in the Somali Regional State of Ethiopia, specifically within the Tog-Wajaale Woreda of the Fafen Zone. It is situated approximately:

| Element | Value |
| --- | --- |
| Distance from Hargeisa | ~90 km |
| Distance from Port of Berbera | ~249 km |
| Distance from Jigjiga | ~70 km |
| Distance from Harar | ~175 km |
| Coordinates | 38P 1061474.60m N, 316716.77m E |
| Elevation | 1,510 to 1,615 meters |

### 2.1.2 Administrative Structure

Tog-Wajaale was established as a city administrative center in 2009 E.C. (Ethiopian Calendar). It includes 20 kebele administrations, with:

| Area | Number of Kebele |
| --- | --- |
| Built-up Areas | 7 kebele |
| Peripheral Regions | 13 kebele |
| Total | 20 kebele |

### 2.1.3 Climate and Environment

Tog-Wajaale experiences a hot semi-arid climate with:

| Parameter | Details |
| --- | --- |
| Climate Type | Hot semi-arid |
| Temperature | 28°C to 35°C (daytime) |
| Rainfall | 300-500 mm annually |
| Rainy Seasons | Gu (April-June), Deyr (October-November) |
| Key Risks | Droughts, flash floods, desertification, dust storms |

## 2.2 DEMOGRAPHIC PROFILE AND GROWTH TRENDS

### 2.2.1 Population Growth

Tog-Wajaale has experienced remarkable population growth over the past three decades:

| Period | Population | Growth Rate | Area (ha) | Density (p/ha) |
| --- | --- | --- | --- | --- |
| 1994 | 8,000 | - | 80 | 100.00 |
| 2007 | 14,800 | 85.0% | 138 | 107.25 |
| 2015 | 46,454 | 213.9% | 469 | 99.04 |
| 2024 | 82,064 | 76.6% | 711 | 115.42 |
| 2030 (Projected) | 119,000 | 45.0% | 1,450 | 82.07 |
| 2055 (Projected) | 554,700 | 366.0% | 8,990 | 61.70 |

Source: Tog-Wajaale Urban Expansion Plan (2025-2055)

### 2.2.2 Urban Area Expansion

| Period | Area (ha) | Expansion Factor |
| --- | --- | --- |
| 1994 | 80 | 1.0x |
| 2007 | 138 | 1.7x |
| 2015 | 469 | 5.9x |
| 2024 | 711 | 8.9x |
| 2055 | 8,990 | 112.4x |

### 2.2.3 Key Growth Drivers

| Driver | Description |
| --- | --- |
| Strategic Location | Positioned on Ethio-Berbera trade corridor; proximity to Port of Berbera |
| Economic Opportunities | Free Trade Zone; cross-border trade; growing commercial sector |
| Rural-Urban Migration | Push factors (drought, land degradation); pull factors (jobs, education, healthcare) |
| Infrastructure Development | Investments in roads, utilities, and public services |
| Government Policies | Decentralization; promotion of secondary cities |
| Demographics | Youthful population (60% under 25); high natural increase |

## 2.3 ECONOMIC CONTEXT AND TRADE SIGNIFICANCE

### 2.3.1 Economic Profile

Tog-Wajaale's economy is characterized by:

| Sector | Description |
| --- | --- |
| Trade and Commerce | The city serves as a commercial hub for the region, with significant cross-border trade with Somaliland |
| Free Trade Zone | Established after 2015, facilitating trade in livestock, textiles, and electronics |
| Informal Trade | Thriving informal trade networks (franco valuta) |
| Emerging Sectors | Growing potential in logistics, agro-processing, manufacturing, and commercial real estate |
| Employment | Trade, transportation, services, and small-scale manufacturing |

### 2.3.2 The Ethio-Berbera Corridor

The Ethio-Berbera Corridor represents a transformative opportunity for Tog-Wajaale:

| Aspect | Significance |
| --- | --- |
| Trade Connectivity | Reduces Ethiopia's reliance on Djibouti ports; lowers logistics costs by ~30% |
| Economic Diversification | Attracts logistics companies, warehouses, and cross-border businesses |
| Job Creation | Generates employment in transportation, customs, and services sectors |
| Regional Integration | Strengthens Ethiopia-Somaliland economic ties |
| Industrial Growth | Facilitates development of agro-processing, manufacturing, and commercial real estate |

### 2.3.3 Recent Major Infrastructure Developments

| Infrastructure Project | Details |
| --- | --- |
| Berbera-Tog-Wajaale Railway | UAE confirmed plans to finance a 250 km railway linking Tog-Wajaale to Berbera, project valued at USD 3 billion |
| Tog-Wajaale Border Bridge Reconstruction | TradeMark Africa launched reconstruction in May 2026 with Sweden funding through SWIFT Programme |
| One-Stop Border Post (OSBP) | Feasibility study recommends a juxtaposed model for Tog-Wajaale OSBP; ongoing upgrades |
| Berbera Corridor Road Upgrades | UAE pledged additional USD 100 million to upgrade the 250 km road connecting Berbera to Tog-Wajaale |
| Jigjiga-Tog-Wajaale Power Transmission Line | 73.1 km 400kV double circuit transmission line proposed |

## 2.4 URBAN INFRASTRUCTURE CHALLENGES

### 2.4.1 Transport Infrastructure Gaps

| Gap | Description | Impact |
| --- | --- | --- |
| Road Network | Outdated, insufficient for population growth | Congestion, reduced mobility |
| Connecting Roads | Awbare, Hartishekh unpaved | Limited accessibility, reduced economic opportunities |
| Public Transport | No formalized system | Reliance on private vehicles, congestion, environmental impact |
| NMT Infrastructure | Insufficient pedestrian, cycling infrastructure | Safety concerns, limited mobility options |

### 2.4.2 Utility Infrastructure Gaps

| Gap | Description | Impact |
| --- | --- | --- |
| Water Supply | Insufficient for growing population | Water scarcity, health concerns |
| Sanitation | Inadequate systems | Health risks, environmental degradation |
| Electricity | Unreliable supply | Economic constraints, service limitations |

### 2.4.3 Social Infrastructure Gaps

| Gap | Description | Impact |
| --- | --- | --- |
| Healthcare | Insufficient facilities | Limited access to healthcare |
| Education | Inadequate capacity | Limited access to education |
| Housing | Affordability and availability gaps | Informal settlements, overcrowding |
| Youth Services | No formal skills training or enterprise support | Youth unemployment, irregular migration |
| Returnee Support | No dedicated reception facility | Returnees lack accommodation and reintegration support |
| Waste Management | No engineered landfill or collection fleet | Environmental and health risks |

## 2.5 THE ETHIO-BERBERA CORRIDOR OPPORTUNITY

### 2.5.1 Strategic Significance

The Ethio-Berbera Corridor connects landlocked Ethiopia to the Port of Berbera in Somaliland, offering:

| Benefit | Description |
| --- | --- |
| Shorter Route | Alternative to the Djibouti route |
| Cost Reduction | Approximately 30% reduction in logistics costs |
| Diversification | Reduced reliance on a single port (Djibouti) |
| Regional Integration | Enhanced trade integration in the Horn of Africa |

### 2.5.2 Impact on Tog-Wajaale

As a transit city on this corridor, Tog-Wajaale has the potential to:

| Impact | Description |
| --- | --- |
| Logistics Hub | Become a logistics and trade hub |
| Investment Attraction | Attract logistics companies and warehouses |
| Industrial Growth | Facilitate accelerated industrial growth |
| Employment | Generate employment opportunities |
| Urbanization | Drive urbanization and economic development |

## 2.6 STRATEGIC ALIGNMENT WITH URBAN EXPANSION PLAN

### 2.6.1 Vision Alignment

Vision: To transform Tog-Wajaale into a regional center for commerce, education, and culture by 2055, emphasizing a diversified economy and green urbanism.

Project Contribution:

- Creates world-class infrastructure that supports commerce and trade

- Develops a diversified economy through FTZ and industrial development

- Integrates sustainable principles including green spaces and climate resilience

### 2.6.2 Alignment with Objectives

| Objective | Project Contribution |
| --- | --- |
| Infrastructure & Mobility | Road upgrades, urban expansion, and solid waste management |
| Economic Growth | FTZ & Logistics Hub creates jobs and attracts investment |
| Sustainable Planning | Green spaces, climate-resilient infrastructure, waste management |
| Population & Housing | Urban expansion provides 5,000+ housing units |
| Social Inclusivity | Youth Centre and Reception Centre support vulnerable populations |

### 2.6.3 Phased Implementation

The project aligns with the TWUEP's three-phase implementation strategy:

| Phase | Period | Focus | Portfolio Projects |
| --- | --- | --- | --- |
| Phase 1 | 2025-2030 | Short-Term Growth and Infrastructure Development | Urban Expansion (Phase 1); Corridor Roads; Solid Waste; Youth Centre |
| Phase 2 | 2031-2045 | Mid-Term Urban Expansion and Economic Development | FTZ (Phase 1); Reception Centre |
| Phase 3 | 2046-2055 | Long-Term Development and Sustainability | FTZ (Phase 2); Urban Expansion (Phase 2) |

## 2.7 LEGAL AND POLICY FRAMEWORK

### 2.7.1 Legal Framework Summary

| Level | Framework Component |
| --- | --- |
| National | Constitution of Ethiopia; National Urban Planning Laws; Environmental Protection Laws; National Migration Policy |
| Regional | Somali Regional State Urban Planning Policies; Land Use and Ownership Regulations; Regional Development Plans |
| Local | Tog-Wajaale Municipality Building Codes; Taxation and Incentive Policies; Municipal Development Plans |
| International | Sustainable Development Goals (SDGs); IGAD Regional Migration Fund; Cities Alliance Programme |

### 2.7.2 Key Policy Frameworks

| Framework | Relevance |
| --- | --- |
| National Migration Policy | Provides framework for managing migration and protecting migrants' rights; supports Reception Centre and Youth Centre |
| National Solid Waste Management Strategy | Provides framework for sustainable waste management; supports Solid Waste project |
| Ethiopia Urban Expansion Initiative | Provides technical and institutional framework; supports Urban Expansion project |
| SDG 11 (Sustainable Cities) | Provides international framework; supports all projects |
| SDG 13 (Climate Action) | Provides framework for climate resilience; supports Urban Expansion, Corridor Roads, and Solid Waste |

# CHAPTER THREE: PROJECT DESCRIPTION AND TECHNICAL SCOPE

## 3.1 PORTFOLIO OVERVIEW

### 3.1.1 Project Summary

| Priority | Project | Investment (USD) | Investment (Birr)* | Classification |
| --- | --- | --- | --- | --- |
| 01 | Planned Urban Expansion Programme | 63,000,000 | 10,082,009,700 | Foundation |
| 02 | Corridor & Arterial Road Upgrade | 40,000,000 | 6,401,276,000 | Connectivity |
| 03 | Inland Special Trade Zone & Logistics Hub | 250,000,000 | 40,007,975,000 | Economic Engine |
| 04 | Solid Waste Management System | 10,000,000 | 1,600,319,000 | Livability |
| 05 | Youth Skills, Enterprise & Migration Centre | 10,000,000 | 1,600,319,000 | Human Capital |
| 06 | Reception & Reintegration Centre | 7,000,000 | 1,120,223,300 | Social Protection |
| TOTAL |  | 380,000,000 | 60,812,122,000 |  |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 3.1.2 Project Classification

| Classification | Description | Projects |
| --- | --- | --- |
| Foundation | Creates the enabling conditions for all other investments | Priority 01 |
| Connectivity | Provides access and mobility for all other investments | Priority 02 |
| Economic Engine | Drives growth and job creation | Priority 03 |
| Livability | Ensures environmental sustainability and quality of life | Priority 04 |
| Human Capital | Develops the workforce and addresses social challenges | Priority 05 |
| Social Protection | Supports vulnerable populations | Priority 06 |

### 3.1.3 Implementation Sequencing Rationale

| Sequence | Priority | Classification | Rationale |
| --- | --- | --- | --- |
| First | Priority 01 | Foundation | Must be implemented first to create the land and framework for all other investments |
| Second | Priority 02 | Connectivity | Must follow foundation to provide access to all areas |
| Third | Priority 03 | Economic Engine | Requires foundation and connectivity to be effective |
| Fourth | Priority 04 | Livability | Can be implemented in parallel with economic engine |
| Fifth | Priority 05 | Human Capital | Best implemented as FTZ develops to provide trained workforce |
| Sixth | Priority 06 | Social Protection | Can be implemented throughout but highest impact when other systems are in place |

## 3.2 PRIORITY 01: PLANNED URBAN EXPANSION PROGRAMME

### 3.2.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Planned Urban Expansion Programme |
| Description | Phase 1 delivery of the TWUEP's planned urban expansion - serviced residential and mixed-use land, water, sanitation and green space |
| Indicative Investment | USD 63,000,000 (Birr 10,082,009,700) |
| Sector | Urban Development & Planning |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Blended: grant + concessional loan + PPP |
| Ranking Rationale | Foundation - Creates the spatial framework and serviced land for all other investments; manages 12.6-fold population growth |

### 3.2.2 Components Breakdown

| Component | Description | Estimated Cost (USD) |
| --- | --- | --- |
| Planned Residential & Mixed-Use Zones | New housing and mixed-use developments | 20,000,000 |
| Water Supply & Sanitation Systems | Expansion of water and sanitation | 15,000,000 |
| Public Services & Social Infrastructure | Schools, health centres, and services | 10,000,000 |
| Green Spaces & Urban Parks | Parks and recreational areas | 8,000,000 |
| Land Readjustment & City Planning | Land management and urban planning | 10,000,000 |
| TOTAL |  | 63,000,000 |

### 3.2.3 Value Creation

| Outcome | Target |
| --- | --- |
| Projected City Population Served (2030) | 119,000 |
| New Housing Units | 5,000+ |
| Water Access | 100% access to clean water |
| Sanitation Coverage | 80%+ sanitation coverage |
| Green Spaces | 15%+ of urban area as green space |

### 3.2.4 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 02 (Corridor Upgrade) | Road network supports planned expansion areas |
| With Priority 03 (FTZ) | New housing and services for FTZ workers |
| With Priority 04 (Solid Waste) | Waste services for new expansion areas |
| With Priority 05 (Youth Centre) | Youth housing and services in expansion areas |
| With Priority 06 (Reception Centre) | Housing for returnees |

## 3.3 PRIORITY 02: CORRIDOR & ARTERIAL ROAD UPGRADE

### 3.3.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Corridor & Arterial Road Upgrade |
| Description | A 20 km programme of arterial and corridor road upgrades across Tog-Wajaale |
| Indicative Investment | USD 40,000,000 (Birr 6,401,276,000) |
| Sector | Transport Infrastructure |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Concessional loan / grant |
| Ranking Rationale | Connectivity - Essential for access to FTZ, urban expansion areas, and trade corridor; addresses immediate infrastructure deficit |

### 3.3.2 Components Breakdown

| Component | Description | Estimated Cost (USD) |
| --- | --- | --- |
| Arterial Road Development | Construction and upgrade of 20 km priority roads | 20,000,000 |
| Drainage & Stormwater Systems | Comprehensive drainage infrastructure | 6,000,000 |
| Sidewalks & Pedestrian Facilities | Safe pedestrian infrastructure | 5,000,000 |
| Street Lighting & Traffic Safety | Lighting, signage, and safety features | 5,000,000 |
| Landscaping & Green Buffers | Green infrastructure and environmental integration | 4,000,000 |
| TOTAL |  | 40,000,000 |

### 3.3.3 Value Creation

| Outcome | Target |
| --- | --- |
| People/Businesses Served | 82,064+ (growing to 554,700 by 2055) |
| Jobs Created | ~900 construction jobs |
| Travel Time | 30% reduction in travel time |
| Safety | 50% reduction in road accidents |
| Flood Risk | Reduced flooding on priority routes |

### 3.3.4 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 01 (Urban Expansion) | Road network supports planned expansion areas |
| With Priority 03 (FTZ) | Access roads connect FTZ to the Berbera corridor and city centre |
| With Border Bridge | Complementary infrastructure for cross-border connectivity |

## 3.4 PRIORITY 03: INLAND SPECIAL TRADE ZONE & LOGISTICS HUB

### 3.4.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Inland Special Trade Zone & Logistics Hub |
| Description | A 50-hectare special trade zone and dry port adjacent to the border crossing |
| Indicative Investment | USD 250,000,000 (Birr 40,007,975,000) |
| Sector | Trade & Industrial Infrastructure |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | PPP / Concession |
| Ranking Rationale | Economic Engine - Largest economic impact; leverages strategic location; creates 6,000+ jobs; catalytic for private investment |

### 3.4.2 Components Breakdown

| Component | Description | Estimated Cost (USD) |
| --- | --- | --- |
| Dry Port & Logistics Hub | Container handling, customs clearance, logistics | 70,000,000 |
| Warehousing & Distribution Parks | Storage and distribution facilities | 50,000,000 |
| Industrial Parks & Manufacturing Zones | Production and processing facilities | 60,000,000 |
| Customs & Trade Facilitation | On-site customs clearance and trade services | 30,000,000 |
| Commercial & Business Services | Office space, retail, and support services | 20,000,000 |
| Supporting Utilities | Power, water, telecommunications | 20,000,000 |
| TOTAL |  | 250,000,000 |

### 3.4.3 Value Creation

| Outcome | Target |
| --- | --- |
| Jobs Created | ~6,000 direct and indirect jobs |
| Companies Established | 100+ companies |
| Trade Volume | USD 500 million+ annually |
| Tax Revenue | USD 50 million+ annually |
| Economic Growth | 5%+ contribution to city GDP |

### 3.4.4 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 01 (Urban Expansion) | New housing and services for FTZ workers |
| With Priority 02 (Corridor Upgrade) | Access roads connect FTZ to the Berbera corridor |
| With Priority 05 (Youth Centre) | Skilled workforce for FTZ industries |
| With Border Bridge | Enhanced connectivity and trade facilitation |

## 3.5 PRIORITY 04: SOLID WASTE MANAGEMENT SYSTEM

### 3.5.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Solid Waste Management System |
| Description | A citywide solid waste management system delivering a clean, healthy city |
| Indicative Investment | USD 10,000,000 (Birr 1,600,319,000) |
| Sector | Municipal Services & Environment |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Grant / concessional loan |
| Ranking Rationale | Livability - Environmental and public health imperative; essential for livable city; relatively low-cost, high-impact |

### 3.5.2 Components Breakdown

| Component | Description | Estimated Cost (USD) |
| --- | --- | --- |
| Engineered Landfill Disposal Site | Sanitary landfill with environmental controls | 3,000,000 |
| Transfer Stations | Network of collection points across the city | 2,000,000 |
| Collection Fleet & Equipment | Modern waste collection vehicles and equipment | 2,500,000 |
| Waste Segregation & Recycling Centre | Sorting, processing, and recycling facilities | 1,500,000 |
| Community Awareness & Capacity Building | Public education and training programmes | 1,000,000 |
| TOTAL |  | 10,000,000 |

### 3.5.3 Value Creation

| Outcome | Target |
| --- | --- |
| People Served | 82,064+ (growing to 554,700 by 2055) |
| Waste Collection Coverage | 90%+ of households |
| Recycling Rate | 30%+ of waste recycled |
| Environmental Benefit | Reduced open dumping & waterway pollution |

### 3.5.4 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 01 (Urban Expansion) | Waste services planned for new expansion areas |
| With Priority 02 (Corridor Upgrade) | Road access enables waste collection in expanded areas |
| With Priority 03 (FTZ) | Waste services for FTZ and industrial facilities |

## 3.6 PRIORITY 05: YOUTH SKILLS, ENTERPRISE & MIGRATION CENTRE

### 3.6.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Youth Skills, Enterprise & Migration Centre |
| Description | A dedicated centre delivering skills training, enterprise incubation and safe-migration services |
| Indicative Investment | USD 10,000,000 (Birr 1,600,319,000) |
| Sector | Skills, Enterprise & Migration Services |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Grant |
| Ranking Rationale | Human Capital - Addresses youth unemployment and irregular migration; builds workforce for FTZ; leverages existing programmes |

### 3.6.2 Components Breakdown

| Component | Description | Estimated Cost (USD) |
| --- | --- | --- |
| Skills Training Facilities | Vocational and technical training centre | 3,000,000 |
| Entrepreneurship Incubation Centre | Business incubation and support | 2,500,000 |
| Digital & Career Development Labs | Digital skills and career guidance | 2,000,000 |
| Job Placement & Migration Services | Employment and migration guidance | 1,500,000 |
| Business Support & Mentoring | Mentorship and business advisory | 1,000,000 |
| TOTAL |  | 10,000,000 |

### 3.6.3 Value Creation

| Outcome | Target |
| --- | --- |
| Trained by 2030 | 5,000+/year (TWUEP target) |
| Jobs Created | ~200 construction jobs + placements |
| Beneficiaries | 60% youth under 25; women/youth/displaced & host communities |

### 3.6.4 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 03 (FTZ) | Skilled workforce for FTZ industries |
| With Priority 06 (Reception Centre) | Skills training for returnees |
| With IGAD RMF | Alignment with IGAD Regional Migration Fund programmes |

## 3.7 PRIORITY 06: RECEPTION & REINTEGRATION CENTRE

### 3.7.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Reception & Reintegration Centre |
| Description | A dedicated reception and reintegration centre providing dignified support, counselling and livelihood opportunities |
| Indicative Investment | USD 7,000,000 (Birr 1,120,223,300) |
| Sector | Migration & Social Services |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Grant |
| Ranking Rationale | Social Protection - Addresses returnee needs; supports vulnerable population; complements other investments |

### 3.7.2 Components Breakdown

| Component | Description | Estimated Cost (USD) |
| --- | --- | --- |
| Reception & Accommodation Facilities | Welcome centre and temporary accommodation | 2,000,000 |
| Counselling & Psychosocial Support | Mental health and psychosocial services | 1,500,000 |
| Skills Training & Livelihood Programmes | Vocational training and livelihood support | 1,500,000 |
| Reintegration Grants & Business Support | Grants and business development support | 1,000,000 |
| Monitoring, Follow-up & Case Management | Ongoing support and case management | 1,000,000 |
| TOTAL |  | 7,000,000 |

### 3.7.3 Value Creation

| Outcome | Target |
| --- | --- |
| Returnees Served / Year | Pending assessment |
| Jobs Created | ~100 construction + case management |
| Beneficiaries | Returnees, women & youth |

### 3.7.4 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 05 (Youth Centre) | Skills training for returnees |
| With Priority 01 (Urban Expansion) | Housing and services for returnees |
| With Priority 03 (FTZ) | Employment opportunities for returnees |

## 3.8 PROJECT SYNERGIES AND INTEGRATION

### 3.8.1 Project Synergies Matrix

| Project | Priority 01 | Priority 02 | Priority 03 | Priority 04 | Priority 05 | Priority 06 |
| --- | --- | --- | --- | --- | --- | --- |
| Priority 01: Urban Expansion | — | Road network supports expansion | Housing for FTZ workers | Waste services for new areas | Housing for youth | Housing for returnees |
| Priority 02: Corridor Roads | Supports expansion areas | — | Access to FTZ | Access for collection | Access for centre | Access for centre |
| Priority 03: FTZ | Workforce housing | Road access | — | Industrial waste services | Skilled workforce | Employment for returnees |
| Priority 04: Solid Waste | Serves new areas | Enables collection | Serves FTZ | — | Employment opportunities | Employment opportunities |
| Priority 05: Youth Centre | Housing for youth | Access for centre | Workforce for FTZ | Employment in waste | — | Skills for returnees |
| Priority 06: Reception Centre | Housing for returnees | Access for centre | Employment for returnees | Employment in waste | Skills training | — |

### 3.8.2 Multiplier Effects

| Effect | Description |
| --- | --- |
| Economic Multiplier | Each USD invested creates additional economic activity |
| Employment Multiplier | Direct jobs create indirect employment |
| Infrastructure Multiplier | Infrastructure enables further development |
| Social Multiplier | Social investments improve quality of life |
| Environmental Multiplier | Environmental investments enhance sustainability |

# CHAPTER FOUR: PRIORITIZATION METHODOLOGY AND DETAILED PROJECT PROFILES

## 4.1 Prioritization Framework

The Tog-Wajaale EACC Priority Investment Portfolio comprises six strategic projects. To ensure objective, transparent, and evidence-based prioritization, a weighted scoring methodology was developed. Projects have been ranked based on six criteria, each assigned a weight reflecting its relative importance in achieving sustainable urban development.

### 4.1.1 Scoring Criteria and Weights

| Criterion | Weight | Description | Rationale |
| --- | --- | --- | --- |
| Strategic Foundation | 25% | Projects that create the enabling conditions for other investments | Highest weight as foundation projects enable all subsequent investments |
| Economic Impact | 20% | Job creation, investment attraction, and economic growth potential | Critical for attracting investment and ensuring long-term sustainability |
| Social Impact | 20% | Benefits to vulnerable populations, quality of life improvements | Essential for inclusive development and community support |
| Feasibility & Readiness | 15% | Current stage, evidence available, implementation complexity | Important for implementation timelines and risk management |
| Catalytic Effect | 10% | Ability to unlock other investments and generate synergies | Recognizes projects that unlock additional investments |
| Environmental Sustainability | 10% | Environmental benefits and climate resilience | Important for long-term resilience and climate commitments |

### 4.1.2 Scoring Scale

| Score | Description | Interpretation |
| --- | --- | --- |
| 9-10 | Exceptional | Project strongly and comprehensively meets the criterion |
| 7-8 | Strong | Project meets the criterion well with minor gaps |
| 5-6 | Moderate | Project partially meets the criterion with notable gaps |
| 3-4 | Weak | Project marginally meets the criterion with significant gaps |
| 1-2 | Very Weak | Project does not meet the criterion |

### 4.1.3 Weight Distribution Rationale

| Weight | Rationale |
| --- | --- |
| 25% - Strategic Foundation | Highest weight because projects that create enabling conditions have the most significant and lasting impact. Without foundation projects, other investments cannot be effectively implemented. |
| 20% - Economic Impact | Economic growth is essential for attracting investment, creating jobs, and ensuring long-term sustainability. Projects with strong economic impact generate revenue and reduce dependency on external funding. |
| 20% - Social Impact | Social inclusion is a core principle of the TWUEP. Projects that benefit vulnerable populations, improve quality of life, and address migration challenges contribute to social stability and community support. |
| 15% - Feasibility & Readiness | Projects that are more ready for implementation present lower risks and can deliver benefits more quickly. This criterion recognizes the importance of practical implementation capacity. |
| 10% - Catalytic Effect | Some projects have the ability to unlock other investments and generate significant synergies. These projects create a multiplier effect that extends beyond their direct impact. |
| 10% - Environmental Sustainability | Environmental sustainability is essential for long-term resilience. Projects with environmental benefits contribute to climate action, resource efficiency, and public health. |

## 4.2 Project Scoring Matrix

| Criterion | Weight | Priority 01: Urban Expansion | Priority 02: Corridor Roads | Priority 03: FTZ & Logistics | Priority 04: Solid Waste | Priority 05: Youth Centre | Priority 06: Reception Centre |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Foundation | 25% | 9.5 | 9.0 | 8.0 | 7.5 | 6.5 | 6.0 |
| Economic Impact | 20% | 8.0 | 7.5 | 9.5 | 6.5 | 7.0 | 5.5 |
| Social Impact | 20% | 8.0 | 7.0 | 7.5 | 8.5 | 9.0 | 9.0 |
| Feasibility & Readiness | 15% | 8.0 | 8.0 | 7.0 | 7.5 | 7.5 | 7.0 |
| Catalytic Effect | 10% | 9.0 | 8.5 | 9.5 | 7.0 | 7.5 | 6.5 |
| Environmental Sustainability | 10% | 8.5 | 8.0 | 7.0 | 9.0 | 6.0 | 5.5 |
| Weighted Score | 100% | 8.50 | 8.18 | 8.15 | 7.55 | 7.20 | 6.63 |
| Rank |  | 1 | 2 | 3 | 4 | 5 | 6 |

### 4.2.1 Detailed Score Breakdown

Priority 01: Planned Urban Expansion Programme (Score: 8.50)

| Factor | Score | Justification |
| --- | --- | --- |
| Strategic Foundation | 9.5 | Creates the spatial framework for all other investments; manages 12.6-fold population growth |
| Economic Impact | 8.0 | Enables economic development through serviced land; supports 5,000+ housing units |
| Social Impact | 8.0 | Provides housing and services for growing population; prevents informal settlements |
| Feasibility & Readiness | 8.0 | TWUEP framework in place; expansion boundary mapped; medium-growth scenario selected |
| Catalytic Effect | 9.0 | Unlocks potential for FTZ, housing, and commercial development |
| Environmental Sustainability | 8.5 | Incorporates green spaces (15%+ of urban area); climate-resilient zoning |

Priority 02: Corridor & Arterial Road Upgrade (Score: 8.18)

| Factor | Score | Justification |
| --- | --- | --- |
| Strategic Foundation | 9.0 | Essential for access to all other investments; provides critical mobility |
| Economic Impact | 7.5 | Enables trade facilitation; reduces transport costs; ~900 construction jobs |
| Social Impact | 7.0 | Improves safety; reduces travel time; enhances access to services |
| Feasibility & Readiness | 8.0 | Road network mapped; flood-risk zones identified; indicative cost estimate available |
| Catalytic Effect | 8.5 | Enables trade and economic activity; supports FTZ access |
| Environmental Sustainability | 8.0 | Climate-resilient drainage; flood risk reduction; green buffers |

Priority 03: Inland Special Trade Zone & Logistics Hub (Score: 8.15)

| Factor | Score | Justification |
| --- | --- | --- |
| Strategic Foundation | 8.0 | Leverages strategic location on Berbera corridor; requires foundation and connectivity |
| Economic Impact | 9.5 | Largest economic impact (~6,000 jobs; USD 500M+ trade; USD 50M+ tax revenue) |
| Social Impact | 7.5 | Creates employment; supports 40% women/youth/displaced beneficiaries |
| Feasibility & Readiness | 7.0 | Informal FTZ operating since 2015; indicative site identified; PPP structure needed |
| Catalytic Effect | 9.5 | Attracts private investment and anchor tenants; catalytic for regional trade |
| Environmental Sustainability | 7.0 | Green building standards; requires ESIA |

Priority 04: Solid Waste Management System (Score: 7.55)

| Factor | Score | Justification |
| --- | --- | --- |
| Strategic Foundation | 7.5 | Essential public service; supports urban livability |
| Economic Impact | 6.5 | Limited direct economic impact; supports public health and productivity |
| Social Impact | 8.5 | Improves quality of life for all residents; public health benefits |
| Feasibility & Readiness | 7.5 | Relatively low-cost, high-impact investment; indicative site identified |
| Catalytic Effect | 7.0 | Supports urban expansion and industrial development |
| Environmental Sustainability | 9.0 | Direct environmental benefits; reduced pollution; climate action |

Priority 05: Youth Skills, Enterprise & Migration Centre (Score: 7.20)

| Factor | Score | Justification |
| --- | --- | --- |
| Strategic Foundation | 6.5 | Builds human capital; supports workforce development |
| Economic Impact | 7.0 | Builds workforce for FTZ; supports entrepreneurship |
| Social Impact | 9.0 | Addresses youth unemployment and irregular migration; high social impact |
| Feasibility & Readiness | 7.5 | Leverages existing programmes (IGAD RMF, Cities Alliance); indicative cost available |
| Catalytic Effect | 7.5 | Supports FTZ workforce development; builds local capacity |
| Environmental Sustainability | 6.0 | Limited direct environmental impact |

Priority 06: Reception & Reintegration Centre (Score: 6.63)

| Factor | Score | Justification |
| --- | --- | --- |
| Strategic Foundation | 6.0 | Supports social protection; complements other investments |
| Economic Impact | 5.5 | Limited direct economic impact; supports social stability |
| Social Impact | 9.0 | Addresses needs of vulnerable returnees; high social impact |
| Feasibility & Readiness | 7.0 | Leverages IOM MRC and IGAD RMF programmes; indicative cost available |
| Catalytic Effect | 6.5 | Complements Youth Centre and other investments |
| Environmental Sustainability | 5.5 | Limited direct environmental impact |

## 4.3 Ranking Summary

| Rank | Priority | Project | Investment (USD) | Weighted Score | Classification |
| --- | --- | --- | --- | --- | --- |
| 1 | Priority 01 | Planned Urban Expansion Programme | 63,000,000 | 8.50 | Foundation |
| 2 | Priority 02 | Corridor & Arterial Road Upgrade | 40,000,000 | 8.18 | Connectivity |
| 3 | Priority 03 | Inland Special Trade Zone & Logistics Hub | 250,000,000 | 8.15 | Economic Engine |
| 4 | Priority 04 | Solid Waste Management System | 10,000,000 | 7.55 | Livability |
| 5 | Priority 05 | Youth Skills, Enterprise & Migration Centre | 10,000,000 | 7.20 | Human Capital |
| 6 | Priority 06 | Reception & Reintegration Centre | 7,000,000 | 6.63 | Social Protection |

## 4.4 Classification System

| Classification | Description | Projects | Rationale |
| --- | --- | --- | --- |
| Foundation | Creates the enabling conditions for all other investments | Priority 01 | Provides serviced land, housing, and infrastructure framework |
| Connectivity | Provides access and mobility for all other investments | Priority 02 | Enables access to FTZ, urban expansion, and trade corridor |
| Economic Engine | Drives growth and job creation | Priority 03 | Largest economic impact; attracts investment; creates jobs |
| Livability | Ensures environmental sustainability and quality of life | Priority 04 | Essential for public health and environmental protection |
| Human Capital | Develops the workforce and addresses social challenges | Priority 05 | Builds skills; addresses youth unemployment and migration |
| Social Protection | Supports vulnerable populations | Priority 06 | Provides essential services to returnees |

## 4.5 Detailed Ranking Rationale

### 4.5.1 Priority 01: Planned Urban Expansion Programme

Score: 8.50 | Rank: 1 | Classification: Foundation

| Factor | Score | Rationale |
| --- | --- | --- |
| Strategic Foundation | 9.5 | Creates the spatial framework and serviced land for all other investments |
| Catalytic Effect | 9.0 | Unlocks potential for FTZ, housing, and commercial development |
| Environmental Sustainability | 8.5 | Incorporates green spaces and climate-resilient zoning |

Key Justification:

This project is ranked #1 because it creates the fundamental conditions for all other investments. Without planned urban expansion, the city risks unplanned sprawl, informal settlements, and inefficient infrastructure. It provides the serviced land, roads, and utilities that enable the FTZ, housing, and social infrastructure to function effectively.

Key Benefits:

- Manages 576% population increase

- Provides 5,000+ new housing units

- Creates 100% water access and 80% sanitation coverage

- Establishes 15%+ urban green space

- Prevents informal settlement and unplanned sprawl

### 4.5.2 Priority 02: Corridor & Arterial Road Upgrade

Score: 8.18 | Rank: 2 | Classification: Connectivity

| Factor | Score | Rationale |
| --- | --- | --- |
| Strategic Foundation | 9.0 | Essential for access to all other investments |
| Catalytic Effect | 8.5 | Enables trade and economic activity |

Key Justification:

Road infrastructure is essential for connecting the FTZ to the Berbera corridor, enabling access to urban expansion areas, and facilitating trade. Without road upgrades, the economic potential of other investments cannot be realized. The project addresses immediate infrastructure deficits including unpaved roads, poor drainage, and flooding.

Key Benefits:

- 20 km of upgraded arterial roads

- 30% reduction in travel time

- 50% reduction in road accidents

- Reduced flooding on priority routes

- ~900 construction jobs

### 4.5.3 Priority 03: Inland Special Trade Zone & Logistics Hub

Score: 8.15 | Rank: 3 | Classification: Economic Engine

| Factor | Score | Rationale |
| --- | --- | --- |
| Economic Impact | 9.5 | Largest economic impact (~6,000 jobs, USD 500M+ trade) |
| Catalytic Effect | 9.5 | Attracts private investment and anchor tenants |
| Strategic Foundation | 8.0 | Leverages Tog-Wajaale's strategic location |

Key Justification:

This project delivers the largest economic impact and creates the most jobs. However, it requires the foundation created by Priority 01 (Urban Expansion) and the connectivity provided by Priority 02 (Roads). It is ranked third because it depends on the first two projects for success.

Key Benefits:

- ~6,000 direct and indirect jobs

- 100+ companies established

- USD 500 million+ annual trade

- USD 50 million+ annual tax revenue

- 5%+ contribution to city GDP

### 4.5.4 Priority 04: Solid Waste Management System

Score: 7.55 | Rank: 4 | Classification: Livability

| Factor | Score | Rationale |
| --- | --- | --- |
| Environmental Sustainability | 9.0 | Direct environmental and public health benefits |
| Social Impact | 8.5 | Improves quality of life for all residents |
| Feasibility & Readiness | 7.5 | Relatively low-cost, high-impact investment |

Key Justification:

Solid waste management is essential for public health, environmental protection, and quality of life. While it doesn't create as many jobs or generate as much economic activity as the FTZ, it is a fundamental service that enables a livable city as population grows toward 554,700.

Key Benefits:

- 90%+ waste collection coverage

- 30%+ recycling rate

- Reduced open dumping and waterway pollution

- Improved public health

- Reduced methane emissions

### 4.5.5 Priority 05: Youth Skills, Enterprise & Migration Centre

Score: 7.20 | Rank: 5 | Classification: Human Capital

| Factor | Score | Rationale |
| --- | --- | --- |
| Social Impact | 9.0 | Addresses youth unemployment and irregular migration |
| Economic Impact | 7.0 | Builds workforce for FTZ and other opportunities |
| Feasibility & Readiness | 7.5 | Leverages existing programmes (IGAD RMF, Cities Alliance) |

Key Justification:

This project addresses critical social challenges including youth unemployment and irregular migration. It builds the human capital needed for the FTZ and other economic opportunities. However, it is most effective when the FTZ is operational and can absorb trained workers.

Key Benefits:

- 5,000+ youth trained annually by 2030

- Entrepreneurship support and incubation

- Safe migration information and guidance

- Job placement services

- Reduced irregular migration

### 4.5.6 Priority 06: Reception & Reintegration Centre

Score: 6.63 | Rank: 6 | Classification: Social Protection

| Factor | Score | Rationale |
| --- | --- | --- |
| Social Impact | 9.0 | Addresses needs of vulnerable returnees |
| Feasibility & Readiness | 7.0 | Leverages existing programmes (IOM MRC, IGAD RMF) |
| Economic Impact | 5.5 | Limited direct economic impact |

Key Justification:

This project provides essential social protection for vulnerable returnees. While it has high social impact, it has limited economic impact compared to other projects. It is most effective when complemented by the Youth Centre (for skills training) and Urban Expansion (for housing).

Key Benefits:

- Dignified reception for returnees

- Psychosocial support and counselling

- Skills training and livelihood programmes

- Reintegration grants and business support

- Case management and follow-up

## 4.6 Implementation Sequencing Rationale

| Sequence | Priority | Classification | Rationale |
| --- | --- | --- | --- |
| First | Priority 01 | Foundation | Must be implemented first to create the land and framework for all other investments |
| Second | Priority 02 | Connectivity | Must follow foundation to provide access to all areas |
| Third | Priority 03 | Economic Engine | Requires foundation and connectivity to be effective |
| Fourth | Priority 04 | Livability | Can be implemented in parallel with economic engine |
| Fifth | Priority 05 | Human Capital | Best implemented as FTZ develops to provide trained workforce |
| Sixth | Priority 06 | Social Protection | Can be implemented throughout but highest impact when other systems are in place |

### 4.6.1 Sequencing Diagram

text

PHASE 1: FOUNDATION (2025-2026)

┌─────────────────────────────────────────────────────────┐

│ PRIORITY 01: PLANNED URBAN EXPANSION │

│ Creates the spatial framework and serviced land │

│ Investment: USD 10,000,000 (Feasibility & Planning) │

└─────────────────────────────────────────────────────────┘

│

▼

PHASE 2: CONNECTIVITY (2025-2026)

┌─────────────────────────────────────────────────────────┐

│ PRIORITY 02: CORRIDOR & ARTERIAL ROAD UPGRADE │

│ Provides access and mobility │

│ Investment: USD 5,000,000 (Feasibility & Design) │

└─────────────────────────────────────────────────────────┘

│

▼

PHASE 3: ECONOMIC ENGINE (2027-2030)

┌─────────────────────────────────────────────────────────┐

│ PRIORITY 03: INLAND SPECIAL TRADE ZONE & LOGISTICS HUB│

│ Drives growth and job creation │

│ Investment: USD 80,000,000 (Phase 1 Development) │

└─────────────────────────────────────────────────────────┘

│

┌───────────────────────┼───────────────────────────────┐

│ │ │

▼ ▼ ▼

PHASE 4: LIVABILITY PHASE 5: HUMAN CAPITAL PHASE 6: SOCIAL

(2027-2028) (2027-2028) PROTECTION

┌────────────────┐ ┌────────────────┐ (2028-2029)

│ PRIORITY 04: │ │ PRIORITY 05: │ ┌────────────────┐

│ SOLID WASTE │ │ YOUTH CENTRE │ │ PRIORITY 06: │

│ MANAGEMENT │ │ │ │ RECEPTION │

│ Investment: │ │ Investment: │ │ CENTRE │

│ USD 8,000,000 │ │ USD 8,000,000 │ │ Investment: │

└────────────────┘ └────────────────┘ │ USD 6,000,000 │

└────────────────┘

## 4.7 Summary of Prioritization

| Rank | Priority | Project | Classification | Investment (USD) | Weighted Score | Key Strength |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Priority 01 | Planned Urban Expansion Programme | Foundation | 63,000,000 | 8.50 | Enables all other investments |
| 2 | Priority 02 | Corridor & Arterial Road Upgrade | Connectivity | 40,000,000 | 8.18 | Provides access and mobility |
| 3 | Priority 03 | Inland Special Trade Zone & Logistics Hub | Economic Engine | 250,000,000 | 8.15 | Largest economic impact |
| 4 | Priority 04 | Solid Waste Management System | Livability | 10,000,000 | 7.55 | Environmental and public health |
| 5 | Priority 05 | Youth Skills, Enterprise & Migration Centre | Human Capital | 10,000,000 | 7.20 | Addresses youth unemployment |
| 6 | Priority 06 | Reception & Reintegration Centre | Social Protection | 7,000,000 | 6.63 | Supports vulnerable returnees |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418

Project Website: www.twuep.com.et

## 4.8 PRIORITY 01: PLANNED URBAN EXPANSION PROGRAMME — DETAILED PROFILE

### 4.8.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Planned Urban Expansion Programme |
| Description | Phase 1 delivery of the TWUEP's planned urban expansion - serviced residential and mixed-use land, water, sanitation and green space |
| Indicative Investment | USD 63,000,000 (Birr 10,082,009,700)* |
| Sector | Urban Development & Planning |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Blended: grant + concessional loan + PPP |
| Ranking Rationale | Foundation - Creates the spatial framework and serviced land for all other investments; manages 12.6-fold population growth |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 4.8.2 Strategic Rationale

#### 4.8.2.1 Population Growth Context

Tog-Wajaale's built-up area is projected to grow 12.6-fold by 2055, with population rising from 82,064 to 554,700. Without planned expansion, this growth risks repeating the overcrowded informal settlement pattern seen in the city's past growth.

| Year | Population | Built-up Area (ha) | Density (p/ha) |
| --- | --- | --- | --- |
| 1994 | 8,000 | 80 | 100.00 |
| 2007 | 14,800 | 138 | 107.25 |
| 2015 | 46,454 | 469 | 99.04 |
| 2024 | 82,064 | 711 | 115.42 |
| 2030 (Projected) | 119,000 | 1,450 | 82.07 |
| 2055 (Projected) | 554,700 | 8,990 | 61.70 |

Source: Tog-Wajaale Urban Expansion Plan (2025-2055)

#### 4.8.2.2 Why This is Priority #1

| Reason | Description |
| --- | --- |
| Enabling Infrastructure | Provides the land and services framework for all other investments |
| Population Growth Management | Manages 576% population increase |
| Catalytic Effect | Unlocks potential for FTZ, housing, and commercial development |
| Long-term Impact | Creates foundation for 30-year urban development |
| Risk Mitigation | Prevents informal settlement and unplanned sprawl |

#### 4.8.2.3 Urban Expansion Planning Context

Ethiopia is now among the most rapidly urbanizing countries in the world. The Ethiopia Urban Expansion Initiative has trained 18 cities in the urban expansion planning process and delivered a strong return on investment. Tog-Wajaale is part of this initiative.

| Principle | Description |
| --- | --- |
| Anticipatory Planning | Planning for future growth rather than reacting to it |
| Road Network First | Establishing a grid of arterial roads before development |
| Public Land Reservations | Reserving land for public facilities and green spaces |
| Incremental Development | Phased development matching city capacity |
| Participatory Approach | Involving stakeholders in the planning process |

#### 4.8.2.4 Growth Scenario Selected

The Tog-Wajaale Urban Expansion Plan (TWUEP) selected the Medium-Growth Scenario as the most viable option:

| Parameter | Value |
| --- | --- |
| Population by 2055 | 554,700 |
| Urban Density by 2055 | 61.7 people per hectare |
| Urban Area by 2055 | 8,990 hectares (12.6x 2024 built-up area) |
| Annual Growth Rate | 6.4% |
| Infrastructure Investment | Modernizing existing, developing new facilities |

#### 4.8.2.5 Key Urbanization Drivers

| Driver | Description |
| --- | --- |
| Strategic Location | Positioned on Ethio-Berbera trade corridor; proximity to Port of Berbera |
| Economic Opportunities | Free Trade Zone; cross-border trade; growing commercial sector |
| Rural-Urban Migration | Push factors (drought, land degradation); pull factors (jobs, education, healthcare) |
| Infrastructure Development | Investments in roads, utilities, and public services |
| Government Policies | Decentralization; promotion of secondary cities |
| Demographics | Youthful population (60% under 25); high natural increase |

### 4.8.3 Project Scope

#### 4.8.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Planned Residential & Mixed-Use Zones | New housing and mixed-use developments | 20,000,000 | 3,200,638,000 |
| Water Supply & Sanitation Systems | Expansion of water and sanitation | 15,000,000 | 2,400,478,500 |
| Public Services & Social Infrastructure | Schools, health centres, and services | 10,000,000 | 1,600,319,000 |
| Green Spaces & Urban Parks | Parks and recreational areas | 8,000,000 | 1,280,255,200 |
| Land Readjustment & City Planning | Land management and urban planning | 10,000,000 | 1,600,319,000 |
| TOTAL |  | 63,000,000 | 10,082,009,700 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

#### 4.8.3.2 Component Details

1. Planned Residential & Mixed-Use Zones (USD 20,000,000)

| Element | Description |
| --- | --- |
| Residential Zones | Planned housing for growing population |
| Mixed-Use Development | Integrated residential and commercial |
| Affordable Housing | Housing accessible to all income levels |
| Density Planning | Appropriate density for sustainable urban form |
| Serviced Plots | Infrastructure-serviced land parcels |

Targets:

- 5,000+ new housing units

- 50,000+ new residents accommodated

- 20% affordable housing provision

2. Water Supply & Sanitation Systems (USD 15,000,000)

| Element | Description |
| --- | --- |
| Water Distribution Network | Expanded water distribution system |
| Water Treatment | Water treatment and quality assurance |
| Sewerage System | Sewage collection and treatment |
| Sanitation Facilities | Public sanitation facilities |
| Stormwater Drainage | Drainage systems for flood prevention |

Targets:

- 100% access to clean water

- 80%+ sanitation coverage

3. Public Services & Social Infrastructure (USD 10,000,000)

| Element | Description |
| --- | --- |
| Schools | Primary and secondary schools |
| Health Centres | Primary healthcare facilities |
| Community Centres | Community gathering spaces |
| Public Facilities | Government and public service facilities |

Targets:

- Universal access to education and healthcare

- Community services within walking distance

4. Green Spaces & Urban Parks (USD 8,000,000)

| Element | Description |
| --- | --- |
| Urban Parks | Public parks and recreational areas |
| Green Corridors | Green connections between areas |
| Community Gardens | Community-managed green spaces |
| Environmental Conservation | Protection of environmentally sensitive areas |

Targets:

- 15%+ of urban area as green space

- Equitable access to green spaces

5. Land Readjustment & City Planning (USD 10,000,000)

| Element | Description |
| --- | --- |
| Land Readjustment | Fair and transparent land management |
| City Planning | Urban planning and zoning |
| GIS and Mapping | Spatial data and mapping |
| Regulatory Framework | Urban planning regulations |

### 4.8.4 Value Creation

#### 4.8.4.1 Expected Outcomes

| Outcome | Target |
| --- | --- |
| Projected City Population Served (2030) | 119,000 |
| New Housing Units | 5,000+ |
| Water Access | 100% access to clean water |
| Sanitation Coverage | 80%+ sanitation coverage |
| Green Spaces | 15%+ of urban area as green space |

#### 4.8.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Managed Growth | Structured expansion prevents informal settlements |
| Reduced Congestion | Planned road network reduces congestion |
| Environmental Protection | Protection of environmentally sensitive areas |
| Improved Livability | Access to services, green spaces, and infrastructure |
| Economic Development | Land availability supports economic activity |
| Property Values | Planned expansion increases property values |
| Social Inclusion | Equitable access to services and opportunities |

#### 4.8.4.3 Land Readjustment as a Key Tool

| Benefit | Description |
| --- | --- |
| Fair Participation | Landowners participate fairly in development |
| Infrastructure Financing | Land value captured for infrastructure financing |
| Efficient Land Use | More efficient and planned land use |
| Reduced Displacement | Minimizes displacement of communities |
| Community Benefits | Equitable sharing of development benefits |

### 4.8.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | TWUEP Ch.5 population & land projections (82,064 → 119,000 by 2030); medium-growth scenario selected | Detailed Phase 1 land-use plan |
| Site / Land & Approvals | In progress | Expansion boundary and undevelopable land mapped (TWUEP Figs.1-3) | Land survey, titling and readjustment plan |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & master plan |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 63M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | Slope & hazard mapping (TWUEP Ch.4) | ESIA and resettlement action plan |
| Revenue, O&M & Delivery Model | Gap | — | Land value capture and O&M financing model |
| Procurement / Transaction Plan | Gap | — | Transaction strategy & investor sounding |

### 4.8.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | Public delivery with PPP components for serviced land parcels |
| Operator & O&M | Municipal planning department; private developers for serviced plots |
| Revenue / Cost Recovery | Land lease and readjustment proceeds; municipal budget allocation |
| Funding Mix | Public capital budget + donor grant/concessional debt + private co-investment in serviced plots; municipal own-source revenue supports O&M |

### 4.8.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 02 (Corridor Upgrade) | Road network supports planned expansion areas |
| With Priority 03 (FTZ) | New housing and services for FTZ workers |
| With Priority 04 (Solid Waste) | Waste services for new expansion areas |
| With Priority 05 (Youth Centre) | Youth housing and services in expansion areas |
| With Priority 06 (Reception Centre) | Housing for returnees |

### 4.8.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| Informal settlement encroachment ahead of servicing | Early expansion boundary enforcement; kebele-level coordination |
| Land acquisition & resettlement across expansion area | Early resettlement action plan (RAP); TWCA/regional coordination |
| Infrastructure financing gap for phased servicing | Phased delivery aligned with TWUEP implementation phases; blended finance structure |
| Inadequate infrastructure capacity | Comprehensive infrastructure planning; phased implementation |
| Market demand uncertainty | Land value capture mechanisms; phased development |
| Environmental degradation | Environmental protection measures; green infrastructure |

### 4.8.9 Next Steps

Priority Action: Develop a Detailed Phase 1 Land-Use Plan

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / GIS & Surveying Department |
| Estimated Cost | USD 200,000 - 300,000 |
| Expected Outcome | Detailed land-use plan ready for financing and implementation |

#### 4.8.9.1 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Review TWUEP expansion boundaries | Week 1-2 | GIS Department | Confirmed expansion areas |
| Conduct land use assessment | Week 2-4 | Urban Planning Team | Land suitability analysis |
| Develop Phase 1 land-use plan | Week 4-12 | Project Director | Detailed land-use plan |
| Engage stakeholders | Ongoing | Engagement Team | Community input and buy-in |
| Prepare feasibility study TOR | Week 4-8 | Project Director | Consultant procurement ready |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418
Abdiwasac Khaliif Muhumed – GIS & Surveying Department

Project Website: www.twuep.com.et

## 4.9 PRIORITY 02: CORRIDOR & ARTERIAL ROAD UPGRADE — DETAILED PROFILE

### 4.9.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Corridor & Arterial Road Upgrade |
| Description | A 20 km programme of arterial and corridor road upgrades across Tog-Wajaale |
| Indicative Investment | USD 40,000,000 (Birr 6,401,276,000)* |
| Sector | Transport Infrastructure |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Concessional loan / grant |
| Ranking Rationale | Connectivity - Essential for access to FTZ, urban expansion areas, and trade corridor; addresses immediate infrastructure deficit |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 4.9.2 Strategic Rationale

#### 4.9.2.1 Current Infrastructure Challenges

Much of Tog-Wajaale's road network is unpaved, undrained or unfit, and cannot support the city's rapid growth or its role as a trade corridor. Poor drainage causes flooding on several routes, constraining safe movement for residents and traders.

| Challenge | Description | Impact |
| --- | --- | --- |
| Unpaved Roads | Significant portions of the road network remain unpaved, limiting accessibility | Reduced mobility; increased transport costs |
| Poor Drainage | Inadequate drainage causes flooding on several routes, particularly during rainy seasons | Flood damage; road closures; safety risks |
| Congestion | Increasing traffic volumes from cross-border trade strain existing road capacity | Travel delays; reduced economic efficiency |
| Safety Concerns | Lack of proper lighting, signage, and pedestrian facilities creates safety risks | Accidents; injuries; fatalities |
| Limited Accessibility | Poor road conditions constrain safe movement for residents and traders | Reduced economic activity; social exclusion |

#### 4.9.2.2 Why This is Priority #2

| Reason | Description |
| --- | --- |
| Connectivity | Provides access to FTZ, urban expansion areas, and trade corridor |
| Trade Facilitation | Reduces transport costs and transit times |
| Safety | Improves road safety through proper infrastructure |
| Flood Management | Addresses critical drainage and flooding issues |
| Enabling Investment | Creates conditions for economic development |

#### 4.9.2.3 Recent Infrastructure Developments

| Initiative | Details | Relevance |
| --- | --- | --- |
| Tog-Wajaale Border Bridge Reconstruction | TradeMark Africa launched reconstruction in May 2026 with Sweden funding; includes structural reinforcement, wadi river drainage, and flood wall barriers | Enhanced cross-border connectivity |
| One-Stop Border Post (OSBP) | Feasibility study recommends a juxtaposed model for Tog-Wajaale OSBP; ongoing upgrades aim to streamline procedures | Streamlined customs; reduced delays |
| Jigjiga-Tog Wajaale Power Transmission Line | 73.1 km 400kV double circuit transmission line proposed | Reliable power supply for infrastructure |
| Berbera Corridor Road Upgrades | UK funding of over USD 16.6 million channelled through TradeMark Africa; EU has invested in Berbera-Hargeisa-Tog-Wajaale highway | Regional connectivity; trade facilitation |
| Tog-Wajaale Weighbridge Project | Underway to facilitate transit and transport between Ethiopia and Somaliland | Regulated transport; road protection |

#### 4.9.2.4 Population Growth Driving Demand

The city's population is projected to grow from 82,064 to 119,000 by 2030 and 554,700 by 2055, placing increasing demands on the transport network. The urban area is expected to expand 12.6-fold by 2055, requiring planned road infrastructure to support this growth.

| Year | Population | Travel Demand (Est.) |
| --- | --- | --- |
| 2024 | 82,064 | Baseline |
| 2030 | 119,000 | +45% |
| 2055 | 554,700 | +576% |

### 4.9.3 Project Scope

#### 4.9.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Arterial Road Development | Construction and upgrade of 20 km priority roads | 20,000,000 | 3,200,638,000 |
| Drainage & Stormwater Systems | Comprehensive drainage infrastructure | 6,000,000 | 960,191,400 |
| Sidewalks & Pedestrian Facilities | Safe pedestrian infrastructure | 5,000,000 | 800,159,500 |
| Street Lighting & Traffic Safety | Lighting, signage, and safety features | 5,000,000 | 800,159,500 |
| Landscaping & Green Buffers | Green infrastructure and environmental integration | 4,000,000 | 640,127,600 |
| TOTAL |  | 40,000,000 | 6,401,276,000 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

#### 4.9.3.2 Component Details

1. Arterial Road Development (USD 20,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Road Construction | 20 km of new and upgraded arterial roads | 4-6 lane standard with BRT integration |
| Pavement Design | Durable pavement for heavy vehicle traffic | Designed for 20-30 year lifespan |
| Geometric Design | Improved road geometry for safety and efficiency | International road design standards |
| Intersection Improvements | Upgraded intersections with traffic controls | Signalized intersections where needed |
| Right-of-Way | 50m corridor width | Adequate for road, BRT, and NMT |

2. Drainage & Stormwater Systems (USD 6,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Stormwater Drainage | Comprehensive drainage systems | 1-in-10-year and 1-in-50-year flood design |
| Culverts & Crossings | Crossings for water flow | Adequate capacity for seasonal flows |
| Flood Protection | Climate-resilient flood protection measures | Elevated segments where needed |
| Permeable Pavements | Sustainable drainage solutions | Where geotechnically suitable |

3. Sidewalks & Pedestrian Facilities (USD 5,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Pedestrian Walkways | Safe sidewalks along upgraded routes | 2-3m wide walkways |
| Crossings | Safe pedestrian crossings | At-grade and elevated crossings |
| Accessibility | Accessible design for persons with disabilities | Universal design principles |
| Shaded Walkways | Protection from sun in hot semi-arid climate | Shade structures and trees |

4. Street Lighting & Traffic Safety (USD 5,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Street Lighting | Adequate lighting for safety and security | LED lighting; solar where feasible |
| Traffic Signs | Comprehensive signage | International standard signage |
| Road Markings | Clear road markings | Durable, reflective markings |
| Safety Barriers | Physical safety measures | Where needed for safety |
| Traffic Signals | Signalized intersections where needed | Modern traffic signal systems |

5. Landscaping & Green Buffers (USD 4,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Green Buffers | Landscaping along roads | Native, drought-resistant species |
| Tree Planting | Shade trees and vegetation | 1-2 rows of trees per road |
| Aesthetic Improvement | Enhanced visual appeal | Integrated landscape design |
| Environmental Integration | Integration with natural environment | Ecological considerations |

### 4.9.4 Value Creation

#### 4.9.4.1 Expected Outcomes

| Outcome | Target |
| --- | --- |
| People/Businesses Served | 82,064+ (growing to 554,700 by 2055) |
| Jobs Created | ~900 construction jobs |
| Travel Time | 30% reduction in travel time |
| Safety | 50% reduction in road accidents |
| Flood Risk | Reduced flooding on priority routes |
| Accessibility | Improved access to economic zones |

#### 4.9.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Trade Facilitation | Improved road conditions reduce transport costs and transit times |
| Market Access | Enhanced connectivity to markets during rainy seasons |
| Safety | Reduced road accidents through improved infrastructure |
| Urban Mobility | Improved movement for residents and businesses |
| Economic Growth | Better roads attract investment and support economic activity |
| Emergency Access | Improved access for emergency services |
| Climate Resilience | Flood-resistant design protects infrastructure |

#### 4.9.4.3 Cost-Benefit Indicators

| Indicator | Estimated Impact |
| --- | --- |
| Transport Cost Reduction | 20-30% reduction in vehicle operating costs |
| Travel Time Savings | USD 5-10 million annually in time savings |
| Accident Reduction | 50% reduction in accident costs |
| Flood Damage Reduction | Significant reduction in flood-related damages |

### 4.9.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | TWUEP road network maps identify priority corridors; population growing 82,064 → 554,700 | Formal prioritisation & traffic study |
| Site / Land & Approvals | In progress | Existing & expansion road network mapped citywide | ROW survey and titling per route |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & design |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 40M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | Flood-risk zones mapped (TWUEP Ch.4) | ESIA and resettlement action plan |
| Revenue, O&M & Delivery Model | Gap | — | O&M budget and maintenance plan |
| Procurement / Transaction Plan | Gap | — | Transaction strategy & contractor sourcing |

#### 4.9.5.1 Bankability Strengths

| Strength | Description |
| --- | --- |
| Strong Policy Support | Aligned with TWUEP and regional development plans |
| Clear Demand | Population growth and trade volumes demonstrate clear need |
| Strategic Location | Supports the Berbera corridor trade route |
| Climate Resilience | Addresses flood risks through improved drainage |
| Social Benefits | Improved safety and accessibility for all residents |

#### 4.9.5.2 Bankability Gaps

| Gap | Description | Required Action |
| --- | --- | --- |
| Feasibility Study | No detailed feasibility study completed | Commission full feasibility study |
| Traffic Data | No formal traffic survey conducted | Conduct traffic and demand study |
| ESIA | Environmental assessment not completed | Commission ESIA and RAP |
| O&M Plan | No maintenance plan developed | Develop O&M budget and plan |

### 4.9.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | Public delivery — TWCA capital works programme |
| Operator & O&M | Municipal roads authority |
| Revenue / Cost Recovery | Municipal budget allocation; potential road-user fees |
| Funding Mix | Public capital budget + donor grant/concessional debt; TWCA own-source revenue supports O&M, not earmarked as capital |

#### 4.9.6.1 Project Implementation Structure

text

┌─────────────────────────────────────────────────────────────┐

│ PROJECT OVERSIGHT │

│ Tog-Wajaale City Administration │

│ (Mayor's Office / City Manager) │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────────────┴────────────────────────────────────┐

│ PROJECT MANAGEMENT │

│ Project Director / Manager │

│ Urban Expansion Team / Technical Team │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────┼────────────────┐

│ │ │

▼ ▼ ▼

┌───────────────┐ ┌───────────────┐ ┌───────────────┐

│ FEASIBILITY │ │ DESIGN & │ │ CONSTRUCTION │

│ & DESIGN │ │ PLANNING │ │ CONTRACTOR │

│ CONSULTANT │ │ CONSULTANT │ │ │

└───────────────┘ └───────────────┘ └───────────────┘

### 4.9.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 01 (Urban Expansion) | Road network supports planned expansion areas |
| With Priority 03 (FTZ) | Access roads connect FTZ to the Berbera corridor and city centre |
| With Border Bridge | Complementary infrastructure for cross-border connectivity |
| With OSBP Implementation | Improved road access supports streamlined border procedures |
| With Priority 04 (Solid Waste) | Road access enables waste collection in expanded areas |
| With BRT Corridor | Road upgrade integrates with proposed BRT system |

### 4.9.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| Land acquisition & right-of-way clearance delays | Early land-use mapping; engage kebele and clan elders (Ugaas); transparent compensation |
| Flash flooding on riverbed-adjacent routes | Climate-resilient drainage, permeable pavements, elevated segments |
| Delay in detailed engineering | Early appointment of design consultant; dedicated feasibility budget line |
| Coordination with border infrastructure projects | Align with Tog-Wajaale Bridge reconstruction and OSBP implementation timelines |
| Cost escalation | Phased implementation; fixed-price contracts; contingency provisions |
| Community opposition | Participatory planning; benefit-sharing; transparent communication |
| Inadequate maintenance funding | Dedicated O&M budget line; performance-based maintenance contracts |

### 4.9.9 Implementation Phasing

#### 4.9.9.1 Phase 1: Feasibility & Design (2025-2026)

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Road Prioritisation Study | Months 1-3 | Project Director |
| Traffic Survey and Analysis | Months 2-5 | Transport Consultant |
| Feasibility Study | Months 3-8 | Feasibility Consultant |
| ESIA and RAP | Months 4-9 | Environmental Consultant |
| Detailed Design | Months 6-12 | Design Consultant |
| Procurement Preparation | Months 10-12 | Procurement Team |

#### 4.9.9.2 Phase 2: Construction (2026-2029)

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Site Preparation | Months 1-3 | Contractor |
| Drainage Works | Months 3-9 | Contractor |
| Road Construction | Months 6-24 | Contractor |
| Sidewalks and NMT | Months 18-30 | Contractor |
| Lighting and Safety | Months 24-33 | Contractor |
| Landscaping | Months 30-36 | Contractor |

#### 4.9.9.3 Phase 3: Commissioning & Handover (2029-2030)

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Testing and Commissioning | Months 34-36 | Contractor |
| Training | Months 34-36 | Contractor/Operator |
| Handover | Month 36 | Contractor/Project Team |
| Post-Implementation Review | Month 38 | Project Team |

### 4.9.10 Next Steps

#### 4.9.10.1 Priority Action

Commission a Road Prioritisation & Feasibility Study

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / Urban Expansion Team |
| Estimated Cost | USD 300,000 - 500,000 |
| Expected Outcome | Prioritised road upgrade plan with detailed feasibility and cost estimates |

#### 4.9.10.2 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Finalise road prioritisation criteria | Week 1-2 | Project Director | Clear prioritisation framework |
| Conduct preliminary traffic surveys | Week 2-6 | Transport Consultant | Traffic volume and demand data |
| Identify priority road sections | Week 4-8 | Urban Expansion Team | Prioritised road list |
| Prepare feasibility study TOR | Week 4-8 | Project Director | Consultant procurement ready |
| Engage stakeholders | Ongoing | Engagement Team | Community input and buy-in |
| Develop preliminary cost estimates | Week 8-12 | Infrastructure Specialist | Indicative project costs |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418
Mohammed Muhumed Ahmed – Infrastructure Development Specialist

Project Website: www.twuep.com.et

## 4.10 PRIORITY 03: INLAND SPECIAL TRADE ZONE & LOGISTICS HUB — DETAILED PROFILE

### 4.10.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Inland Special Trade Zone & Logistics Hub |
| Description | A 50-hectare special trade zone and dry port adjacent to the border crossing |
| Indicative Investment | USD 250,000,000 (Birr 40,007,975,000)* |
| Sector | Trade & Industrial Infrastructure |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | PPP / Concession |
| Ranking Rationale | Economic Engine - Largest economic impact; leverages strategic location; creates 6,000+ jobs; catalytic for private investment |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 4.10.2 Strategic Rationale

#### 4.10.2.1 The Opportunity

Cross-border traders and manufacturers at Tog-Wajaale lack a dedicated dry port, warehousing and customs-facilitation infrastructure. An informal FTZ has traded livestock, textiles and electronics since 2015, but rising bilateral trade with Somaliland has outpaced its unserviced footprint.

| Issue | Description |
| --- | --- |
| No Dedicated Dry Port | No formal container handling or logistics infrastructure |
| Limited Warehousing | Inadequate storage and distribution facilities |
| Customs Bottlenecks | No on-site customs facilitation |
| Informal Operations | Trade conducted without formal infrastructure |
| Growing Demand | Trade volumes increasing but infrastructure not keeping pace |

#### 4.10.2.2 Why This is Priority #3

| Reason | Description |
| --- | --- |
| Economic Impact | Largest investment and job creation potential (~6,000 jobs) |
| Strategic Location | Leverages Tog-Wajaale's position on the Berbera corridor |
| Catalytic Effect | Attracts private investment and anchor tenants |
| Trade Facilitation | Enhances cross-border trade and regional integration |
| Revenue Generation | Significant revenue through land lease, service charges, and customs |

#### 4.10.2.3 Strategic Location Benefits

| Element | Description |
| --- | --- |
| Distance from Hargeisa | ~90 km |
| Distance from Port of Berbera | ~249 km |
| Distance from Jigjiga | ~70 km |
| Distance from Harar | ~175 km |
| Corridor Role | Key node on the Berbera-to-Ethiopia economic corridor |
| Trade Volume | Handles approximately 95% of eastern Ethiopia's imports and exports |

#### 4.10.2.4 Recent Major Infrastructure Developments

| Infrastructure Project | Details | Impact on FTZ |
| --- | --- | --- |
| Berbera-Tog-Wajaale Railway | UAE confirmed plans to finance a 250 km railway linking Tog-Wajaale to Berbera, project valued at USD 3 billion | Enhanced logistics connectivity; reduced transport costs |
| Tog-Wajaale Border Bridge Reconstruction | TradeMark Africa launched reconstruction in May 2026 with Sweden funding through SWIFT Programme | Improved cross-border connectivity; facilitated trade |
| One-Stop Border Post (OSBP) | Feasibility study recommends a juxtaposed model for Tog-Wajaale OSBP; ongoing upgrades | Streamlined customs procedures; reduced delays |
| Berbera Corridor Road Upgrades | UAE pledged additional USD 100 million to upgrade the 250 km road connecting Berbera to Tog-Wajaale | Improved road access; reduced transport costs |
| Jigjiga-Tog-Wajaale Power Transmission Line | 73.1 km 400kV double circuit transmission line proposed | Reliable power supply for industrial operations |

#### 4.10.2.5 Trade Significance

| Element | Description |
| --- | --- |
| Market Operations | 24 hours a day, 7 days a week |
| Trade Types | Formal and informal trade |
| Key Commodities | Livestock, textiles, electronics, agricultural products |
| Cross-Border Trade | Increasing bilateral trade with Somaliland |
| Regional Hub | Serves as a gateway for trade in the Horn of Africa |

#### 4.10.2.6 Investment Context

| Investment | Details | Relevance |
| --- | --- | --- |
| UAE Railway Investment | USD 3 billion for 250 km railway linking Tog-Wajaale to Berbera | Transformative connectivity; anchor for FTZ development |
| Berbera Corridor Road Investment | USD 100 million for road upgrades | Improved transport access; reduced logistics costs |
| UK/EU Corridor Funding | USD 16.6 million (UK) + EU investment in Berbera-Hargeisa-Tog-Wajaale highway | Enhanced regional connectivity |
| IGAD RMF Investment | Germany €8 million grant for migration corridor infrastructure | Complementary development; community benefits |

### 4.10.3 Project Scope

#### 4.10.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Dry Port & Logistics Hub | Container handling, customs clearance, logistics | 70,000,000 | 11,202,233,000 |
| Warehousing & Distribution Parks | Storage and distribution facilities | 50,000,000 | 8,001,595,000 |
| Industrial Parks & Manufacturing Zones | Production and processing facilities | 60,000,000 | 9,601,914,000 |
| Customs & Trade Facilitation | On-site customs clearance and trade services | 30,000,000 | 4,800,957,000 |
| Commercial & Business Services | Office space, retail, and support services | 20,000,000 | 3,200,638,000 |
| Supporting Utilities | Power, water, telecommunications | 20,000,000 | 3,200,638,000 |
| TOTAL |  | 250,000,000 | 40,007,975,000 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

#### 4.10.3.2 Component Details

1. Dry Port & Logistics Hub (USD 70,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Container Handling | Container yard and handling equipment | 20,000+ TEU capacity |
| Customs Clearance | On-site customs clearance facilities | Integrated customs services |
| Logistics Services | Logistics and freight forwarding services | Full-service logistics hub |
| Storage Facilities | General and specialized storage | 50,000+ sqm storage |
| Container Yard | Container storage and handling | 5+ ha container yard |

2. Warehousing & Distribution Parks (USD 50,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| General Warehousing | Standard warehousing facilities | 100,000+ sqm |
| Cold Storage | Temperature-controlled storage | 20,000+ sqm cold storage |
| Distribution Centre | Central distribution facilities | Full logistics services |
| Value-Added Services | Packaging, labelling, processing | Value-added logistics |

3. Industrial Parks & Manufacturing Zones (USD 60,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Manufacturing Facilities | Production and assembly facilities | 50,000+ sqm factory space |
| Agro-Processing | Agricultural processing facilities | Food processing; livestock |
| Textile & Garment | Textile and garment production | Garment manufacturing |
| Light Manufacturing | Light industrial facilities | Electronics; assembly |

4. Customs & Trade Facilitation (USD 30,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Customs Facilities | Customs clearance offices | Full-service customs |
| Trade Services | Trade facilitation services | One-stop trade services |
| Inspection Facilities | Quality control and inspection | Quality assurance |
| Administration | Administrative offices | FTZ management |

5. Commercial & Business Services (USD 20,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Office Buildings | Business and administrative offices | 20,000+ sqm |
| Retail Spaces | Commercial and retail areas | 10,000+ sqm |
| Banking Services | Financial services | Full banking services |
| Business Support | Business advisory and support | Business incubation |

6. Supporting Utilities (USD 20,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Power Supply | Reliable electricity supply | 20+ MW capacity |
| Water Supply | Clean water for industrial use | 5,000+ m³/day |
| Telecommunications | High-speed connectivity | Fiber optic connectivity |
| Waste Management | Industrial waste management | Treatment facilities |

### 4.10.4 Value Creation

#### 4.10.4.1 Expected Outcomes

| Outcome | Target | Measurement |
| --- | --- | --- |
| Jobs Created | ~6,000 direct and indirect jobs | Employment records |
| Companies Established | 100+ companies | FTZ registration |
| Trade Volume | USD 500 million+ annually | Customs records |
| Tax Revenue | USD 50 million+ annually | Revenue records |
| Economic Growth | 5%+ contribution to city GDP | Economic analysis |
| Projected City Population Served (2055) | 554,700 | Census data |

#### 4.10.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Economic Diversification | Diversifies economy beyond traditional trade and agriculture |
| Regional Integration | Strengthens Ethiopia-Somaliland trade ties |
| Investment Attraction | Attracts domestic and foreign direct investment |
| Technology Transfer | Facilitates technology transfer and skills development |
| Value Addition | Promotes value addition to local products |
| Foreign Exchange | Generates foreign exchange through exports |

#### 4.10.4.3 Social Impact

| Impact | Description |
| --- | --- |
| Women's Employment | 40% target for women in employment |
| Youth Employment | Significant youth employment opportunities |
| Host Community Benefits | Benefits for displaced persons and host communities |
| Skills Development | Training and skills development for local workforce |
| Community Investment | Infrastructure and services benefiting local communities |

### 4.10.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | Informal FTZ trading since 2015; TWUEP names cross-border SEZs a priority; pop. growing 82,064 → 554,700 | Formal market / tenant demand study |
| Site / Land & Approvals | In progress | Indicative 50 ha site identified adjacent to border crossing | Land survey, titling and zoning approval |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & master plan |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 250M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | — | ESIA and safeguard instruments |
| Revenue, O&M & Delivery Model | Gap | — | Financial model, lease/tariff structure |
| Procurement / Transaction Plan | Gap | — | Transaction strategy & investor/operator sounding |

#### 4.10.5.1 Bankability Strengths

| Strength | Description |
| --- | --- |
| Strategic Location | Prime position on the Berbera trade corridor |
| Demand Evidence | Informal FTZ trading since 2015 demonstrates demand |
| Infrastructure Pipeline | Confirmed investments in railway, road, and bridge |
| Policy Support | TWUEP prioritizes cross-border SEZs |
| Revenue Potential | Significant revenue through land lease and customs |
| PPP Suitability | Attractive for private sector investment |

#### 4.10.5.2 Bankability Gaps

| Gap | Description | Required Action |
| --- | --- | --- |
| Market Study | No formal tenant demand study | Commission market and demand study |
| Feasibility Study | No detailed feasibility analysis | Commission full feasibility study |
| ESIA | Environmental assessment not completed | Commission ESIA and safeguards |
| Financial Model | No detailed financial model | Develop financial model |
| PPP Structure | No PPP framework developed | Engage PPP advisor |

### 4.10.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | PPP / concession via a dedicated Special Purpose Vehicle (SPV) |
| Operator & O&M | Private concessionaire responsible for zone operations & maintenance |
| Revenue / Cost Recovery | Land lease, service charges and tenant fees |
| Funding Mix | Private equity/debt + government land as equity-in-kind; TWCA own-source revenue (ETB 144M FY2018EC - ETB 195M FY2019EC - USD 0.9-1.2M) supports capacity, not zone capital |

#### 4.10.6.1 Recommended PPP Structure

text

┌─────────────────────────────────────────────────────────────┐

│ PROJECT OVERSIGHT │

│ Tog-Wajaale City Administration │

│ (Mayor's Office / City Manager) │

└────────────────────────┬────────────────────────────────────┘

│

│ Concession Agreement

▼

┌─────────────────────────────────────────────────────────────┐

│ CONCESSIONAIRE (SPV) │

│ Private Consortium (Equity Investors) │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────┼────────────────┐

│ │ │

▼ ▼ ▼

┌───────────────┐ ┌───────────────┐ ┌───────────────┐

│ DESIGN │ │ CONSTRUCTION │ │ OPERATIONS │

│ CONTRACTOR │ │ CONTRACTOR │ │ & O&M │

└───────────────┘ └───────────────┘ └───────────────┘

#### 4.10.6.2 Revenue Streams

| Revenue Source | Description | Estimated Annual Revenue (USD) |
| --- | --- | --- |
| Land Leases | Lease payments for industrial/commercial plots | 5,000,000 |
| Infrastructure Fees | Fees for utilities and infrastructure services | 3,000,000 |
| Service Charges | Management and service fees | 2,000,000 |
| Customs Revenue | Import/export duties (government share) | 10,000,000 |
| Tax Revenue | Corporate and income tax (government share) | 15,000,000 |
| Rental Income | Building and facility rentals | 5,000,000 |
| TOTAL |  | 40,000,000 |

### 4.10.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 01 (Urban Expansion) | New housing and services for FTZ workers |
| With Priority 02 (Corridor Upgrade) | Access roads connect FTZ to the Berbera corridor |
| With Priority 04 (Solid Waste) | Waste services for FTZ and industrial facilities |
| With Priority 05 (Youth Centre) | Skilled workforce for FTZ industries |
| With Priority 06 (Reception Centre) | Employment opportunities for returnees |
| With Border Bridge | Enhanced connectivity and trade facilitation |
| With OSBP Implementation | Streamlined customs procedures for FTZ operations |
| With Berbera Railway | Enhanced logistics connectivity |

### 4.10.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| FTZ investor / tenant demand uptake | Anchor tenant pre-agreements; phased development from a serviced first phase; market sounding study |
| Cross-border customs & bilateral coordination | Formal MOU with customs and border authorities; phased licensing aligned with bilateral trade talks |
| Land acquisition & resettlement within zone footprint | Early resettlement action plan (RAP); TWCA/regional coordination ahead of construction |
| Competition from other FTZs | Unique value proposition; competitive incentives |
| Infrastructure delivery delays | Phased implementation; experienced developers |
| Political instability in border region | Strong bilateral framework; diplomatic engagement |
| Currency fluctuation | Currency hedging; indexation mechanisms |
| Financial viability | Anchor tenants; diversified revenue streams |

### 4.10.9 Implementation Phasing

#### 4.10.9.1 Phase 1: Feasibility & Planning (2025-2026)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Market & Tenant Demand Study | Months 1-6 | Consultant | 200,000 |
| Feasibility Study & Master Plan | Months 3-9 | Consultant | 400,000 |
| ESIA and Safeguards | Months 4-9 | Consultant | 250,000 |
| PPP Structuring | Months 6-12 | PPP Advisor | 300,000 |
| Financial Model | Months 6-12 | Consultant | 200,000 |
| TOTAL |  |  | 1,350,000 |

#### 4.10.9.2 Phase 2: Site Development (2027-2029)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Land Acquisition | Months 1-6 | Legal Team | 15,000,000 |
| Site Preparation | Months 3-9 | Contractor | 20,000,000 |
| Infrastructure Development | Months 6-24 | Contractor | 50,000,000 |
| Dry Port & Logistics Hub | Months 12-24 | Contractor | 40,000,000 |
| TOTAL |  |  | 125,000,000 |

#### 4.10.9.3 Phase 3: Facility Development (2029-2031)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Warehousing & Distribution | Months 18-30 | Contractor | 30,000,000 |
| Industrial Parks | Months 24-36 | Contractor | 40,000,000 |
| Commercial Facilities | Months 24-36 | Contractor | 20,000,000 |
| Supporting Utilities | Months 18-30 | Contractor | 15,000,000 |
| TOTAL |  |  | 105,000,000 |

#### 4.10.9.4 Phase 4: Operationalization (2031-2035)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Tenant Acquisition | Ongoing | Operator | - |
| Full Operations | 2033+ | Operator | - |
| Phased Expansion | 2031-2035 | Developer | 18,650,000 |
| TOTAL |  |  | 18,650,000 |

### 4.10.10 Next Steps

#### 4.10.10.1 Priority Action

Launch a Formal Market & Tenant Demand Study

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / Urban Expansion Team |
| Estimated Cost | USD 150,000 - 250,000 |
| Expected Outcome | Evidence base for investor engagement and PPP structuring |

#### 4.10.10.2 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Finalise market study TOR | Week 1-3 | Project Director | Consultant procurement ready |
| Engage potential anchor tenants | Week 2-8 | Investment Specialist | Letters of intent from tenants |
| Conduct preliminary investor sounding | Week 4-10 | Project Director | Investor interest assessment |
| Identify PPP advisor | Week 4-8 | Procurement Team | PPP advisor engaged |
| Develop preliminary financial model | Week 8-12 | Financial Specialist | Initial financial projections |
| Engage stakeholders | Ongoing | Engagement Team | Community and business input |

#### 4.10.10.3 Immediate Actions

| Action | Responsible | Timeline |
| --- | --- | --- |
| Formalise MOU with customs and border authorities | Mayor's Office | 0-60 days |
| Confirm 50 ha site location and zoning | GIS Department | 0-45 days |
| Engage TradeMark Africa for corridor coordination | Project Director | 0-30 days |
| Launch market study procurement | Procurement Team | 0-30 days |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418

Project Website: www.twuep.com.et

## 4.11 PRIORITY 04: SOLID WASTE MANAGEMENT SYSTEM — DETAILED PROFILE

### 4.11.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Solid Waste Management System |
| Description | A citywide solid waste management system delivering a clean, healthy city |
| Indicative Investment | USD 10,000,000 (Birr 1,600,319,000)* |
| Sector | Municipal Services & Environment |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Grant / concessional loan |
| Ranking Rationale | Livability - Environmental and public health imperative; essential for livable city; relatively low-cost, high-impact |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 4.11.2 Strategic Rationale

#### 4.11.2.1 Current Situation

Tog-Wajaale has no engineered landfill, formal collection fleet or recycling capacity. Uncollected waste accumulates in open sites and waterways, posing health and environmental risks that will intensify as population grows.

| Issue | Description | Impact |
| --- | --- | --- |
| No Engineered Landfill | Waste is disposed of in open, unregulated sites | Environmental contamination; public health risks |
| No Formal Collection | Absence of organized waste collection services | Uncollected waste accumulates; visual pollution |
| No Recycling Capacity | No facilities for waste segregation or recycling | Resource loss; increased landfill burden |
| Waterway Pollution | Waste accumulates in waterways, causing contamination | Water contamination; ecosystem damage |
| Health Risks | Open waste sites pose significant public health risks | Disease transmission; respiratory issues |

#### 4.11.2.2 Population Growth Driving Demand

| Year | Population | Waste Generation (Est. kg/day)* | Waste Generation (tonnes/year) |
| --- | --- | --- | --- |
| 2024 | 82,064 | ~41,000 | ~15,000 |
| 2030 | 119,000 | ~59,500 | ~21,700 |
| 2055 | 554,700 | ~277,000 | ~101,000 |

*Based on estimated waste generation of 0.5 kg/person/day (typical for developing urban centers)

#### 4.11.2.3 Why This is Priority #4

| Reason | Description |
| --- | --- |
| Public Health | Addresses immediate health and environmental risks |
| Environmental Protection | Prevents water contamination and pollution |
| Low Cost, High Impact | USD 10 million investment with significant benefits |
| Population Growth | Essential as city grows toward 554,700 residents |
| Climate Action | Reduces methane emissions from open waste |
| Quality of Life | Creates a cleaner, more attractive city |

#### 4.11.2.4 Environmental and Health Risks

| Risk | Description | Severity |
| --- | --- | --- |
| Water Contamination | Leachate from open waste sites contaminates groundwater and surface water | High |
| Air Pollution | Open burning of waste releases harmful emissions | High |
| Disease Vectors | Uncollected waste attracts pests and disease vectors | Medium |
| Flood Risk | Waste blocking drainage channels increases flood risk | Medium |
| Greenhouse Gas Emissions | Methane emissions from decomposing organic waste | High |
| Visual Pollution | Open waste sites degrade the urban environment | Medium |

#### 4.11.2.5 Legal and Policy Framework

| Framework | Relevance |
| --- | --- |
| TWUEP Chapter 4 | Identifies environmental hazards and waste management as a priority |
| Federal Environmental Protection Authority | National standards for waste management |
| National Solid Waste Management Strategy | Framework for sustainable waste management |
| SDG 11.6 | Reduce environmental impact of cities |
| SDG 12.4 | Environmentally sound management of chemicals and waste |
| SDG 13 | Climate action through methane reduction |

### 4.11.3 Project Scope

#### 4.11.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Engineered Landfill Disposal Site | Sanitary landfill with environmental controls | 3,000,000 | 480,095,700 |
| Transfer Stations | Network of collection points across the city | 2,000,000 | 320,063,800 |
| Collection Fleet & Equipment | Modern waste collection vehicles and equipment | 2,500,000 | 400,079,750 |
| Waste Segregation & Recycling Centre | Sorting, processing, and recycling facilities | 1,500,000 | 240,047,850 |
| Community Awareness & Capacity Building | Public education and training programmes | 1,000,000 | 160,031,900 |
| TOTAL |  | 10,000,000 | 1,600,319,000 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

#### 4.11.3.2 Component Details

1. Engineered Landfill Disposal Site (USD 3,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Site Selection | Geologically suitable location with proper access | 10-15 ha site |
| Liner System | Engineered liner to prevent groundwater contamination | HDPE liner + clay |
| Leachate Management | Collection and treatment of leachate | Treatment pond system |
| Gas Management | Methane gas collection and flaring (or utilization) | Gas collection system |
| Cover System | Daily and final cover to control odours and pests | Soil cover system |
| Access Roads | All-weather access for collection vehicles | Paved access road |
| Fencing | Security and control | Perimeter fencing |
| Site Office | Administrative and control facilities | Office and weighbridge |

2. Transfer Stations (USD 2,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Station Locations | Strategically located across the city | 3-5 stations |
| Waste Transfer | Collection and consolidation of waste | Covered transfer area |
| Compaction | Compaction for efficient transport to landfill | Compactor equipment |
| Environmental Controls | Odour control and pest management | Ventilation; pest control |
| Access | All-weather access for collection vehicles | Paved access |
| Staff Facilities | Amenities for workers | Facilities and offices |

3. Collection Fleet & Equipment (USD 2,500,000)

| Element | Quantity | Unit Cost (USD) | Total Cost (USD) | Specification |
| --- | --- | --- | --- | --- |
| Compactor Trucks | 5 | 200,000 | 1,000,000 | 20-tonne capacity |
| Collection Vehicles | 10 | 80,000 | 800,000 | 10-tonne capacity |
| Sweeping Equipment | 2 | 150,000 | 300,000 | Mechanical sweepers |
| Containers & Bins | 200+ | 2,000 | 400,000 | 1.1m³ and 4m³ containers |
| TOTAL |  |  | 2,500,000 |  |

4. Waste Segregation & Recycling Centre (USD 1,500,000)

| Element | Description | Specification |
| --- | --- | --- |
| Segregation Line | Manual and mechanical sorting of waste | Sorting belt and stations |
| Recycling Facilities | Processing of recyclable materials | Plastic; paper; metal; glass |
| Composting Facility | Organic waste composting | Aerated static pile system |
| Storage Area | Storage for recyclable materials | Covered storage |
| Administration | Office and management facilities | Administrative building |
| Weighbridge | Weight recording | Truck weighbridge |

5. Community Awareness & Capacity Building (USD 1,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Public Education | Awareness campaigns on waste management | Campaigns; materials; events |
| Behaviour Change | Promotion of waste segregation and recycling | Behaviour change programmes |
| Training | Training for waste management workers | Technical and safety training |
| School Programmes | Environmental education in schools | Curriculum and activities |
| Community Engagement | Community participation programmes | Community events and incentives |
| Monitoring | Programme effectiveness monitoring | Surveys and assessments |

### 4.11.4 Value Creation

#### 4.11.4.1 Expected Outcomes

| Outcome | Target | Measurement |
| --- | --- | --- |
| People Served | 82,064+ (growing to 554,700 by 2055) | Population coverage |
| Waste Collection Coverage | 90%+ of households | Service area mapping |
| Recycling Rate | 30%+ of waste recycled | Waste composition analysis |
| Landfill Reduction | 50% reduction in landfill waste | Landfill volume tracking |
| Jobs Created | 50+ direct jobs | Employment records |

#### 4.11.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Public Health | Reduced disease transmission through proper waste management |
| Environmental Protection | Reduced pollution and contamination of water sources |
| Climate Action | Reduced methane emissions from organic waste (40%+ reduction) |
| Resource Recovery | Recycling and composting recover valuable resources |
| Aesthetic Improvement | Cleaner, more attractive city environment |
| Flood Risk Reduction | Reduced blockage of drainage channels |
| Informal Sector Integration | Integration of informal waste pickers |
| Community Empowerment | Community participation in waste management |

#### 4.11.4.3 Environmental Impact

| Indicator | Baseline | Target | Improvement |
| --- | --- | --- | --- |
| Open Dumping Sites | Multiple unregulated sites | Eliminated | 100% reduction |
| Waterway Pollution | High contamination | Low contamination | 80% reduction |
| Methane Emissions | Significant (open dumping) | Controlled (landfill gas management) | 60% reduction |
| Recycling Rate | <5% | 30%+ | 600% increase |
| Waste-to-Landfill | 100% | <50% | 50% reduction |
| Public Health Incidents | Frequent | Infrequent | 70% reduction |

### 4.11.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | TWUEP names waste management a public service priority; pop. growing 82,064 → 554,700 | Formal waste generation & composition study |
| Site / Land & Approvals | Gap | — | Landfill site identification and titling |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & design |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 10M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | — | ESIA and landfill siting safeguards |
| Revenue, O&M & Delivery Model | Gap | — | Waste levy structure and O&M plan |
| Procurement / Transaction Plan | Gap | — | Fleet & equipment procurement plan |

#### 4.11.5.1 Bankability Strengths

| Strength | Description |
| --- | --- |
| Clear Demand | No existing waste management services |
| Population Growth | Demand will increase with population growth |
| Public Health Imperative | Strong justification for investment |
| Environmental Benefits | Climate and environmental benefits |
| Low Cost | Relatively low investment for significant impact |
| Replicability | Model can be replicated in other areas |

#### 4.11.5.2 Bankability Gaps

| Gap | Description | Required Action |
| --- | --- | --- |
| Landfill Site | No site identified | Site identification and assessment |
| Waste Data | No formal waste generation data | Waste generation and composition study |
| Feasibility Study | No detailed analysis | Commission feasibility study |
| ESIA | No environmental assessment | Commission ESIA |
| Financial Model | No detailed financial projections | Develop financial model |
| O&M Plan | No maintenance and operations plan | Develop O&M plan |

### 4.11.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | Public delivery — TWCA municipal services |
| Operator & O&M | Municipal sanitation department or contracted private operator |
| Revenue / Cost Recovery | Municipal waste levy; municipal budget allocation for shortfall |
| Funding Mix | Public capital budget + donor grant/concessional debt; municipal own-source revenue supports O&M |

#### 4.11.6.1 Recommended Operating Model

text

┌─────────────────────────────────────────────────────────────┐

│ PROJECT OVERSIGHT │

│ Tog-Wajaale City Administration │

│ (Mayor's Office / City Manager) │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────────────┴────────────────────────────────────┐

│ PROJECT MANAGEMENT │

│ Municipal Sanitation Department │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────┼────────────────┐

│ │ │

▼ ▼ ▼

┌───────────────┐ ┌───────────────┐ ┌───────────────┐

│ LANDFILL │ │ COLLECTION │ │ RECYCLING │

│ OPERATOR │ │ FLEET O&M │ │ CENTRE O&M │

│ (Contractor) │ │ (Department/ │ │ (Contractor/ │

│ │ │ Contractor) │ │ Department) │

└───────────────┘ └───────────────┘ └───────────────┘

#### 4.11.6.2 Revenue Model

| Revenue Source | Description | Target |
| --- | --- | --- |
| Waste Levy | Monthly fee on households | Covers 60-80% of O&M |
| Municipal Subsidy | Budget allocation for shortfall | Covers 20-40% of O&M |
| Recycling Revenue | Sale of recyclable materials | Supplementary revenue |
| Service Fees | Commercial and industrial fees | Supplementary revenue |

### 4.11.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 01 (Urban Expansion) | Waste services planned for new expansion areas |
| With Priority 02 (Corridor Upgrade) | Road access enables waste collection in expanded areas |
| With Priority 03 (FTZ) | Waste services for FTZ and industrial facilities |
| With Priority 05 (Youth Centre) | Employment opportunities in waste sector for youth |
| With Priority 06 (Reception Centre) | Employment opportunities for returnees |
| With Climate Action | Reduced methane emissions through landfill gas management |

### 4.11.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| Landfill site selection & community acceptance | Early site screening with community consultation; formal siting criteria; engage kebele and clan elders (Ugaas) |
| Waste levy under-collection | Phase-in levy structure with municipal subsidy backstop; billing system development; community awareness campaigns |
| Fleet O&M cost overruns | Standardised equipment specification; maintenance contract with supplier; operator training |
| Recycling market volatility | Diversified recycling streams; strategic partnerships with recyclers |
| Climate impact on landfill operations | Climate-resilient design; flood protection measures |
| Community resistance to landfill | Early consultation; benefit-sharing; transparent operation |
| Inadequate technical capacity | Training; technical assistance; experienced partners |
| Political interference | Clear operational guidelines; transparent management |

### 4.11.9 Implementation Phasing

#### 4.11.9.1 Phase 1: Feasibility & Planning (2025-2026)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Waste Generation & Composition Study | Months 1-4 | Consultant | 100,000 |
| Site Identification & Assessment | Months 2-6 | Consultant | 80,000 |
| Feasibility Study | Months 3-8 | Consultant | 150,000 |
| ESIA and Safeguards | Months 4-9 | Consultant | 120,000 |
| Detailed Design | Months 6-12 | Design Consultant | 200,000 |
| Community Engagement | Ongoing | Engagement Team | 50,000 |
| TOTAL |  |  | 700,000 |

#### 4.11.9.2 Phase 2: Infrastructure Development (2026-2028)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Landfill Site Development | Months 1-12 | Contractor | 3,000,000 |
| Transfer Stations Construction | Months 6-15 | Contractor | 2,000,000 |
| Collection Fleet Procurement | Months 6-12 | Procurement Team | 2,500,000 |
| Recycling Centre Construction | Months 9-18 | Contractor | 1,500,000 |
| TOTAL |  |  | 9,000,000 |

#### 4.11.9.3 Phase 3: Operationalization (2028-2029)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Staff Recruitment & Training | Months 12-15 | HR Department | 100,000 |
| Community Awareness Campaign | Months 12-18 | Engagement Team | 100,000 |
| Waste Levy Implementation | Month 15+ | Finance Department | - |
| Full Operations | Month 18+ | Operator | - |
| TOTAL |  |  | 200,000 |

### 4.11.10 Next Steps

#### 4.11.10.1 Priority Action

Commission a Waste Generation & Composition Study

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / Environmental Compliance Officer |
| Estimated Cost | USD 100,000 - 200,000 |
| Expected Outcome | Evidence base for technical design and financing |

#### 4.11.10.2 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Finalise waste study TOR | Week 1-3 | Project Director | Consultant procurement ready |
| Identify potential landfill sites | Week 2-6 | Environmental Officer | Site shortlist |
| Conduct preliminary site assessments | Week 4-10 | Environmental Consultant | Site suitability assessment |
| Engage communities on site selection | Week 6-12 | Engagement Team | Community acceptance |
| Engage potential development partners | Week 4-10 | Project Director | Partner interest assessment |
| Develop preliminary cost estimates | Week 8-12 | Infrastructure Specialist | Indicative project costs |

#### 4.11.10.3 Immediate Actions

| Action | Responsible | Timeline |
| --- | --- | --- |
| Identify 3-5 potential landfill sites | Environmental Officer | 0-30 days |
| Engage kebele leaders on site selection | Engagement Team | 0-45 days |
| Prepare waste study procurement | Project Director | 0-30 days |
| Contact development finance partners | City Manager | 0-30 days |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418
Mohammed Isse Muhumed – Environmental Compliance Officer

Project Website: www.twuep.com.et

## 4.12 PRIORITY 05: YOUTH SKILLS, ENTERPRISE & MIGRATION CENTRE — DETAILED PROFILE

### 4.12.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Youth Skills, Enterprise & Migration Centre |
| Description | A dedicated centre delivering skills training, enterprise incubation and safe-migration services for Tog-Wajaale's fast-growing youth population |
| Indicative Investment | USD 10,000,000 (Birr 1,600,319,000)* |
| Sector | Skills, Enterprise & Migration Services |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Grant |
| Ranking Rationale | Human Capital - Addresses youth unemployment and irregular migration; builds workforce for FTZ; leverages existing programmes |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 4.12.2 Strategic Rationale

#### 4.12.2.1 The Youth Challenge

Tog-Wajaale has a young and fast-growing population. With limited access to formal skills training, enterprise support and safe migration information, many young people are pushed toward irregular, high-risk migration routes.

| Issue | Description | Impact |
| --- | --- | --- |
| Limited Skills Training | Lack of formal vocational and technical training facilities | Youth lack employable skills |
| High Youth Unemployment | Insufficient employment opportunities for young people | Economic dependency; social challenges |
| Irregular Migration | Youth pushed toward dangerous, irregular migration routes | Human rights violations; loss of life |
| Limited Enterprise Support | Lack of business incubation and entrepreneurship support | Limited economic diversification |
| No Safe Migration Information | Absence of formal migration guidance services | Vulnerability to trafficking and exploitation |

#### 4.12.2.2 Population Context

| Year | Total Population | Youth Population (15-35)* | Youth Percentage |
| --- | --- | --- | --- |
| 2024 | 82,064 | ~49,000 | ~60% |
| 2030 | 119,000 | ~71,000 | ~60% |
| 2055 | 554,700 | ~333,000 | ~60% |

*Based on 60% of population under 25 years (TWUEP demographic data)

#### 4.12.2.3 Why This is Priority #5

| Reason | Description |
| --- | --- |
| Youth Unemployment | Addresses critical youth employment challenge |
| Migration Management | Provides safe migration information and alternatives |
| Workforce Development | Builds workforce for FTZ and other economic opportunities |
| Existing Programmes | Leverages IGAD RMF and Cities Alliance programmes |
| Social Stability | Reduces desperation and social tensions |

#### 4.12.2.4 Tog-Wajaale as a Migration Corridor

Tog-Wajaale is a critical transit location for migrants from various parts of Ethiopia travelling to Middle East countries. It serves as a key node along the Eastern Migration Route, one of the busiest migration pathways in the region.

Key Migration Facts:

| Element | Description |
| --- | --- |
| Route | Eastern Migration Route to Middle East |
| Key Destination | Saudi Arabia (employment and remittances) |
| Transit Role | Primary land crossing between Ethiopia and Somaliland |
| Vulnerability | High risk of trafficking and exploitation |
| Push Factors | Poverty, unemployment, lack of opportunity |
| Pull Factors | Employment prospects, remittances |

#### 4.12.2.5 Existing Programmes and Partnerships

| Programme | Details | Relevance |
| --- | --- | --- |
| IGAD Regional Migration Fund (RMF) | Officially launched RMF project activities in Tog-Wajaale in May 2026; approved projects include upgrading the livestock market center, construction of two Community Development Centers, and a new vegetable market | Foundation for migration-related investments |
| Germany Grant | Signed an €8 million grant agreement with IGAD to scale up the RMF, focusing on key corridors including Togwajale | Significant funding for corridor development |
| IOM Migration Response Centre | Operates in Tog-Wajaale, providing protection and assistance to vulnerable migrants | Existing partner with local presence |
| Cities Alliance Programme | Supports sustainable and inclusive urban growth in cities along the 940 km trade route connecting Addis Ababa to Berbera Port | Strategic framework for corridor development |
| Save the Children International (SCI) & OWDA | Implement protection-related activities including child protection, legal assistance, psychosocial support, and family tracing | Protection services for vulnerable youth |

#### 4.12.2.6 IGAD Regional Migration Fund (RMF) Details

| Element | Details |
| --- | --- |
| Launch | Officially launched in Tog-Wajaale in May 2026 |
| Purpose | Create economic opportunities and improve living conditions of migrants, refugees, and host communities |
| Approved Projects | Upgrading livestock market center, construction of two Community Development Centers, new vegetable market |
| Funding | Germany €8 million grant to scale up RMF |
| Focus Corridors | Key corridors including Togwajale (Ethiopia–Somaliland) |
| Investment Planning | Missions conducted identifying thematic areas including livestock, agriculture, water source development, and youth entrepreneurship development |
| Endorsement | Consultations with Ethiopian and Somali government officials endorsed Tog-Wajaale as a key RMF location |

### 4.12.3 Project Scope

#### 4.12.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Skills Training Facilities | Vocational and technical training centre | 3,000,000 | 480,095,700 |
| Entrepreneurship Incubation Centre | Business incubation and support | 2,500,000 | 400,079,750 |
| Digital & Career Development Labs | Digital skills and career guidance | 2,000,000 | 320,063,800 |
| Job Placement & Migration Services | Employment and migration guidance | 1,500,000 | 240,047,850 |
| Business Support & Mentoring | Mentorship and business advisory | 1,000,000 | 160,031,900 |
| TOTAL |  | 10,000,000 | 1,600,319,000 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

#### 4.12.3.2 Component Details

1. Skills Training Facilities (USD 3,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Vocational Training | Market-aligned technical and vocational skills training | Construction; mechanics; ICT; hospitality; agriculture |
| Workshops | Practical training workshops for various trades | 10+ fully equipped workshops |
| Classrooms | Theory and classroom-based learning spaces | 20+ classrooms |
| Equipment | Training equipment and tools | Industry-standard equipment |
| Libraries | Learning and resource centres | Reference materials; digital resources |

Aligned with the TWUEP's Vocational Training Centre target of 5,000 trained per year by 2030.

Priority Training Sectors:

| Sector | Description | Labour Market Demand |
| --- | --- | --- |
| Construction | Building trades, infrastructure development | High (urban expansion, roads) |
| Logistics & Transport | Freight, customs, supply chain management | High (FTZ, corridor development) |
| ICT & Digital Skills | Digital literacy, IT support, programming | Growing (digital economy) |
| Hospitality & Tourism | Hotel, restaurant, travel services | Medium (service sector growth) |
| Agriculture & Agro-Processing | Farming, food processing, value addition | High (livestock, agricultural sector) |
| Renewable Energy | Solar installation, maintenance | Growing (energy transition) |

2. Entrepreneurship Incubation Centre (USD 2,500,000)

| Element | Description | Specification |
| --- | --- | --- |
| Incubation Spaces | Co-working and incubation spaces for startups | 30+ incubation workstations |
| Business Advisory | Business planning and advisory services | 5+ business advisors |
| Access to Finance | Linkages to microfinance and business loans | Financial institution partnerships |
| Networking | Business networking and mentorship opportunities | Industry connections |
| Legal Support | Legal and regulatory advisory | Business registration support |
| Digital Support | E-commerce and digital marketing support | Digital business development |

3. Digital & Career Development Labs (USD 2,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Digital Skills Training | ICT and digital literacy training | 50+ computers; software training |
| Career Counselling | Career guidance and counselling services | 3+ career counsellors |
| Job Readiness | CV writing, interview skills, job search support | Workshops and coaching |
| Online Learning | Access to online learning platforms | Subscription to leading platforms |
| Career Resources | Labour market information and resources | Career library and database |
| Soft Skills | Communication, teamwork, leadership training | Soft skills development programmes |

4. Job Placement & Migration Services (USD 1,500,000)

| Element | Description | Specification |
| --- | --- | --- |
| Job Placement | Linkages with employers and job matching | 500+ placements/year |
| Migration Information | Safe and legal migration information | IOM-aligned information |
| Skills Profiling | Skills assessment and profiling | Comprehensive assessment |
| Labour Market Information | Labour market intelligence | Regular market analysis |
| Employer Engagement | Employer outreach and partnerships | 100+ employer partnerships |
| Pre-Departure Orientation | Pre-departure orientation for migrants | Safe migration workshops |

5. Business Support & Mentoring (USD 1,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Mentorship Programme | Experienced business mentors | 30+ trained mentors |
| Business Development | Business development services | Business growth support |
| Market Linkages | Market access and linkages | 200+ business linkages/year |
| Post-Startup Support | Ongoing support for startups | 12-month post-incubation support |
| Peer Learning | Peer learning and networking | Business forums and events |
| Access to Finance | Linkages to financial institutions | Microfinance and loan linkages |

### 4.12.4 Value Creation

#### 4.12.4.1 Expected Outcomes

| Outcome | Target | Measurement |
| --- | --- | --- |
| Trained by 2030 | 5,000+/year (TWUEP target) | Training records |
| Youth Placed in Jobs | 1,000+ placements/year | Placement records |
| Businesses Incubated | 50+ businesses/year | Incubation records |
| Entrepreneurs Supported | 200+ entrepreneurs/year | Business support records |
| Migration Counselled | 1,000+ youth/year | Counselling records |
| Jobs Created | ~200 construction + placements | Employment records |

#### 4.12.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Reduced Irregular Migration | Safe alternatives through skills and employment |
| Economic Empowerment | Youth-led enterprises and job creation |
| Social Stability | Reduced desperation and social tensions |
| Skills Development | Market-aligned skills for employability |
| Regional Integration | Cross-border economic opportunities |
| FTZ Workforce | Skilled workforce for FTZ industries |
| Gender Empowerment | 40% target for women participants |
| Host Community Benefits | Benefits for displaced and host communities |

#### 4.12.4.3 Gender Impact

| Indicator | Target |
| --- | --- |
| Women Participants | 40%+ of all training participants |
| Women-Led Businesses | 30%+ of incubated businesses |
| Women in Leadership | 30%+ of leadership positions |
| Gender-Responsive Services | All services gender-sensitive |
| Safe Spaces | Dedicated safe spaces for women |
| Childcare Support | Childcare facilities for participants |

### 4.12.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | TWUEP names Vocational Training Centre a priority (5,000/yr by 2030); city is a key migration corridor; IGAD RMF and Cities Alliance programmes active | Formal skills-gap & migration needs assessment |
| Site / Land & Approvals | Gap | — | Site identification and titling |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & design |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 10M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | — | Social safeguard screening |
| Revenue, O&M & Delivery Model | Gap | — | O&M and programme financing plan |
| Procurement / Transaction Plan | Gap | — | Training provider & partner sounding |

#### 4.12.5.1 Bankability Strengths

| Strength | Description |
| --- | --- |
| Strong Policy Support | TWUEP prioritises vocational training (5,000/yr by 2030) |
| Existing Programmes | IGAD RMF, Cities Alliance, and IOM programmes active |
| Funding Pipeline | Germany €8 million grant for corridor development |
| Social Impact | High social impact and youth benefits |
| Strategic Location | Key migration corridor with high youth population |
| Partnership Potential | Strong potential for NGO and UN partnerships |

#### 4.12.5.2 Bankability Gaps

| Gap | Description | Required Action |
| --- | --- | --- |
| Skills Gap Assessment | No formal skills assessment | Conduct skills-gap and needs assessment |
| Migration Needs Assessment | No formal migration needs data | Conduct migration needs assessment |
| Site Identification | No site identified | Identify and secure site |
| Feasibility Study | No detailed analysis | Commission feasibility study |
| O&M Plan | No operations and maintenance plan | Develop O&M and financing plan |
| Partner Engagement | Limited partner sounding | Engage potential partners |

### 4.12.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | Public delivery with NGO/donor-funded programme partner |
| Operator & O&M | Municipal youth affairs office with contracted training provider |
| Revenue / Cost Recovery | Municipal budget + donor/grant programme funding |
| Funding Mix | Grant-funded capital + programme co-financing from development partners; municipal budget for facility O&M |

#### 4.12.6.1 Recommended Partnership Structure

text

┌─────────────────────────────────────────────────────────────┐

│ PROJECT OVERSIGHT │

│ Tog-Wajaale City Administration │

│ (Mayor's Office / City Manager) │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────────────┴────────────────────────────────────┐

│ PROJECT MANAGEMENT │

│ Municipal Youth Affairs Office │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────┼────────────────┐

│ │ │

▼ ▼ ▼

┌───────────────┐ ┌───────────────┐ ┌───────────────┐

│ TRAINING │ │ INCUBATION │ │ MIGRATION │

│ PROVIDER │ │ MANAGER │ │ SERVICES │

│ (Contractor) │ │ (Contractor/ │ │ (IOM/NGO) │

│ │ │ NGO) │ │ │

└───────────────┘ └───────────────┘ └───────────────┘

#### 4.12.6.2 Programme Partners

| Partner Type | Potential Partners | Role |
| --- | --- | --- |
| Training Provider | Vocational training institutions; Private trainers | Skills training delivery |
| Incubation Partner | Business incubators; Entrepreneurship support organisations | Business incubation |
| Migration Partner | IOM; UNHCR; Migration-focused NGOs | Migration services |
| Financial Partner | Microfinance institutions; Banks | Access to finance |
| Employer Partner | Private sector companies; FTZ | Job placement |
| Government Partner | Regional Youth Office; Ministry of Labour | Policy support |

### 4.12.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 03 (FTZ) | Skilled workforce for FTZ industries |
| With Priority 06 (Reception Centre) | Skills training for returnees |
| With IGAD RMF | Alignment with IGAD Regional Migration Fund programmes |
| With Cities Alliance EACC | Strategic framework for corridor development |
| With IOM MRC | Complement IOM Migration Response Centre services |
| With Urban Expansion | Youth housing and services in expansion areas |
| With Solid Waste | Employment opportunities in waste sector |

### 4.12.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| Programme funding sustainability beyond capital phase | Multi-year donor programme agreements; municipal budget line for O&M |
| Low uptake among target youth | Community outreach and kebele-level mobilisation; linkage to job placement outcomes |
| Coordination with migration service providers | Formal partnership with IOM/UNHCR-affiliated actors already active in the corridor |
| Skills mismatch with labour market | Market-aligned training; employer engagement; regular curriculum review |
| Limited employer linkages | Private sector engagement; job placement services |
| Gender disparities in participation | Targeted outreach; safe spaces for women; childcare support |
| Political interference in migration services | Clear guidelines; professional service delivery |
| Staff turnover | Competitive compensation; professional development opportunities |

### 4.12.9 Implementation Phasing

#### 4.12.9.1 Phase 1: Feasibility & Planning (2025-2026)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Skills-Gap & Needs Assessment | Months 1-4 | Consultant | 100,000 |
| Migration Needs Assessment | Months 2-5 | Consultant/IOM | 80,000 |
| Feasibility Study | Months 3-8 | Consultant | 120,000 |
| Programme Design | Months 4-9 | Project Team | 100,000 |
| Partner Engagement | Ongoing | Project Director | 50,000 |
| TOTAL |  |  | 450,000 |

#### 4.12.9.2 Phase 2: Construction (2026-2028)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Site Development | Months 1-6 | Contractor | 1,000,000 |
| Skills Training Facilities | Months 3-12 | Contractor | 3,000,000 |
| Incubation Centre | Months 6-15 | Contractor | 2,500,000 |
| Digital & Career Labs | Months 9-16 | Contractor | 2,000,000 |
| Migration Services Section | Months 12-18 | Contractor | 1,500,000 |
| TOTAL |  |  | 10,000,000 |

#### 4.12.9.3 Phase 3: Operationalization (2028-2029)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Staff Recruitment | Months 14-16 | HR Department | 100,000 |
| Partner Agreements | Months 14-18 | Project Director | - |
| Training Programme Launch | Month 18 | Training Provider | - |
| Incubation Centre Launch | Month 18 | Incubation Manager | - |
| Migration Services Launch | Month 18 | Migration Partner | - |
| Community Outreach | Ongoing | Engagement Team | 50,000 |
| TOTAL |  |  | 150,000 |

### 4.12.10 Next Steps

#### 4.12.10.1 Priority Action

Conduct a Youth Skills & Migration Needs Assessment

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / Urban Expansion Team |
| Estimated Cost | USD 100,000 - 150,000 |
| Expected Outcome | Evidence base for programme design and partner engagement |

#### 4.12.10.2 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Finalise needs assessment TOR | Week 1-3 | Project Director | Consultant procurement ready |
| Identify potential site for centre | Week 2-6 | Urban Expansion Team | Site shortlist |
| Engage IOM on partnership | Week 2-8 | Project Director | MOU for migration services |
| Engage IGAD on RMF alignment | Week 2-6 | City Manager | RMF programme alignment |
| Identify potential training providers | Week 4-10 | Project Director | Provider interest assessment |
| Engage youth groups | Week 2-12 | Engagement Team | Youth input and buy-in |
| Develop preliminary cost estimates | Week 8-12 | Infrastructure Specialist | Indicative project costs |

#### 4.12.10.3 Immediate Actions

| Action | Responsible | Timeline |
| --- | --- | --- |
| Identify and secure site for centre | Urban Expansion Team | 0-45 days |
| Engage IGAD RMF and Cities Alliance | City Manager | 0-30 days |
| Prepare needs assessment procurement | Project Director | 0-30 days |
| Contact IOM for partnership discussions | Project Director | 0-30 days |
| Consult youth stakeholders | Engagement Team | 0-60 days |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418

Project Website: www.twuep.com.et

## 4.13 PRIORITY 06: RECEPTION & REINTEGRATION CENTRE — DETAILED PROFILE

### 4.13.1 Project Overview

| Parameter | Details |
| --- | --- |
| Project Name | Tog-Wajaale Reception & Reintegration Centre |
| Description | A dedicated reception and reintegration centre providing dignified support, counselling and livelihood opportunities for migrants returning through Tog-Wajaale |
| Indicative Investment | USD 7,000,000 (Birr 1,120,223,300)* |
| Sector | Migration & Social Services |
| Project Owner | Tog-Wajaale City Administration (TWCA) |
| Current Readiness | Stage 1 of 5 (Concept) |
| Instrument Sought | Grant |
| Ranking Rationale | Social Protection - Addresses returnee needs; supports vulnerable population; complements other investments |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 4.13.2 Strategic Rationale

#### 4.13.2.1 The Challenge

As Ethiopia's busiest land crossing to Somaliland, Tog-Wajaale receives significant numbers of returning migrants with no dedicated reception facility. Returnees currently lack accommodation, psychosocial support or a structured pathway to reintegration.

| Issue | Description | Impact |
| --- | --- | --- |
| No Dedicated Reception Facility | Returnees currently lack accommodation, psychosocial support, or a structured pathway to reintegration | Returnees left vulnerable; no coordinated support |
| Significant Returnee Numbers | As Ethiopia's busiest land crossing to Somaliland, Tog-Wajaale receives significant numbers of returning migrants | Overwhelmed existing services; unmet needs |
| Vulnerable Returnees | Many returnees are in vulnerable conditions requiring immediate support | Protection risks; health and safety concerns |
| No Structured Reintegration | Absence of formal support for sustainable reintegration | Returnees may re-migrate irregularly; limited livelihood opportunities |

#### 4.13.2.2 Why This is Priority #6

| Reason | Description |
| --- | --- |
| Humanitarian Need | Addresses immediate needs of vulnerable returnees |
| Social Protection | Provides essential services to vulnerable population |
| Complementary | Complements Youth Centre and other investments |
| Existing Programmes | Leverages IOM MRC, IGAD RMF, and Cities Alliance |
| Reasonable Cost | USD 7 million investment with significant social impact |

#### 4.13.2.3 Tog-Wajaale as a Migration Corridor

Tog-Wajaale is a critical transit location for migrants from various parts of Ethiopia travelling to Middle East countries. It serves as a key node along the Eastern Migration Route, one of the busiest migration pathways in the region.

Key Migration Facts:

| Element | Description |
| --- | --- |
| Route | Eastern Migration Route to Middle East |
| Key Destination | Saudi Arabia (employment and remittances) |
| Transit Role | Primary land crossing between Ethiopia and Somaliland |
| Return Flow | Significant numbers of returnees pass through Tog-Wajaale |
| Vulnerability | Returnees often in vulnerable conditions |
| Protection Needs | Psychosocial support, accommodation, livelihood support |

#### 4.13.2.4 Existing Programmes and Partnerships

| Programme | Details | Relevance |
| --- | --- | --- |
| IOM Migration Response Centre (MRC) | Operates in Tog-Wajaale, providing protection and assistance to vulnerable migrants; includes awareness raising, protection assistance, and coordination | Existing infrastructure and expertise |
| Save the Children International (SCI) & OWDA | Implement protection-related activities including child protection, legal assistance, psychosocial support, shelter/NFI assistance, and family tracing and reunification | Protection services for vulnerable returnees |
| IGAD Regional Migration Fund (RMF) | Officially launched RMF project activities in Tog-Wajaale in May 2026; Germany signed an €8 million grant agreement to scale up the RMF | Foundation for migration-related investments |
| Cities Alliance Programme | Supports sustainable and inclusive urban growth in cities along migration corridors | Strategic framework for migration management |
| National Migration Policy | Adopted by the Government of Ethiopia, providing a framework for managing migration and protecting migrants' rights | Policy framework and support |

#### 4.13.2.5 IOM Migration Response Centre (MRC) Details

| Element | Details |
| --- | --- |
| Location | Tog-Wajaale |
| Purpose | Protection and assistance to vulnerable migrants |
| Services | Awareness raising; protection assistance; coordination |
| Partner Implementation | SCI and OWDA implement protection activities |
| Protection Services | Child protection; legal assistance; psychosocial support; shelter/NFI assistance; family tracing and reunification |
| Coordination | Regional and national actors engagement |

#### 4.13.2.6 IGAD Regional Migration Fund (RMF) Details

| Element | Details |
| --- | --- |
| Purpose | Create economic opportunities and improve living conditions of migrants, refugees, and host communities |
| Approved Projects | Upgrading livestock market center, construction of two Community Development Centers, new vegetable market |
| Funding | Germany €8 million grant to scale up RMF |
| Focus Corridors | Key corridors including Togwajale (Ethiopia–Somaliland) |
| Investment Planning | Missions conducted identifying thematic areas including livestock, agriculture, water source development, and youth entrepreneurship development |
| Endorsement | Consultations with Ethiopian and Somali government officials endorsed Tog-Wajaale as a key RMF location |

#### 4.13.2.7 National and Regional Policy Context

| Element | Details |
| --- | --- |
| National Migration Policy | Adopted by the Government of Ethiopia, providing a framework for managing migration and protecting migrants' rights |
| Safe Migration | Recognizes the importance of safe, orderly, and regular migration |
| Protection of Migrants' Rights | Emphasizes protection of migrants' rights |
| Sustainable Reintegration | Recognizes the importance of sustainable reintegration of returnees |
| Somali Regional State | Actively involved in migration management, serving as a member of the IGAD RMF National Steering Committee |
| Collaboration | Commitment to managing the challenges and opportunities of migration and displacement |

### 4.13.3 Project Scope

#### 4.13.3.1 Components Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Reception & Accommodation Facilities | Welcome centre and temporary accommodation | 2,000,000 | 320,063,800 |
| Counselling & Psychosocial Support | Mental health and psychosocial services | 1,500,000 | 240,047,850 |
| Skills Training & Livelihood Programmes | Vocational training and livelihood support | 1,500,000 | 240,047,850 |
| Reintegration Grants & Business Support | Grants and business development support | 1,000,000 | 160,031,900 |
| Monitoring, Follow-up & Case Management | Ongoing support and case management | 1,000,000 | 160,031,900 |
| TOTAL |  | 7,000,000 | 1,120,223,300 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

#### 4.13.3.2 Component Details

1. Reception & Accommodation Facilities (USD 2,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Reception Centre | Welcoming and registration of returnees | Intake and assessment area |
| Temporary Accommodation | Short-term housing for returnees | 50+ beds capacity |
| Basic Amenities | Water, sanitation, hygiene facilities | WASH facilities |
| Medical Check-up | Basic health screening and first aid | Medical examination room |
| Nutrition Support | Food and nutrition assistance | Kitchen and dining area |
| Recreation | Recreational and social spaces | Common areas |

2. Counselling & Psychosocial Support (USD 1,500,000)

| Element | Description | Specification |
| --- | --- | --- |
| Individual Counselling | One-on-one counselling sessions | 5+ counsellors |
| Group Counselling | Group therapy and support groups | Group spaces |
| Psychosocial Support | Mental health and psychosocial support | MHPSS programming |
| Trauma Support | Trauma-informed care and support | Trauma specialists |
| Crisis Intervention | Emergency support for crisis situations | 24/7 support |
| Referral System | Referral to specialised services | Referral pathways |

3. Skills Training & Livelihood Programmes (USD 1,500,000)

| Element | Description | Specification |
| --- | --- | --- |
| Vocational Training | Market-aligned skills training | Construction; agriculture; trades |
| Livelihood Support | Support for income-generating activities | 200+ returnees/year |
| Agriculture Support | Agricultural skills and inputs | Farming and livestock |
| Digital Skills | Digital literacy and ICT training | Basic ICT skills |
| Business Skills | Basic business and financial literacy | Entrepreneurial skills |
| Life Skills | Life skills and resilience training | Essential life skills |

4. Reintegration Grants & Business Support (USD 1,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Reintegration Grants | Financial support for reintegration | 200+ grants/year |
| Business Support | Business planning and advisory services | Business mentors |
| Access to Finance | Linkages to microfinance and business loans | Financial institution partnerships |
| Market Linkages | Market access and linkages | Market connections |
| Startup Kits | Equipment and materials for startups | 100+ startup kits/year |
| Business Mentoring | Ongoing business mentoring | 12-month mentoring programme |

5. Monitoring, Follow-up & Case Management (USD 1,000,000)

| Element | Description | Specification |
| --- | --- | --- |
| Case Management | Personalized support and case management | 5+ case managers |
| Follow-up | Ongoing monitoring and follow-up | 12-month follow-up |
| Documentation | Proper documentation and reporting | Electronic case management system |
| Referral Pathways | Linkages to other service providers | Comprehensive referral system |
| Outcome Monitoring | Monitoring of reintegration outcomes | Outcome tracking |
| Impact Evaluation | Impact assessment of interventions | Regular evaluations |

### 4.13.4 Value Creation

#### 4.13.4.1 Expected Outcomes

| Outcome | Target | Measurement |
| --- | --- | --- |
| Returnees Served / Year | Pending assessment | Registration records |
| Successfully Reintegrated | 80%+ successful reintegration | Follow-up surveys |
| Livelihood Support | 500+ returnees supported | Programme records |
| Psychosocial Support | All returnees receive support | Service records |
| Jobs Created | ~100 construction + case management | Employment records |
| Beneficiaries | Returnees, women & youth | Beneficiary tracking |

#### 4.13.4.2 Additional Benefits

| Benefit | Description |
| --- | --- |
| Dignified Reception | Dignified and respectful reception for returnees |
| Trauma Support | Psychological and emotional support for traumatised returnees |
| Sustainable Reintegration | Livelihood opportunities for sustainable reintegration |
| Community Acceptance | Improved community acceptance of returnees |
| Reduced Irregular Migration | Addressing root causes through livelihood support |
| Social Cohesion | Strengthened social cohesion and stability |
| Protection | Protection for vulnerable returnees |
| Family Reunification | Support for family reunification |

#### 4.13.4.3 Protection Impact

| Indicator | Target |
| --- | --- |
| Child Protection | All child returnees receive protection support |
| Women's Protection | All women returnees receive targeted support |
| Psychosocial Support | All returnees receive psychosocial support |
| Legal Assistance | Legal support for returnees in need |
| Shelter/NFI Assistance | Shelter and non-food items for returnees in need |
| Family Tracing | Family tracing and reunification support |

### 4.13.5 Readiness & Bankability

| Requirement | Status | Evidence Available | Remaining Gap / Next Step |
| --- | --- | --- | --- |
| Demand & Strategic Fit | In progress | Cities Alliance Cities & Migration Programme active in Tog-Wajaale; city is a key return corridor; IOM MRC operating; IGAD RMF active | Formal returnee flow and needs assessment |
| Site / Land & Approvals | Gap | — | Site identification and titling |
| Feasibility & Technical Design | Gap | — | Full engineering feasibility & design |
| Cost Estimate / BOQ | In progress | Indicative capital cost (USD 7M) | Detailed BOQ from design consultant |
| Environmental, Social & Climate Screening | Gap | — | Social safeguard screening |
| Revenue, O&M & Delivery Model | Gap | — | O&M and case-management financing plan |
| Procurement / Transaction Plan | Gap | — | Implementing partner sounding |

#### 4.13.5.1 Bankability Strengths

| Strength | Description |
| --- | --- |
| Strong Humanitarian Need | Clear justification based on returnee flows |
| Existing Programmes | IOM MRC, IGAD RMF, and Cities Alliance programmes active |
| Policy Support | National Migration Policy framework |
| Protection Framework | Strong protection rationale |
| Partnership Potential | Strong potential for UN and NGO partnerships |
| Complementary | Complements other investments in the portfolio |

#### 4.13.5.2 Bankability Gaps

| Gap | Description | Required Action |
| --- | --- | --- |
| Returnee Flow Data | No formal returnee flow data | Conduct returnee flow and needs assessment |
| Site Identification | No site identified | Identify and secure site |
| Feasibility Study | No detailed analysis | Commission feasibility study |
| O&M Plan | No operations and maintenance plan | Develop O&M and financing plan |
| Partner Engagement | Limited partner sounding | Engage potential partners |

### 4.13.6 Delivery & Operating Model

| Element | Details |
| --- | --- |
| Project Owner / Lead | Tog-Wajaale City Administration (TWCA) |
| Delivery Structure | Public delivery with NGO/donor-funded programme partner |
| Operator & O&M | Municipal social affairs office with contracted implementing partner |
| Revenue / Cost Recovery | Municipal budget + donor/grant programme funding |
| Funding Mix | Grant-funded capital + programme co-financing from migration-focused partners; municipal budget for facility O&M |

#### 4.13.6.1 Recommended Partnership Structure

text

┌─────────────────────────────────────────────────────────────┐

│ PROJECT OVERSIGHT │

│ Tog-Wajaale City Administration │

│ (Mayor's Office / City Manager) │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────────────┴────────────────────────────────────┐

│ PROJECT MANAGEMENT │

│ Municipal Social Affairs Office │

└────────────────────────┬────────────────────────────────────┘

│

┌────────────────┼────────────────┐

│ │ │

▼ ▼ ▼

┌───────────────┐ ┌───────────────┐ ┌───────────────┐

│ RECEPTION │ │ PSYCHOSOCIAL│ │ LIVELIHOOD │

│ SERVICES │ │ SERVICES │ │ PROGRAMMES │

│ (IOM/NGO) │ │ (IOM/NGO) │ │ (NGO/Partner)│

└───────────────┘ └───────────────┘ └───────────────┘

#### 4.13.6.2 Programme Partners

| Partner Type | Potential Partners | Role |
| --- | --- | --- |
| Migration Partner | IOM; UNHCR; Migration-focused NGOs | Reception and protection services |
| Psychosocial Partner | Mental health organisations; NGOs | Psychosocial support |
| Training Provider | Vocational training institutions | Skills training |
| Livelihood Partner | NGOs; Microfinance institutions | Livelihood support |
| Protection Partner | SCI; OWDA; Child protection NGOs | Protection services |
| Government Partner | Regional Social Affairs Office; Ministry of Labour | Policy support |

### 4.13.7 Key Synergies

| Synergy | Description |
| --- | --- |
| With Priority 05 (Youth Centre) | Skills training for returnees |
| With Priority 01 (Urban Expansion) | Housing and services for returnees |
| With Priority 03 (FTZ) | Employment opportunities for returnees |
| With IGAD RMF | Alignment with IGAD Regional Migration Fund programmes |
| With IOM MRC | Complement IOM Migration Response Centre services |
| With Cities Alliance EACC | Strategic framework for migration management |
| With National Migration Policy | Policy framework implementation |

### 4.13.8 Top Risks & Mitigation

| Critical Risk | Mitigation / Responsible Party |
| --- | --- |
| Fluctuating returnee volumes affecting planning | Flexible facility design; phased capacity scaling |
| Programme funding sustainability beyond capital phase | Multi-year donor agreements; municipal budget line for O&M |
| Coordination across humanitarian & development actors | Formal MOU with IOM/UNHCR-affiliated actors and Cities Alliance programme |
| Community acceptance of returnees | Community engagement and awareness programmes; benefit-sharing |
| Returnee protection concerns | Safeguarding protocols; protection-focused programming |
| Staff capacity and turnover | Competitive compensation; training; professional development |
| Political sensitivity of migration | Clear guidelines; professional service delivery; policy alignment |

### 4.13.9 Implementation Phasing

#### 4.13.9.1 Phase 1: Feasibility & Planning (2025-2026)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Returnee Flow & Needs Assessment | Months 1-4 | Consultant/IOM | 80,000 |
| Feasibility Study | Months 3-8 | Consultant | 120,000 |
| Programme Design | Months 4-9 | Project Team | 100,000 |
| Partner Engagement | Ongoing | Project Director | 50,000 |
| Social Safeguard Screening | Months 2-5 | Social Development Specialist | 60,000 |
| TOTAL |  |  | 410,000 |

#### 4.13.9.2 Phase 2: Construction (2026-2028)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Site Development | Months 1-6 | Contractor | 500,000 |
| Reception & Accommodation Facilities | Months 3-12 | Contractor | 2,000,000 |
| Counselling & Psychosocial Facilities | Months 6-12 | Contractor | 1,500,000 |
| Skills Training & Livelihood Facilities | Months 9-15 | Contractor | 1,500,000 |
| Administration & Case Management Facilities | Months 12-18 | Contractor | 1,000,000 |
| TOTAL |  |  | 6,500,000 |

#### 4.13.9.3 Phase 3: Operationalization (2028-2029)

| Activity | Timeline | Responsible | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Staff Recruitment | Months 14-16 | HR Department | 80,000 |
| Partner Agreements | Months 14-18 | Project Director | - |
| Programme Launch | Month 18 | Implementing Partner | - |
| Returnee Intake Commencement | Month 18+ | Operator | - |
| Community Awareness Campaign | Months 12-18 | Engagement Team | 50,000 |
| TOTAL |  |  | 130,000 |

### 4.13.10 Next Steps

#### 4.13.10.1 Priority Action

Conduct a Returnee Flow & Needs Assessment

| Element | Details |
| --- | --- |
| Timeline | 0-6 months |
| Responsible | Project Director / Urban Expansion Team |
| Estimated Cost | USD 80,000 - 120,000 |
| Expected Outcome | Evidence base for programme design and partner engagement |

#### 4.13.10.2 Key Activities for Next 90 Days

| Activity | Timeline | Responsible | Expected Outcome |
| --- | --- | --- | --- |
| Finalise returnee flow assessment TOR | Week 1-3 | Project Director | Consultant procurement ready |
| Identify potential site for centre | Week 2-6 | Urban Expansion Team | Site shortlist |
| Engage IOM on partnership and coordination | Week 2-8 | Project Director | MOU for services |
| Engage IGAD on RMF alignment | Week 2-6 | City Manager | RMF programme alignment |
| Contact SCI and OWDA for protection partnership | Week 2-8 | Project Director | Partner interest assessment |
| Engage community on the project | Week 4-12 | Engagement Team | Community acceptance |
| Develop preliminary cost estimates | Week 8-12 | Infrastructure Specialist | Indicative project costs |

#### 4.13.10.3 Immediate Actions

| Action | Responsible | Timeline |
| --- | --- | --- |
| Identify and secure site for centre | Urban Expansion Team | 0-45 days |
| Engage IOM for partnership discussions | Project Director | 0-30 days |
| Engage IGAD RMF and Cities Alliance | City Manager | 0-30 days |
| Prepare returnee flow assessment procurement | Project Director | 0-30 days |
| Consult community stakeholders | Engagement Team | 0-60 days |

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Contact:
Mahamud Yusuf Adan – Mayor: +251 915 330528
Abdikarim Hassen Yusuf – City Manager: +251 915 074535
Shemshedin Hassen Yusuf – Project Director: +251 911 542418

Project Website: www.twuep.com.et

# CHAPTER FIVE: INVESTMENT REQUIREMENTS AND FINANCIAL ANALYSIS

## 5.1 TOTAL PORTFOLIO COST ESTIMATE

### 5.1.1 Portfolio Investment Summary

| Priority | Project | Investment (USD) | Investment (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| 01 | Planned Urban Expansion Programme | 63,000,000 | 10,082,009,700 | 16.6% |
| 02 | Corridor & Arterial Road Upgrade | 40,000,000 | 6,401,276,000 | 10.5% |
| 03 | Inland Special Trade Zone & Logistics Hub | 250,000,000 | 40,007,975,000 | 65.8% |
| 04 | Solid Waste Management System | 10,000,000 | 1,600,319,000 | 2.6% |
| 05 | Youth Skills, Enterprise & Migration Centre | 10,000,000 | 1,600,319,000 | 2.6% |
| 06 | Reception & Reintegration Centre | 7,000,000 | 1,120,223,300 | 1.9% |
| TOTAL |  | 380,000,000 | 60,812,122,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 5.1.2 Investment by Classification

| Classification | Projects | Investment (USD) | Investment (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| Foundation | Priority 01 | 63,000,000 | 10,082,009,700 | 16.6% |
| Connectivity | Priority 02 | 40,000,000 | 6,401,276,000 | 10.5% |
| Economic Engine | Priority 03 | 250,000,000 | 40,007,975,000 | 65.8% |
| Livability | Priority 04 | 10,000,000 | 1,600,319,000 | 2.6% |
| Human Capital | Priority 05 | 10,000,000 | 1,600,319,000 | 2.6% |
| Social Protection | Priority 06 | 7,000,000 | 1,120,223,300 | 1.9% |
| TOTAL |  | 380,000,000 | 60,812,122,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 5.2 FINANCING REQUIREMENTS

### 5.2.1 Total Capital Requirement

| Parameter | Details |
| --- | --- |
| Total Portfolio Cost | USD 380,000,000 / Birr 60,812,122,000 |
| Capital Sought | USD 380,000,000 (full portfolio capitalization) |
| Financing Instruments | Blended Finance (Grants, Concessional Loans, Private Investment, PPP) |
| Expected Funding Mix | To be determined through feasibility studies and financier engagement |
| Implementation Period | 2025-2035 (phased over 10 years) |

### 5.2.2 Financing Needs by Project

| Priority | Project | Total Cost (USD) | Financing Gap (USD) | Preferred Instrument |
| --- | --- | --- | --- | --- |
| 01 | Urban Expansion | 63,000,000 | 63,000,000 | Blended: grant + concessional loan + PPP |
| 02 | Corridor Roads | 40,000,000 | 40,000,000 | Concessional loan / grant |
| 03 | FTZ & Logistics | 250,000,000 | 250,000,000 | PPP / Concession |
| 04 | Solid Waste | 10,000,000 | 10,000,000 | Grant / concessional loan |
| 05 | Youth Centre | 10,000,000 | 10,000,000 | Grant |
| 06 | Reception Centre | 7,000,000 | 7,000,000 | Grant |
| TOTAL |  | 380,000,000 | 380,000,000 |  |

## 5.3 MUNICIPAL REVENUE CONTEXT

### 5.3.1 Municipal Budget

| Fiscal Year | Municipal Revenue (Birr) | Municipal Revenue (USD)* |
| --- | --- | --- |
| FY 2018 E.C. (2025-26 G.C.) | 144,000,000 | 899,821 |
| FY 2019 E.C. (2026-27 G.C.) | 195,000,000 | 1,218,507 |

Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 5.3.2 Key Observations

| Observation | Description |
| --- | --- |
| Limited Municipal Capacity | Municipal revenue represents a small fraction of the total portfolio cost (approximately 1.1-1.5% of USD 380 million) |
| Growing Revenue | Municipal revenue is increasing year-on-year, reflecting economic growth |
| Municipal Contribution | Limited to coordination, land acquisition, regulatory approvals, community engagement, and technical support |
| O&M Contribution | Municipal may need to support O&M subsidies for some projects |

## 5.4 POTENTIAL REVENUE SOURCES

### 5.4.1 Revenue Sources by Project

| Project | Revenue Source | Suitability |
| --- | --- | --- |
| Priority 01: Urban Expansion | Land lease and readjustment proceeds; municipal budget | High |
| Priority 02: Corridor Roads | Municipal budget; road-user fees (longer term) | Medium |
| Priority 03: FTZ & Logistics | Land lease, service charges, tenant fees, customs revenue | High |
| Priority 04: Solid Waste | Municipal waste levy; municipal budget | Medium |
| Priority 05: Youth Centre | N/A - grant-funded; municipal budget for O&M | Low |
| Priority 06: Reception Centre | N/A - grant-funded; municipal budget for O&M | Low |

### 5.4.2 Portfolio Revenue Potential

| Revenue Source | Description | Estimated Annual Revenue (USD) |
| --- | --- | --- |
| FTZ Land Leases | Lease payments for industrial/commercial plots | 5,000,000 |
| FTZ Service Charges | Management and service fees | 2,000,000 |
| FTZ Customs Revenue | Import/export duties (government share) | 10,000,000 |
| FTZ Tax Revenue | Corporate and income tax (government share) | 15,000,000 |
| Urban Expansion Land Leases | Land lease and readjustment proceeds | 2,000,000 |
| Solid Waste Levy | Monthly fee on households | 1,000,000 |
| TOTAL |  | 35,000,000 |

## 5.5 FINANCIAL MODEL FRAMEWORK

### 5.5.1 Key Financial Parameters

| Parameter | Assumption (To be validated) |
| --- | --- |
| Portfolio Cost | USD 380.0 million / Birr 60.8 billion |
| Project IRR | 12-15% (economic); 8-12% (financial) |
| Equity IRR | 15-20% |
| Debt/Equity Ratio | 70:30 to 80:20 |
| Discount Rate | 8-12% |
| Concession Period | 20-25 years (for PPP projects) |
| Revenue Growth | 3-5% per year |
| O&M Cost Growth | 2-4% per year |

### 5.5.2 Financial Model Components

| Component | Description |
| --- | --- |
| Capital Expenditure | Phased construction costs, contingencies |
| Operating Expenditure | O&M costs for all projects |
| Revenue | FTZ revenue, land leases, waste levy |
| Debt Service | Principal and interest payments |
| Returns | Equity IRR, project IRR |
| Sensitivity Analysis | Key variables (costs, revenue, interest rates) |

## 5.6 COST-BENEFIT ANALYSIS

### 5.6.1 Economic Benefits

| Benefit Category | Description | Estimated Value |
| --- | --- | --- |
| Travel Time Savings | Reduced commute times | To be quantified |
| Vehicle Operating Cost Savings | Reduced fuel and maintenance | To be quantified |
| Logistics Cost Reduction | ~30% along Ethio-Berbera corridor | Significant |
| Trade Volume Increase | USD 500 million+ annually | Significant |
| Job Creation | ~7,000+ direct and indirect jobs | Significant |
| Investment Attraction | USD 380 million+ | Significant |
| Environmental Benefits | Reduced emissions, improved waste management | Significant |
| Health Benefits | Improved public health through waste management | Significant |

### 5.6.2 Economic Viability

| Indicator | Estimated Value |
| --- | --- |
| Net Present Value (NPV) | Positive |
| Economic Internal Rate of Return (EIRR) | >12% |
| Benefit-Cost Ratio | >1.5 |

These parameters will be validated during feasibility studies.

# CHAPTER SIX: READINESS ASSESSMENT AND BANKABILITY ANALYSIS

## 6.1 CURRENT READINESS STAGE

| Stage | Description | Status |
| --- | --- | --- |
| 1 | Concept - Problem, beneficiaries, strategic alignment and preliminary scope are defined | ✓ All Projects |
| 2 | Pre-Feasibility - Options, initial demand, site, indicative cost and delivery choices have been assessed | ⚠ Partial |
| 3 | Feasibility & Approvals - Feasibility, land/site status, key approvals, safeguards and financial or O&M logic are substantially evidenced | ❌ Not Yet |
| 4 | Design/Procurement Ready - Designs, cost estimates/BOQ, procurement or transaction documents are prepared | ❌ Not Yet |
| 5 | Transaction Ready - Financing and delivery structure are agreed, due-diligence evidence is available | ❌ Not Yet |

## 6.2 STRENGTHS AND OPPORTUNITIES

### 6.2.1 Strengths

| Strength | Description |
| --- | --- |
| Strategic Alignment | All projects are integral components of the approved Tog-Wajaale Urban Expansion Plan (2025-2055) |
| Evidence-Based Foundation | Built upon robust data from TWUEP, including population projections, road network analysis, and demographic trends |
| Clear Economic Rationale | Direct link to Ethio-Berbera corridor with potential to reduce logistics costs by ~30% |
| Strong Policy Support | National, regional, and local legal frameworks; international commitments like SDGs |
| Municipal Commitment | Strong ownership demonstrated through TWUEP development and EACC participation |
| Regional Significance | Enhances Ethiopia-Somaliland cooperation and regional trade integration |
| Existing Partnerships | IGAD RMF, IOM MRC, Cities Alliance, TradeMark Africa programmes active |

### 6.2.2 Opportunities

| Opportunity | Description |
| --- | --- |
| International Development Finance | SDG alignment makes projects eligible for various international development finance instruments |
| Private Sector Investment | FTZ offers revenue-generating potential attractive to private investors |
| Regional Integration | Projects can serve as catalyst for strengthened Ethiopia-Somaliland economic cooperation |
| Climate Finance | Sustainability features (NMT, waste management, green spaces) make projects eligible for climate finance |
| Knowledge Transfer | Engagement with international partners can build local capacity |

## 6.3 WEAKNESSES AND GAPS

### 6.3.1 Weaknesses

| Weakness | Description |
| --- | --- |
| Feasibility Study Gap | Projects currently lack comprehensive feasibility studies |
| Environmental Assessment Pending | Project-specific EIAs not yet completed |
| Financial Model Undefined | Detailed financial models with clear funding mix and revenue streams not developed |
| Capacity Constraints | Municipality's technical and financial capacity may be limited |
| Land Acquisition Risk | Significant land acquisition may be required, which could face resistance |
| PPP Framework | Formal PPP frameworks and procurement strategies not yet in place |

### 6.3.2 Gaps

| Gap | Criticality | Action Required | Timeline |
| --- | --- | --- | --- |
| Feasibility Study | Critical | Commission comprehensive feasibility studies | 9 months |
| Environmental Assessment | Critical | Commission project-specific EIAs | 6 months |
| Financial Model | Critical | Develop detailed financial models | 6 months |
| Detailed Design | High | Complete engineering designs | 12 months |
| PPP Framework | High | Develop PPP frameworks and procurement strategies | 6 months |
| Risk Assessment | High | Complete comprehensive risk matrices | 3 months |

## 6.4 BANKABILITY ASSESSMENT

### 6.4.1 Bankability Assessment Matrix

| Bankability Factor | Priority 01 | Priority 02 | Priority 03 | Priority 04 | Priority 05 | Priority 06 |
| --- | --- | --- | --- | --- | --- | --- |
| Strategic Fit | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong |
| Policy/Regulatory Support | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong |
| Economic Justification | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong |
| Technical Feasibility | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial |
| Environmental Assessment | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing |
| Financial Model | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing | ✗ Missing |
| Risk Assessment | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial |
| Implementation Plan | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial | ⚠ Partial |
| Project Ownership | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong |
| Sponsor Commitment | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong | ✓ Strong |

Overall Readiness: Stage 2 (Pre-Feasibility) - All projects require significant development of technical, financial, and environmental documentation to achieve bankability.

## 6.5 GAP ANALYSIS AND REQUIREMENTS FOR BANKABILITY

### 6.5.1 Immediate Requirements

| Requirement | Description | Responsible |
| --- | --- | --- |
| Feasibility Studies | Comprehensive feasibility studies for all six projects | Project Director / Consultant |
| Environmental Impact Assessments | Project-specific EIAs for all projects | Environmental Consultant |
| Financial Models | Detailed financial models for all projects | Financial Consultant |

### 6.5.2 Medium-Term Requirements

| Requirement | Description | Responsible |
| --- | --- | --- |
| Detailed Designs | Engineering designs and specifications | Design Consultant |
| PPP Frameworks | PPP frameworks and procurement strategies | PPP Advisor |
| Risk Assessments | Comprehensive risk assessments | Risk Consultant |
| Implementation Plans | Detailed implementation plans | Project Director |

### 6.5.3 Long-Term Requirements

| Requirement | Description | Responsible |
| --- | --- | --- |
| Financing Commitments | Secured financing commitments from financiers | Mayor's Office / City Manager |
| PPP Transactions | PPP procurement and contract awards | PPP Advisor |
| Construction | Project construction and commissioning | Contractor |

# CHAPTER SEVEN: RISK ASSESSMENT AND MITIGATION STRATEGIES

## 7.1 RISK MANAGEMENT FRAMEWORK

### 7.1.1 Risk Management Process

| Step | Description |
| --- | --- |
| Risk Identification | Systematic identification of potential risks |
| Risk Analysis | Assessment of probability and impact of each risk |
| Risk Evaluation | Prioritization of risks based on significance |
| Risk Treatment | Development of mitigation strategies |
| Risk Monitoring | Ongoing monitoring and review of risks |

### 7.1.2 Risk Categories

| Category | Description |
| --- | --- |
| Political and Regulatory Risks | Risks related to political stability and regulatory environment |
| Financial Risks | Risks related to financing, costs, and revenue |
| Technical and Operational Risks | Risks related to construction, design, and operations |
| Environmental Risks | Risks related to environmental impacts and climate |
| Social and Community Risks | Risks related to community acceptance and social impacts |
| Institutional and Capacity Risks | Risks related to institutional capacity and governance |

## 7.2 POLITICAL AND REGULATORY RISKS

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Political instability in border region | Medium | High | Strong bilateral framework; diplomatic engagement |
| Regulatory changes affecting FTZ | Medium | High | Secure long-term regulatory guarantees |
| Land acquisition disputes | High | Medium | Transparent compensation; community engagement; legal due diligence |
| Border tensions | Low-Medium | High | Maintain diplomatic engagement; joint committee with Somaliland |

## 7.3 FINANCIAL RISKS

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Cost overruns | Medium | High | Detailed cost estimates; contingency provisions; phased implementation |
| Revenue shortfall | Medium | High | Conservative forecasts; diversified revenue streams; government guarantees |
| Currency fluctuation | High | Medium | Currency hedging; indexation mechanisms |
| Investor demand | Medium | High | Anchor tenant pre-agreements; market sounding study |

## 7.4 TECHNICAL AND OPERATIONAL RISKS

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Construction delays | Medium | Medium | Realistic timelines; experienced contractors; phased implementation |
| Design flaws | Low | High | International standards; comprehensive design review |
| Maintenance shortfall | Medium | High | O&M contracts; maintenance reserve fund; performance monitoring |
| Operational efficiency | Medium | Medium | Performance-based contracts; operator incentives |

## 7.5 ENVIRONMENTAL RISKS

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Flood damage | Medium | High | Flood-resistant design; climate-resilient infrastructure |
| Environmental impacts | Medium | Medium | Comprehensive EIA; environmental management plan |
| Climate change | High | High | Climate-resilient design; adaptation measures |

## 7.6 SOCIAL AND COMMUNITY RISKS

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Community opposition | Medium | Medium | Participatory planning; benefit-sharing; transparent communication |
| Displacement | Medium | High | Comprehensive resettlement plan; fair compensation |
| Safety concerns | Medium | Medium | Safety features in design; awareness campaigns |

## 7.7 INSTITUTIONAL AND CAPACITY RISKS

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Limited municipal capacity | Medium | Medium | Technical assistance; training; experienced partners |
| Coordination challenges | Medium | Medium | Clear roles; coordination mechanisms |
| Staff turnover | Medium | Low | Knowledge management; succession planning |

## 7.8 RISK ALLOCATION IN PPP STRUCTURE

| Risk Category | Public Sector | Private Sector | Shared |
| --- | --- | --- | --- |
| Political/Regulatory | ✓ |  |  |
| Land Acquisition | ✓ |  |  |
| Environmental Approvals | ✓ |  |  |
| Construction Risk |  | ✓ |  |
| Design Risk |  | ✓ |  |
| Financing Risk |  | ✓ |  |
| Market/Demand Risk |  | ✓ |  |
| Currency Risk |  |  | ✓ |
| Inflation Risk |  |  | ✓ |
| Operational Risk |  | ✓ |  |
| Force Majeure |  |  | ✓ |

# CHAPTER EIGHT: FINANCING AND PARTNERSHIP STRUCTURE

## 8.1 RECOMMENDED DELIVERY MODEL

### 8.1.1 By Project

| Project | Recommended Delivery Model | Rationale |
| --- | --- | --- |
| Priority 01: Urban Expansion | Public delivery with PPP components | Public sector planning; private sector for serviced plots |
| Priority 02: Corridor Roads | Public delivery | Municipal capital works programme |
| Priority 03: FTZ & Logistics | PPP / Concession | Private sector efficiency; investment attraction |
| Priority 04: Solid Waste | Public delivery | Municipal service; potential private O&M |
| Priority 05: Youth Centre | Public delivery with NGO partner | Social service; grant funding |
| Priority 06: Reception Centre | Public delivery with NGO partner | Social service; grant funding |

### 8.1.2 PPP Structure for FTZ (Priority 03)

| Element | Details |
| --- | --- |
| Model | Design-Build-Finance-Operate-Maintain (DBFOM) Concession |
| Concession Period | 20-25 years |
| Private Partner Role | Design, construction, financing, operation, maintenance, revenue collection |
| Public Sector Role | Policy oversight, regulation, land acquisition, environmental approvals, fare regulation |

## 8.2 RECOMMENDED FINANCING STRUCTURE

### 8.2.1 Portfolio Financing Structure

| Financing Source | Amount (USD) | Amount (Birr)* | Percentage |
| --- | --- | --- | --- |
| Development Finance Institutions | 150,000,000 | 24,004,785,000 | 39.5% |
| Private Sector Investment | 120,000,000 | 19,203,828,000 | 31.6% |
| Government (National/Regional) | 80,000,000 | 12,802,552,000 | 21.0% |
| Municipal Government | 30,000,000 | 4,800,957,000 | 7.9% |
| TOTAL | 380,000,000 | 60,812,122,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

### 8.2.2 Financing Instruments by Project

| Project | Recommended Instruments |
| --- | --- |
| Priority 01: Urban Expansion | Blended: grant + concessional loan + PPP |
| Priority 02: Corridor Roads | Concessional loan / grant; Public capital budget |
| Priority 03: FTZ & Logistics | PPP / Concession; Private equity/debt |
| Priority 04: Solid Waste | Grant / concessional loan; Municipal budget |
| Priority 05: Youth Centre | Grant; Programme co-financing |
| Priority 06: Reception Centre | Grant; Programme co-financing |

## 8.3 POTENTIAL PARTNERS

### 8.3.1 Financiers

| Institution | Rationale | Relevant Projects |
| --- | --- | --- |
| African Development Bank (AfDB) | Infrastructure focus; regional integration | All projects |
| World Bank Group (IFC) | PPP expertise; private sector engagement | Priority 03; All |
| Swiss Agency for Development (SDC) | Existing dialogue support | All projects |
| European DFIs (DEG, FMO, Proparco) | Climate finance; sustainable infrastructure | Priority 03; Priority 04 |
| European Union | Regional integration; infrastructure | Priority 02; Priority 03 |
| IGAD | Regional Migration Fund | Priority 05; Priority 06 |
| TradeMark Africa | Border infrastructure; trade facilitation | Priority 02; Priority 03 |
| IOM | Migration support; protection | Priority 05; Priority 06 |
| Cities Alliance | Urban expansion planning | Priority 01; All |

### 8.3.2 Private Sector Operators

| Partner Type | Rationale | Relevant Projects |
| --- | --- | --- |
| FTZ Operators | Global FTZ experience | Priority 03 |
| Logistics Companies | Logistics and warehousing expertise | Priority 03 |
| Transport Operators | BRT operation; fleet management | Priority 02 |
| Infrastructure Developers | Design and construction expertise | Priority 01; Priority 02; Priority 03 |
| Technology Providers | ITS; systems integration | Priority 02; Priority 03 |

### 8.3.3 Implementing Partners

| Partner Type | Rationale | Relevant Projects |
| --- | --- | --- |
| IOM | Migration expertise; MRC operations | Priority 05; Priority 06 |
| UNHCR | Refugee and returnee support | Priority 06 |
| NGOs | Community engagement; social services | Priority 05; Priority 06 |
| Save the Children (SCI) | Child protection; protection services | Priority 06 |
| Vocational Training Institutions | Skills training delivery | Priority 05 |

## 8.4 PARTNERSHIP ENGAGEMENT STRATEGY

### 8.4.1 Engagement Timeline

| Phase | Activity | Timeline |
| --- | --- | --- |
| Phase 1 | Pre-concept discussions with potential financiers and partners | 0-3 months |
| Phase 2 | Concept note submissions | 3-6 months |
| Phase 3 | Feasibility studies and detailed project preparation | 6-18 months |
| Phase 4 | Financing negotiations and PPP procurement | 18-30 months |
| Phase 5 | Financial close and construction start | 30-36 months |

### 8.4.2 Key Engagement Principles

| Principle | Description |
| --- | --- |
| Transparency | Open and honest engagement with all partners |
| Inclusivity | Engagement with diverse stakeholders |
| Alignment | Alignment with partner priorities and requirements |
| Early Engagement | Early engagement to shape project design |
| Sustained Dialogue | Ongoing dialogue throughout project lifecycle |

# CHAPTER NINE: IMPLEMENTATION ROADMAP

## 9.1 IMPLEMENTATION TIMELINE

### 9.1.1 Overview

| Phase | Period | Investment (USD) | Focus |
| --- | --- | --- | --- |
| Phase 0: Preparation | 2024-2025 | 25,000,000 | Feasibility, design, planning |
| Phase 1: Foundation | 2025-2027 | 80,000,000 | Urban Expansion Phase 1; Corridor Roads; Solid Waste; Youth Centre |
| Phase 2: Growth | 2028-2030 | 125,000,000 | FTZ Phase 1; Urban Expansion; Reception Centre |
| Phase 3: Consolidation | 2031-2035 | 150,000,000 | FTZ Phase 2; Urban Expansion Phase 2 |
| TOTAL | 2024-2035 | 380,000,000 |  |

## 9.2 PHASE 0: PROJECT PREPARATION (2024-2025)

| Activity | Timeline | Investment (USD) | Responsible |
| --- | --- | --- | --- |
| Feasibility Studies | 2025 | 5,000,000 | Consultants |
| Environmental Impact Assessments | 2025 | 2,000,000 | Environmental Consultants |
| Financial Modeling | 2025 | 2,000,000 | Financial Consultants |
| PPP Structuring | 2025 | 2,000,000 | PPP Advisor |
| Stakeholder Engagement | 2024-2025 | 2,000,000 | Engagement Team |
| Land Acquisition Planning | 2025 | 12,000,000 | Legal Team |
| TOTAL |  | 25,000,000 |  |

## 9.3 PHASE 1: FOUNDATION AND DESIGN (2025-2027)

| Project | Activities | Investment (USD) | Timeline |
| --- | --- | --- | --- |
| Priority 01: Urban Expansion | Phase 1 design; land readjustment | 20,000,000 | 2025-2027 |
| Priority 02: Corridor Roads | Feasibility; detailed design; construction | 30,000,000 | 2026-2027 |
| Priority 04: Solid Waste | Feasibility; design; construction | 10,000,000 | 2025-2027 |
| Priority 05: Youth Centre | Feasibility; design; construction | 10,000,000 | 2026-2027 |
| Priority 03: FTZ | Market study; feasibility | 5,000,000 | 2026-2027 |
| Priority 06: Reception Centre | Feasibility; design | 5,000,000 | 2026-2027 |
| TOTAL |  | 80,000,000 |  |

## 9.4 PHASE 2: IMPLEMENTATION AND GROWTH (2028-2030)

| Project | Activities | Investment (USD) | Timeline |
| --- | --- | --- | --- |
| Priority 01: Urban Expansion | Phase 1 construction | 43,000,000 | 2028-2030 |
| Priority 03: FTZ | Phase 1 development | 80,000,000 | 2028-2030 |
| Priority 06: Reception Centre | Construction; operational start | 2,000,000 | 2028-2029 |
| TOTAL |  | 125,000,000 |  |

## 9.5 PHASE 3: CONSOLIDATION AND EXPANSION (2031-2035)

| Project | Activities | Investment (USD) | Timeline |
| --- | --- | --- | --- |
| Priority 03: FTZ | Phase 2 development | 150,000,000 | 2031-2035 |
| TOTAL |  | 150,000,000 |  |

## 9.6 CRITICAL PATH MILESTONES

| Milestone | Target Date | Investment (USD) |
| --- | --- | --- |
| Feasibility Studies Completed | 2025 | 5,000,000 |
| Financing Commitments Secured | 2026 | - |
| Land Acquisition Completed | 2026 | 15,000,000 |
| Youth Skills Centre Operational | 2028 | 10,000,000 |
| Solid Waste Management Operational | 2028 | 10,000,000 |
| Corridor Road Upgrade Complete | 2029 | 40,000,000 |
| Urban Expansion Phase 1 Complete | 2030 | 63,000,000 |
| FTZ Phase 1 Operational | 2030 | 80,000,000 |
| Reception Centre Operational | 2031 | 7,000,000 |
| FTZ Fully Operational | 2035 | 250,000,000 |

# CHAPTER TEN: NEXT STEPS AND 90-DAY ACTION PLAN

## 10.1 PRIORITY ACTIONS

| Action | Description | Timeline | Responsibility | Estimated Cost |
| --- | --- | --- | --- | --- |
| Action 1 | Commission Feasibility Studies | 0-90 days | Mayor's Office | USD 2,000,000 - 3,000,000 |
| Action 2 | Initiate Environmental Impact Assessments | 0-90 days | Urban Expansion Team | USD 500,000 - 1,000,000 |
| Action 3 | Engage Potential Financiers | 0-60 days | Mayor's Office/City Manager | Minimal |
| Action 4 | Engage Potential Private Operators/Partners | 0-90 days | City Manager | Minimal |
| Action 5 | Update Project Briefs | 0-90 days | Urban Expansion Team | Minimal |
| Action 6 | Establish Project Implementation Unit | 0-90 days | City Manager | Minimal |

## 10.2 ACTION 1: COMMISSION FEASIBILITY STUDIES

| Element | Details |
| --- | --- |
| Objective | Commission comprehensive feasibility studies for all six projects |
| Scope | Traffic modeling, technical design, economic analysis, financial modeling, PPP structuring |
| Timeline | 0-90 days (procurement); 6-9 months (studies) |
| Responsible | Project Director / Urban Expansion Team |
| Estimated Cost | USD 2,000,000 - 3,000,000 |

### 10.2.1 Priority Studies

| Project | Priority | Est. Cost (USD) |
| --- | --- | --- |
| Priority 03: FTZ & Logistics | Highest | 500,000 - 750,000 |
| Priority 01: Urban Expansion | High | 400,000 - 600,000 |
| Priority 02: Corridor Roads | High | 300,000 - 500,000 |
| Priority 04: Solid Waste | Medium | 200,000 - 300,000 |
| Priority 05: Youth Centre | Medium | 150,000 - 250,000 |
| Priority 06: Reception Centre | Medium | 100,000 - 200,000 |

## 10.3 ACTION 2: INITIATE ENVIRONMENTAL IMPACT ASSESSMENTS

| Element | Details |
| --- | --- |
| Objective | Complete project-specific Environmental Impact Assessments |
| Scope | Environmental baseline, impact assessment, mitigation measures, social impact assessment, environmental management plan |
| Timeline | 0-60 days (procurement); 4-6 months (studies) |
| Responsible | Project Director / Environmental Compliance Officer |
| Estimated Cost | USD 500,000 - 1,000,000 |

## 10.4 ACTION 3: ENGAGE POTENTIAL FINANCIERS

| Element | Details |
| --- | --- |
| Objective | Initiate structured discussions with potential financiers |
| Targets | AfDB, World Bank/IFC, SDC, European DFIs, EU, TradeMark Africa, Cities Alliance |
| Timeline | 0-60 days (initial engagement) |
| Responsible | Mayor's Office / City Manager |

## 10.5 ACTION 4: ENGAGE POTENTIAL PRIVATE OPERATORS AND PARTNERS

| Element | Details |
| --- | --- |
| Objective | Initiate non-binding discussions with potential private sector partners |
| Targets | FTZ operators, logistics companies, infrastructure developers, IOM, UNHCR, NGOs |
| Timeline | 0-90 days |
| Responsible | City Manager / Project Director |

## 10.6 ACTION 5: UPDATE PROJECT BRIEFS

| Element | Details |
| --- | --- |
| Objective | Update all six project briefs with findings from initial discussions |
| Scope | Updated project descriptions, cost estimates, implementation timelines, partnership strategies |
| Timeline | 0-90 days |
| Responsible | Urban Expansion Team |

## 10.7 ACTION 6: ESTABLISH PROJECT IMPLEMENTATION UNIT

| Element | Details |
| --- | --- |
| Objective | Establish a dedicated Project Implementation Unit |
| Structure | Project Manager, Technical Specialist, Financial Specialist, Engagement Officer, Administrative Support |
| Timeline | 0-90 days |
| Responsible | City Manager |

## 10.8 MONITORING AND REPORTING FRAMEWORK

| Report | Frequency | Audience | Responsible |
| --- | --- | --- | --- |
| Weekly Update | Weekly | Project Team; Management | Project Manager |
| Monthly Report | Monthly | Project Team; City Administration | Project Manager |
| Quarterly Report | Quarterly | Financiers; Partners; Government | Project Manager |
| Annual Report | Annually | All stakeholders | Project Manager |
| Financial Report | Quarterly | Financiers; Government | Finance Officer |

# CHAPTER ELEVEN: CONCLUSION AND RECOMMENDATIONS

## 11.1 SUMMARY OF FINDINGS

### 11.1.1 Portfolio Overview

| Finding | Description |
| --- | --- |
| Total Investment | USD 380 million across 6 priority projects |
| Economic Impact | USD 500 million+ annual trade; ~7,000+ jobs |
| Social Impact | 5,000+ youth trained annually; returnees supported |
| Environmental Impact | Citywide waste management; green infrastructure |
| Urban Impact | 12.6-fold expansion managed; 119,000+ served by 2030 |
| Readiness | All projects at Stage 1 (Concept) |

### 11.1.2 Prioritization Summary

| Rank | Priority | Project | Classification | Investment (USD) |
| --- | --- | --- | --- | --- |
| 1 | Priority 01 | Planned Urban Expansion Programme | Foundation | 63,000,000 |
| 2 | Priority 02 | Corridor & Arterial Road Upgrade | Connectivity | 40,000,000 |
| 3 | Priority 03 | Inland Special Trade Zone & Logistics Hub | Economic Engine | 250,000,000 |
| 4 | Priority 04 | Solid Waste Management System | Livability | 10,000,000 |
| 5 | Priority 05 | Youth Skills, Enterprise & Migration Centre | Human Capital | 10,000,000 |
| 6 | Priority 06 | Reception & Reintegration Centre | Social Protection | 7,000,000 |

## 11.2 KEY RECOMMENDATIONS

| Recommendation | Priority | Timeline |
| --- | --- | --- |
| Commission feasibility studies for all projects | Critical | 0-6 months |
| Prioritize Urban Expansion (Priority 01) as Phase 1 foundation | High | Immediate |
| Pursue road upgrade (Priority 02) as Phase 1 connectivity | High | Immediate |
| Develop PPP framework for FTZ (Priority 03) | High | 0-12 months |
| Engage development partners for solid waste (Priority 04) | Medium | 0-12 months |
| Leverage IGAD RMF and Cities Alliance for social projects (Priority 05, 06) | Medium | 0-12 months |
| Establish Project Implementation Unit | Critical | Immediate |

## 11.3 CONCLUSION

The Tog-Wajaale EACC Priority Investment Project provides a comprehensive framework for transforming the city into a thriving, resilient, and inclusive urban center. The prioritization presented in this report ensures that:

| Element | Description |
| --- | --- |
| 1. Foundation projects | Urban Expansion creates the enabling conditions for all other investments |
| 2. Connectivity projects | Road Upgrade provides access and mobility |
| 3. Economic engine projects | FTZ drives growth and job creation |
| 4. Livability projects | Solid Waste ensures environmental sustainability |
| 5. Human capital projects | Youth Centre develops the workforce |
| 6. Social protection projects | Reception Centre supports vulnerable populations |

This sequenced approach ensures that investments build on each other, maximizing impact and ensuring sustainable urban development. All six projects are at Stage 1 (Concept) of the readiness scale, with clear next steps identified to advance each project toward bankability.

The successful implementation of this portfolio will position Tog-Wajaale as a model for sustainable urban development in the Horn of Africa.

# References

- Tog-Wajaale Urban Expansion Plan (2025-2055). Tog-Wajaale City Administration Municipality Office. February 2025. Available at: www.twuep.com.et

- EACC Investment Posters (All 6 Projects). Tog-Wajaale City Administration. August 2026.

- Cities Alliance. (2023). "Ethiopia: Urban Expansion Exposure Visit to Mekelle." Available at: https://www.citiesalliance.org

- Cities Alliance. (2024). "Making Room for Urban Growth – Urban Expansion Planning in Ethiopia, Uganda and Somalia." Available at: https://www.citiesalliance.org

- Marron Institute. (2022). "Ethiopia Urban Expansion Initiative." New York University. Available at: https://marroninstitute.nyu.edu

- IGAD. (2026). "IGAD Launches the Tog-Wajale Cross-Border Regional Migration Fund Initiatives." Available at: https://igad.int

- TradeMark Africa. (2026). "Tog-Wajaale Border Bridge Reconstruction." Available at: https://trademarkafrica.com

- IOM. (2023). "IOM Upscales its Migration Response Centre in Tog-Wajaale." Available at: https://www.iom.int

- Ministry of Urban Development and Housing (MoUDH). (2016). Urban development in Ethiopia: Trends and challenges. Addis Ababa, Ethiopia.

- World Bank. (2021). Urban development in Ethiopia: Trends and challenges. World Bank Group.

- National Bank of Ethiopia. (2026). Daily Foreign Exchange Rates. August 2026.

Prepared By:

Tog-Wajaale City Administration Municipality Office
Urban Expansion Team

Date: August 2026 G.C

Exchange Rate Note: All Birr equivalents are calculated using the exchange rate of 1 USD = 160.0319 Birr as of August 2026. This rate may fluctuate and should be verified for future financial planning.

# Appendices

# APPENDIX A: PROJECT CONTACT INFORMATION

- Primary Contacts

- Project Management Team

- Technical Team

- Support Staff

- Key Government Stakeholders

- Development Partner Contacts

- Private Sector Contacts

- Community and Civil Society Contacts

- Emergency Contacts

- Contact Protocols

## 1. PRIMARY CONTACTS

## 1.1 City Leadership

| Name | Title | Responsibility | Contact |
| --- | --- | --- | --- |
| Mahamud Yusuf Adan | Mayor | Executive leadership overseeing urban development and administration | +251 915 330528 |
| Abdikarim Hassen Yusuf | City Manager | Operational management and implementation of urban development plans | +251 915 074535 |

## 1.2 Project Leadership

| Name | Title | Responsibility | Contact |
| --- | --- | --- | --- |
| Shemshedin Hassen Yusuf | Project Director / Manager | Overall project coordination and management | +251 911 542418 |

## 2. PROJECT MANAGEMENT TEAM

## 2.1 Core Management

| Name | Title | Responsibility | Contact |
| --- | --- | --- | --- |
| Shemshedin Hassen Yusuf | Project Director / Manager | Overall project coordination and management | +251 911 542418 |
| Mohammed Muhumed Ahmed | Infrastructure Development Specialist | Technical oversight; infrastructure design and implementation | [Contact] |
| Mohammed Isse Muhumed | Environmental Compliance Officer | Environmental management; ESIA oversight | [Contact] |
| Abdiwasac Khaliif Muhumed | GIS & Surveying Department | Spatial data; mapping; land surveying | [Contact] |

## 2.2 Additional Management Roles

| Name | Title | Responsibility | Contact |
| --- | --- | --- | --- |
| Finance Officer | Financial Management | Budget management; financial reporting | [Contact] |
| Procurement Officer | Procurement | Procurement and contract management | [Contact] |
| Stakeholder Engagement Manager | Community Engagement | Stakeholder engagement; community relations | [Contact] |
| GRM Officer | Grievance Management | Grievance redress mechanism management | [Contact] |
| Communications Specialist | Communications | Media relations; public information | [Contact] |
| Social Development Specialist | Social Development | Gender; social inclusion; vulnerable groups | [Contact] |

## 3. TECHNICAL TEAM

| Name | Title | Responsibility | Contact |
| --- | --- | --- | --- |
| Urban Planner | Urban Planning | Urban expansion planning; land use | [Contact] |
| Transport Engineer | Transport Engineering | Road design; BRT design; traffic analysis | [Contact] |
| Civil Engineer | Civil Engineering | Infrastructure design; construction supervision | [Contact] |
| Environmental Specialist | Environment | Environmental monitoring; compliance | [Contact] |
| Structural Engineer | Structural Engineering | Building design; structural analysis | [Contact] |
| Electrical Engineer | Electrical Engineering | Power supply; lighting; electrical systems | [Contact] |
| Mechanical Engineer | Mechanical Engineering | Equipment; fleet; mechanical systems | [Contact] |
| Water/Sanitation Engineer | Water & Sanitation | Water supply; sanitation systems | [Contact] |
| Waste Management Specialist | Waste Management | Solid waste systems; recycling | [Contact] |
| Land Surveyor | Land Surveying | Land surveying; mapping | [Contact] |
| GIS Specialist | GIS & Mapping | Spatial analysis; GIS mapping | [Contact] |
| Economist | Economic Analysis | Cost-benefit analysis; economic impact | [Contact] |
| Financial Analyst | Financial Analysis | Financial modeling; investment analysis | [Contact] |

## 4. SUPPORT STAFF

## 4.1 Administrative Support

| Name | Title | Responsibility | Contact |
| --- | --- | --- | --- |
| Administrative Assistant | Administration | Administrative support; scheduling | [Contact] |
| Receptionist | Reception | Front desk; visitor coordination | [Contact] |
| Driver | Logistics | Transport and logistics | [Contact] |

## 4.2 Field Support

| Name | Title | Responsibility | Contact |
| --- | --- | --- | --- |
| Community Liaison Officers (3) | Community Engagement | Day-to-day community engagement | [Contact] |
| Field Monitors | Field Monitoring | Site monitoring; data collection | [Contact] |
| Survey Enumerators | Data Collection | Household surveys; data collection | [Contact] |

## 5. KEY GOVERNMENT STAKEHOLDERS

## 5.1 National Government

| Name | Title | Organization | Contact |
| --- | --- | --- | --- |
| [Name] | Minister | Federal Ministry of Urban Development and Housing | [Contact] |
| [Name] | State Minister | Federal Ministry of Urban Development and Housing | [Contact] |
| [Name] | Director General | Urban Planning Department | [Contact] |
| [Name] | Director General | Environmental Protection Authority | [Contact] |
| [Name] | Director | Labour and Social Affairs | [Contact] |

## 5.2 Regional Government (Somali Regional State)

| Name | Title | Organization | Contact |
| --- | --- | --- | --- |
| [Name] | President | Somali Regional State | [Contact] |
| [Name] | Vice President | Somali Regional State | [Contact] |
| [Name] | Head | Bureau of Urban Development | [Contact] |
| [Name] | Head | Bureau of Finance and Economic Development | [Contact] |
| [Name] | Head | Bureau of Environment, Forest and Climate Change | [Contact] |
| [Name] | Head | Bureau of Labour and Social Affairs | [Contact] |
| [Name] | Head | Bureau of Trade and Industry | [Contact] |

## 5.3 Local Government (Fafen Zone)

| Name | Title | Organization | Contact |
| --- | --- | --- | --- |
| [Name] | Administrator | Fafen Zone Administration | [Contact] |
| [Name] | Head | Zone Urban Development Department | [Contact] |

## 5.4 Local Government (Woreda/Kebele)

| Name | Title | Organization | Contact |
| --- | --- | --- | --- |
| [Name] | Woreda Administrator | Tog-Wajaale Woreda | [Contact] |
| [Name] | Kebele Chair | Kebele 01 | [Contact] |
| [Name] | Kebele Chair | Kebele 02 | [Contact] |
| [Name] | Kebele Chair | Kebele 03 | [Contact] |
| [Name] | Kebele Chair | Kebele 04 | [Contact] |
| [Name] | Kebele Chair | Kebele 05 | [Contact] |
| [Name] | Kebele Chair | Kebele 06 | [Contact] |
| [Name] | Kebele Chair | Kebele 07 | [Contact] |

## 6. DEVELOPMENT PARTNER CONTACTS

| Name | Title | Organization | Contact |
| --- | --- | --- | --- |
| [Name] | Country Director | Swiss Agency for Development and Cooperation (SDC) | [Contact] |
| [Name] | Programme Manager | SDC East Africa | [Contact] |
| [Name] | Country Representative | African Development Bank (AfDB) | [Contact] |
| [Name] | Senior Infrastructure Specialist | AfDB Ethiopia | [Contact] |
| [Name] | Country Manager | World Bank Group / IFC | [Contact] |
| [Name] | Urban Development Specialist | World Bank | [Contact] |
| [Name] | Programme Manager | Cities Alliance | [Contact] |
| [Name] | Regional Director | TradeMark Africa | [Contact] |
| [Name] | Programme Officer | TradeMark Africa Ethiopia | [Contact] |
| [Name] | Country Representative | UNDP Ethiopia | [Contact] |
| [Name] | Programme Manager | IOM Ethiopia | [Contact] |
| [Name] | Head of Office | UNHCR Ethiopia | [Contact] |
| [Name] | Country Representative | IGAD | [Contact] |
| [Name] | Regional Migration Fund Manager | IGAD RMF | [Contact] |
| [Name] | Head of Cooperation | European Union Delegation to Ethiopia | [Contact] |
| [Name] | Country Director | GIZ Ethiopia | [Contact] |

## 7. PRIVATE SECTOR CONTACTS

## 7.1 Potential Partners

| Name | Title | Organization | Contact |
| --- | --- | --- | --- |
| [Name] | Regional Director | DP World | [Contact] |
| [Name] | Country Manager | Logistics Company | [Contact] |
| [Name] | Director | Infrastructure Development Company | [Contact] |
| [Name] | Senior Manager | International Bank | [Contact] |
| [Name] | Country Head | European DFI | [Contact] |

## 7.2 Local Private Sector

| Name | Title | Organization | Contact |
| --- | --- | --- | --- |
| [Name] | President | Tog-Wajaale Chamber of Commerce | [Contact] |
| [Name] | Director | Local Construction Company | [Contact] |
| [Name] | Manager | Local Logistics Company | [Contact] |

## 8. COMMUNITY AND CIVIL SOCIETY CONTACTS

| Name | Title | Organization | Contact |
| --- | --- | --- | --- |
| [Name] | Elder (Ugaas) | Clan Leadership | [Contact] |
| [Name] | Elder (Ugaas) | Clan Leadership | [Contact] |
| [Name] | Chairperson | Women's Association | [Contact] |
| [Name] | Chairperson | Youth Association | [Contact] |
| [Name] | Director | Local NGO | [Contact] |
| [Name] | Community Leader | IDP Community | [Contact] |
| [Name] | Imam | Religious Leadership | [Contact] |
| [Name] | Representative | Persons with Disabilities Association | [Contact] |
| [Name] | Director | Save the Children International (SCI) | [Contact] |
| [Name] | Director | Organization for Welfare and Development in Action (OWDA) | [Contact] |

## 9. EMERGENCY CONTACTS

| Service | Contact |
| --- | --- |
| Police Emergency | 991 |
| Fire Emergency | 939 |
| Ambulance | 907 |
| Tog-Wajaale Hospital | [Contact] |
| Tog-Wajaale Police Station | [Contact] |
| Tog-Wajaale Fire Station | [Contact] |
| City Administration Emergency Line | [Contact] |

## 10. CONTACT PROTOCOLS

## 10.1 Communication Protocols

| Purpose | Contact Person | Protocol |
| --- | --- | --- |
| General Inquiries | Project Email | Email to twuep369@gmail.com; response within 24-48 hours |
| Project Updates | Project Director / Manager | Monthly briefings and quarterly reports |
| Technical Issues | Infrastructure Development Specialist | Direct coordination with technical team |
| Stakeholder Issues | Stakeholder Engagement Manager | Formal engagement through established channels |
| Grievances | GRM Officer | Through GRM channels |
| Media Inquiries | Communications Specialist | Formal media briefing; coordinated response |
| Government Coordination | City Manager | Formal communication through government protocols |
| Partner Coordination | Project Director / Manager | Regular coordination meetings and reports |

## 10.2 Escalation Protocol

| Level | Issue Type | Contact | Timeline |
| --- | --- | --- | --- |
| Level 1 | Minor operational issues | Infrastructure Development Specialist / Project Manager | 24-48 hours |
| Level 2 | Moderate issues affecting project delivery | Project Director / Manager | 48-72 hours |
| Level 3 | Major issues requiring political decision-making | City Manager | 3-5 days |
| Level 4 | Strategic issues affecting project viability | Mayor | 5-7 days |

## 10.3 Key Communication Channels

| Channel | Purpose | Contact |
| --- | --- | --- |
| Project Website | Public information | www.twuep.com.et |
| Project Email | General inquiries | twuep369@gmail.com |
| GRM Email | Grievance submission | complaints@twuep.com.et |
| Media Contact | Press and media | media@twuep.com.et |
| Partner Coordination | Partner engagement | partners@twuep.com.et |

SUMMARY TABLE: KEY CONTACTS

| Category | Key Contact | Role | Contact |
| --- | --- | --- | --- |
| City Leadership | Mahamud Yusuf Adan | Mayor | +251 915 330528 |
| City Leadership | Abdikarim Hassen Yusuf | City Manager | +251 915 074535 |
| Project Management | Shemshedin Hassen Yusuf | Project Director | +251 911 542418 |
| Technical | Mohammed Muhumed Ahmed | Infrastructure Specialist | [Contact] |
| Environment | Mohammed Isse Muhumed | Environmental Officer | [Contact] |
| GIS & Survey | Abdiwasac Khaliif Muhumed | GIS Specialist | [Contact] |
| General Inquiries | - | Project Information | twuep369@gmail.com |
| Grievances | - | Complaints | complaints@twuep.com.et |

# APPENDIX B: KEY REFERENCE DOCUMENTS

- Document 1: Tog-Wajaale Urban Expansion Plan (2025-2055) - Full Report

- Document 2: Tog-Wajaale Urban Expansion Plan - Existing Situation Assessment

- Document 3: Tog-Wajaale Urban Expansion Plan - Population and Density Growth Trends

- Document 4: Tog-Wajaale Urban Expansion Plan - Conceptual Development and Legal Framework

- Document 5: Tog-Wajaale Urban Expansion Plan - Scenario Developments and Analysis

- Document 6: Tog-Wajaale Urban Expansion Plan - Implementation Phases

- Document 7: Third East Africa City Corridor Dialogue - Project Poster

- Document 8: Ethiopian Urban Expansion Initiative - Overview

- Document 9: Tog-Wajaale City - Location and Area Data

- Document 10: Ethio-Berbera Corridor - Trade and Logistics Data

- Document 11: Sustainable Development Goals (SDGs) Alignment

- Document 12: Municipal Financial Data and Budget Context

- Document 13: Legal and Regulatory Framework Summary

- Document 14: Key Infrastructure and Service Gaps

- Document 15: Project Implementation Partners and Stakeholders

- Document 16: Project Monitoring and Evaluation Framework

- Summary Table: Key Reference Documents

DOCUMENT 1: TOG-WAJAALE URBAN EXPANSION PLAN (2025-2055) - FULL REPORT

| Attribute | Details |
| --- | --- |
| Document Title | Ethiopian Urban Expansion Initiative - Somali Regional State - Tog-Wajaale City Urban Expansion Plan |
| Document Type | Comprehensive Urban Development Plan |
| Date | February 2025 G.C |
| Prepared By | Tog-Wajaale City Administration Municipality Office Urban Expansion Team |
| Purpose | Strategic initiative guiding sustainable development and growth over 30 years |
| Page Count | 87 pages (excluding appendices) |
| Key Sections | Chapter 1: Introduction, Chapter 2: Literature Review, Chapter 3: Methodology, Chapter 4: Existing Situation Assessment, Chapter 5: Population and Density Growth Trends, Chapter 6: Conceptual Development and Legal Framework, Chapter 7-11: Scenario Developments and Analysis |
| Key Figures | Location Map, Slope Analysis Map, Proposed Undevelopable Land Map, Existing Road Network Map, Expansion Road Network Map, Scenarios Development Map, Super Block Types Map, Implementation Phases Map |
| Key Tables | Population Growth Trends, Area Projections, Density Analysis, Scenario Comparisons |
| Vision | Transform Tog-Wajaale into a regional center for commerce, education, and culture by 2055 |
| Population Projection | 82,064 (2024) to 554,700 (2055) - 576% increase |
| Area Projection | 711 ha (2024) to 8,990 ha (2055) - 12.6 times increase |

Executive Summary

The Tog-Wajaale City Urban Expansion Project (2025-2055) is a strategic initiative aimed at guiding sustainable development and growth over the next thirty years. Tog-Wajaale, located in the Somali Region of Ethiopia on the border with Somaliland, has experienced steady urban growth, evolving from a small trading Kebele into an administrative and commercial hub. Rapid population growth and increasing demand for urban services have outstripped the city's capacity, resulting in overcrowded informal settlements, strained infrastructure, and insufficient public services.

The project promotes a well-balanced and planned urban expansion that considers future demographic changes, ensuring that Tog-Wajaale can sustain its growth trajectory without compromising residents' quality of life. Key focuses include upgrading infrastructure, improving public service delivery, developing affordable housing, and driving economic growth through industrial and commercial initiatives. The project also integrates aspects such as climate resilience, green spaces, and smart city technologies.

Key Findings

1. Existing Situation Assessment

| Element | Finding |
| --- | --- |
| Topography | Gently flat plains with elevations from 1,510 to 1,615 meters above sea level |
| Slope | General slope ranges from 1% to 5%, conducive to development |
| Climate | Hot semi-arid climate with low rainfall (300-500 mm annually) |
| Environmental Hazards | Periodic droughts, flash floods, desertification risk |
| Road Network | Relatively well-developed in city center; Awbare and Hartishekh roads unpaved |

2. Population and Density Growth Trends

| Period | Population | Growth Rate | Area (ha) | Density (p/ha) |
| --- | --- | --- | --- | --- |
| 1994 | 8,000 | - | 80 | 100.00 |
| 2007 | 14,800 | 85.0% | 138 | 107.25 |
| 2015 | 46,454 | 213.9% | 469 | 99.04 |
| 2024 | 82,064 | 76.6% | 711 | 115.42 |
| 2030 (Projected) | 119,000 | 45.0% | 1,450 | 82.07 |
| 2055 (Projected) | 554,700 | 366.0% | 8,990 | 61.70 |

3. Key Growth Drivers

| Driver | Description |
| --- | --- |
| Strategic Location | On Ethio-Berbera trade corridor, 90 km from Hargeisa, 249 km from Port of Berbera |
| Economic Opportunities | Free Trade Zone, cross-border trade |
| Rural-Urban Migration | Push factors (drought, land degradation); pull factors (jobs, education, healthcare) |
| Infrastructure Development | Investments in roads, utilities, and public services |
| Demographics | Youthful population (60% under 25) |

4. Implementation Phases

| Phase | Period | Focus |
| --- | --- | --- |
| Phase 1 | 2025-2030 | Short-Term Growth and Infrastructure Development |
| Phase 2 | 2031-2045 | Mid-Term Urban Expansion and Economic Development |
| Phase 3 | 2046-2055 | Long-Term Development and Sustainability |

5. Selected Scenario

- Medium-Growth Approach selected as most viable option

- Population: 554,700 by 2055

- Density: 61.7 people per hectare

- Area: 8,990 hectares (12.6 times 2024 built-up area)

Relevance to EACC Portfolio Projects

The Urban Expansion Plan provides the foundational framework for all EACC priority projects. It establishes:

| Project | Relevance |
| --- | --- |
| Priority 01: Urban Expansion | Core framework; provides land-use and population projections |
| Priority 02: Corridor Roads | Identifies road network priorities and infrastructure gaps |
| Priority 03: FTZ & Logistics | Identifies cross-border SEZs as a priority; provides economic context |
| Priority 04: Solid Waste | Names waste management as a public service priority |
| Priority 05: Youth Centre | Identifies vocational training as a priority (5,000/yr by 2030) |
| Priority 06: Reception Centre | Provides social inclusivity and migration context |

DOCUMENT 2: TOG-WAJAALE URBAN EXPANSION PLAN - EXISTING SITUATION ASSESSMENT

| Attribute | Details |
| --- | --- |
| Document Section | Chapter Four: Existing Situation Assessment |
| Pages | Pages 29-42 |
| Key Topics | Topographic Features, Elevation, Slope Analysis, Climate Condition, Environmental Hazards, Site Morphology, Road Network |
| Key Figures | Slope Analysis Map, Proposed Undevelopable Land Map, Existing Road Network Map |
| Key Tables | Climate Data, Road Network Classification |

Key Findings

1. Topographic Features

| Feature | Description |
| --- | --- |
| Elevation | 1,510 to 1,615 meters above sea level |
| Terrain | Gently flat plains with rolling terrain and outcrops |
| Development Suitability | Flat areas suitable for residential, commercial, industrial development |
| Constraints | Seasonal riverbeds and watercourses can impact land use |

2. Slope Analysis

| Slope Range | Suitability |
| --- | --- |
| 1% - 5% | Generally gentle, conducive to development |
| >5% | Found in western region and along riverbeds |
| Flood Risk Areas | Central, southern, southeastern, southwestern parts near seasonal riverbeds |

3. Climate Condition

| Parameter | Details |
| --- | --- |
| Climate Type | Hot semi-arid |
| Temperature | 28°C to 35°C (daytime) |
| Rainfall | 300-500 mm annually |
| Rainy Seasons | Gu (April-June), Deyr (October-November) |
| Key Risks | Droughts, flash floods, desertification, dust storms |

4. Environmental Hazards

| Hazard | Risk Level | Affected Areas |
| --- | --- | --- |
| Droughts | High | Entire region |
| Flash Floods | Medium | Low-lying areas near riverbeds |
| Desertification | Medium | Semi-arid areas |
| Erosion | Medium | Sloped regions in northern and eastern parts |

5. Road Network

| Road Type | Status | Description |
| --- | --- | --- |
| Arterial Roads | Asphalt (except Awbare, Hartishekh) | Connect to Jigjiga, Dire Dawa, Addis Ababa, Somaliland |
| Feeder Roads | Variable | Connect rural areas to urban core |
| Proposed Roads | 14m-50m width | Arterial and sub-arterial roads for future expansion |

Relevance to EACC Portfolio Projects

The Existing Situation Assessment provides critical data on:

| Project | Relevance |
| --- | --- |
| Priority 02: Corridor Roads | Topographic constraints, flood risk areas, current road network condition |
| Priority 01: Urban Expansion | Land suitability, environmental hazards requiring mitigation |
| Priority 04: Solid Waste | Climate context, environmental risks |
| All Projects | Climate risks that must be addressed in infrastructure design |

DOCUMENT 3: TOG-WAJAALE URBAN EXPANSION PLAN - POPULATION AND DENSITY GROWTH TRENDS

| Attribute | Details |
| --- | --- |
| Document Section | Chapter Five: Population and Density Growth Trends |
| Pages | Pages 43-52 |
| Key Topics | Historical Data and Growth Trends, Population Projections, Key Growth Factors, Recommendations |
| Data Sources | Central Statistical Agency (CSA), Local Kebeles, Elders Gosa leader Ugaas of Clan, Satellite Imagery (30 years) |
| Key Tables | Population Growth by Period, Area Projections, Density Analysis |
| Key Figures | Population Growth Chart, Density Trends Chart |

Key Findings

1. Historical Growth Trends

Period 1: 1994-2007 (Early Urban Growth)

- Population: 8,000 → 14,800 (85% growth)

- Area: 80 ha → 138 ha (72.5% expansion)

- Density: 100 → 107.25 p/ha (+0.54% per year)

- Key Drivers: Migration, Infrastructure developments

Period 2: 2007-2015 (Rapid Transformation)

- Population: 14,800 → 46,454 (213.9% growth)

- Area: 138 ha → 469 ha (239.9% expansion)

- Density: 107.25 → 99.04 p/ha (-0.97% per year)

- Key Drivers: Urbanization plateau, Suburban development

Period 3: 2015-2024 (Sustained Growth)

- Population: 46,454 → 82,064 (76.6% growth)

- Area: 469 ha → 711 ha (51.6% expansion)

- Density: 99.04 → 115.42 p/ha (+1.68% per year)

- Key Drivers: Economic growth, Better living conditions, Improved land-use efficiency

2. Population and Area Projections

| Period | Population | Area (ha) | Density (p/ha) |
| --- | --- | --- | --- |
| 2024 | 82,064 | 711 | 115.42 |
| 2030 | 119,000 | 1,450 | 82.07 |
| 2045 | 301,600 | 4,200 | 71.81 |
| 2055 | 554,700 | 8,990 | 61.70 |

3. Key Factors Influencing Future Growth

| Factor | Impact |
| --- | --- |
| Ethio-Berbera Corridor | Reduced logistics costs (~30%), attracting logistics companies and businesses |
| Cross-Border Trade | Free Trade Zone facilitating trade in livestock, textiles, electronics |
| Rural-Urban Migration | Push factors (droughts, land degradation); Pull factors (jobs, education, healthcare) |
| Infrastructure Development | Strategic investments in roads, utilities, public services |
| Demographics | Youthful population (60% under 25), increasing demand for urban housing |

4. Recommendations

| Recommendation | Description |
| --- | --- |
| Integrated Master Planning | 20-year master plan with density thresholds, climate-responsive zoning |
| Sustainable Infrastructure | Decentralized water recycling, solar microgrids, flood-resistant drainage |
| Affordable Housing | 20-25% affordable units mandate, slum upgrading |
| Transit-Oriented Development | BRT development, mixed-use zones near transit hubs |
| Smart City Technologies | IoT, data analytics, digital land registry |
| Economic Diversification | Free Trade Zone expansion, vocational training centers |
| Regional Collaboration | Strengthen Ethiopia-Somaliland partnerships |

Relevance to EACC Portfolio Projects

The Population and Density Growth Trends provide:

| Project | Relevance |
| --- | --- |
| Priority 01: Urban Expansion | Population projections (576% increase); land area requirements |
| Priority 02: Corridor Roads | Travel demand projections; road network expansion needs |
| Priority 03: FTZ & Logistics | Economic growth projections; labour force availability |
| Priority 05: Youth Centre | Youth population projections; training demand |
| Priority 04: Solid Waste | Waste generation projections based on population growth |

DOCUMENT 4: TOG-WAJAALE URBAN EXPANSION PLAN - CONCEPTUAL DEVELOPMENT AND LEGAL FRAMEWORK

| Attribute | Details |
| --- | --- |
| Document Section | Chapter Six: Conceptual Development and Legal Framework |
| Pages | Pages 53-56 |
| Key Topics | Implementation Phases, Stakeholder Engagement, National Legal Context, Regional Legal Considerations, Local Legal Structures, International Framework, Legal Compliance |
| Key Tables | Legal Framework Summary, Stakeholder Roles |

Key Findings

1. Conceptual Development

Strategic Goals (2024-2055):

| Goal | Objective |
| --- | --- |
| Infrastructure Development | Build resilient, interconnected infrastructure |
| Economic Growth | Position as regional trade and innovation hub |
| Housing and Social Services | Ensure equitable access to quality housing and services |
| Environmental Sustainability | Integrate climate resilience into urban systems |
| Social Inclusivity | Empower marginalized groups in urban governance |

2. Implementation Phases

| Phase | Period | Focus |
| --- | --- | --- |
| Short-Term | 2025-2030 | Initial planning, land acquisition, feasibility studies, infrastructure groundwork |
| Medium-Term | 2031-2045 | Large-scale construction of residential, commercial, and infrastructure projects |
| Long-Term | 2046-2055 | Consolidation of urban systems, refinement of services, further expansion |

3. Stakeholder Engagement

| Stakeholder | Role |
| --- | --- |
| Local Government | Lead planning, regulation, monitoring |
| Private Sector and Investors | Public-private partnerships |
| Community Participation | Decision-making input |

4. Legal Framework Summary

| Level | Framework Component |
| --- | --- |
| National | Constitution of Ethiopia, Urban and Land Use Policies, Environmental Laws |
| Regional | Land Use and Ownership, Urban Planning Regulations (Somali Region) |
| Local | Municipal Laws, Building Codes, Taxation and Incentives |
| International | Sustainable Development Goals (SDGs), International Investment Agreements |

5. Legal Compliance and Risk Management

| Element | Description |
| --- | --- |
| Risk Management | Identify and address legal risks (land acquisition, displacement, environmental degradation) |
| Dispute Resolution | Arbitration, mediation, courts of law |
| Monitoring and Enforcement | Regular audits and assessments |
| Adaptation | Revise zoning laws, incorporate emerging technologies, update environmental regulations |

Relevance to EACC Portfolio Projects

The Conceptual Development and Legal Framework provides:

| Project | Relevance |
| --- | --- |
| All Projects | Strategic goals that all projects support |
| All Projects | Implementation phases and timelines |
| All Projects | Stakeholder engagement framework |
| All Projects | Legal and regulatory compliance requirements |
| All Projects | Risk management framework |

DOCUMENT 5: TOG-WAJAALE URBAN EXPANSION PLAN - SCENARIO DEVELOPMENTS AND ANALYSIS

| Attribute | Details |
| --- | --- |
| Document Sections | Chapter Seven and Eight: Scenario Developments |
| Pages | Pages 57-67 |
| Key Topics | Three Growth Scenarios, Comparative Analysis, Selected Scenario Rationale |
| Key Figure | Scenarios Developments Map |
| Key Tables | Scenario Comparison Matrix |

Key Findings

1. Scenario 1: Low-Growth Approach

| Parameter | Value |
| --- | --- |
| Projected Area | 11,094 hectares |
| Population Growth | 4-5% annual growth rate |
| Urban Density | 50 people per hectare |
| Infrastructure Development | Basic improvements, minimal upgrades |
| Advantages | Cost-effective, minimizes environmental impact |
| Challenges | Risk of overcrowding, inadequate facilities, limited economic development |

2. Scenario 2: Medium-Growth Approach (SELECTED)

| Parameter | Value |
| --- | --- |
| Projected Area | 8,990 hectares |
| Population Growth | 6.4% annual growth rate |
| Urban Density | 61.7 people per hectare |
| Infrastructure Development | Modernizing existing, developing new facilities |
| Advantages | Balanced growth, sustainable, adequate housing and services |
| Challenges | Requires effective governance and resource allocation |

3. Scenario 3: High-Growth Approach

| Parameter | Value |
| --- | --- |
| Projected Area | 4,806 hectares |
| Population Growth | 6.4% annual growth rate |
| Urban Density | 115.42 people per hectare |
| Infrastructure Development | Large-scale projects, smart city initiatives |
| Advantages | High economic growth potential, employment generation |
| Challenges | High financial costs, environmental degradation, unbalanced development |

4. Rationale for Selecting Scenario 2

| Reason | Description |
| --- | --- |
| Sustainability | Resources utilized efficiently without overburdening environment |
| Feasibility | Aligns with city's current capacities and potential for scaling up |
| Economic Opportunities | Promotes steady economic development |
| Infrastructure Development | Focuses on both improving existing systems and new infrastructure |
| Population Management | Provides adequate housing, services, and urban space |

Relevance to EACC Portfolio Projects

The Scenario Developments analysis confirms:

| Project | Relevance |
| --- | --- |
| All Projects | Medium-growth scenario provides foundation for investment case |
| Priority 01: Urban Expansion | Land area projections (8,990 ha by 2055) |
| Priority 02: Corridor Roads | Infrastructure development priorities |
| Priority 03: FTZ & Logistics | Economic growth context |

DOCUMENT 6: TOG-WAJAALE URBAN EXPANSION PLAN - IMPLEMENTATION PHASES

| Attribute | Details |
| --- | --- |
| Document Section | Chapter Ten: Implementation Phases |
| Pages | Pages 75-82 |
| Key Topics | Three Key Implementation Phases, Activities, Deliverables, Challenges |
| Key Figure | Implementation Phases Map |
| Key Tables | Phase-by-Phase Activities and Deliverables |

Key Findings

1. Phase 1: Short-Term Growth and Infrastructure Development (2025-2030)

| Element | Details |
| --- | --- |
| Objective | Establish foundational understanding and prepare for early urban expansion |
| Key Actions | Validate population projections, map current land uses, finalize zoning regulations |
| Infrastructure Expansion | Water/sanitation systems, road/transportation infrastructure, affordable housing projects |
| Growth Management | Density control measures, mixed-use zoning guidelines, vertical housing solutions |
| Challenges | Gathering accurate demographic data, securing land for infrastructure |
| Deliverables | Updated zoning maps, infrastructure/land use plan, completed water/sanitation systems, transportation infrastructure, housing developments |

2. Phase 2: Mid-Term Urban Expansion and Economic Development (2031-2045)

| Element | Details |
| --- | --- |
| Objective | Fine-tune zoning regulations and scale up infrastructure |
| Growth Management | Review and optimize zoning laws, mixed-use development incentives, public-private partnerships |
| Infrastructure Scaling | Large-scale transport projects, upgrade public utilities, education/healthcare expansion |
| Urban Sprawl Prevention | Tighten land use regulations, compact city models, environmental conservation areas |
| Challenges | Securing funding for long-term infrastructure, integrating renewable energy |
| Deliverables | Updated zoning/land use plans, mixed-use development projects, expanded public transport networks, infrastructure upgrades, healthcare/education facilities |

3. Phase 3: Long-Term Development and Sustainability (2046-2055)

| Element | Details |
| --- | --- |
| Objective | Plan for long-term growth and ensure sustainability |
| Urban Growth Planning | Master plan for expansion, land acquisition for future growth, smart city technologies |
| Infrastructure Overhaul | Public transport networks (metro), renewable energy integration, advanced water/waste systems |
| Environmental Sustainability | Green building standards, expanded green spaces, eco-friendly waste management |
| Challenges | Long-term funding, anticipating future technologies |
| Deliverables | Long-term master plan, strategic land acquisitions, metro systems, renewable energy projects, green urban developments, urban parks |

Relevance to EACC Portfolio Projects

The Implementation Phases provide:

| Project | Relevance |
| --- | --- |
| All Projects | Phase 1 timeline (2025-2030) directly aligned with all projects |
| Priority 02: Corridor Roads | Specific activities including transportation infrastructure development |
| Priority 01: Urban Expansion | Growth management strategies |
| Priority 03: FTZ & Logistics | Phase 2 integration with broader urban expansion |

DOCUMENT 7: THIRD EAST AFRICA CITY CORRIDOR DIALOGUE - PROJECT POSTER

| Attribute | Details |
| --- | --- |
| Document Title | Third East Africa City Corridor Dialogue - BRT Corridor & Arterial Road Upgrade - Tog-Wajaale |
| Supported By | Swiss Agency for Development and Cooperation (SDC) |
| Event | Third East Africa City Corridor Dialogue |
| Project Owner | Tog-Wajaale City Administration Municipality Office |
| Sector | Urban Transport & Road Infrastructure |
| Readiness Stage | Stage 2 of 5 (Pre-Feasibility) |
| Total Project Cost | USD 50.0 million / Birr 8.0 billion |

Key Findings

1. Project Overview

| Element | Details |
| --- | --- |
| Project Name | BRT Corridor & Arterial Road Upgrade — Tog-Wajaale |
| Description | Bus Rapid Transit and upgraded arterial roads along the Ethio-Berbera Corridor in Tog-Wajaale, Ethiopia |
| Location | Tog-Wajaale, Somali Regional State, Ethiopia |
| Sector | Urban Transport & Road Infrastructure |
| Project Owner | Tog-Wajaale City Administration Municipality Office |
| Readiness Stage | Stage 2 of 5 (Pre-Feasibility) |

2. Opportunity

| Element | Details |
| --- | --- |
| Population Growth | 82,064 (2024) → ~119,000 (2030) |
| Strategic Significance | Key node on Ethio-Berbera trade corridor |
| Risk | Unmanaged growth risks congestion, undermines ~30% logistics-cost saving over Djibouti route |

3. Proposed Solution

| Element | Details |
| --- | --- |
| BRT Line | 10 km along Ethio-Berbera Corridor |
| Right-of-Way | 50 meters |
| Connecting Roads | Paving Awbare and Hartishekh routes |
| NMT Infrastructure | 50 km pedestrian and cycle pathways by 2030 |
| Investment | USD 50.0 million for road construction, BRT stations and fleet, NMT infrastructure |

4. Investment Snapshot

| Element | Details |
| --- | --- |
| Total Project Cost | USD 50.0 million / Birr 8.0 billion |
| Instrument Sought | Grant / Debt / Equity / PPP / Blended |
| Implementation Period | 2025-2030 (Phase 1 of Urban Expansion Plan) |
| Partnership Sought | Financier / Operator / Adviser / Contractor |

5. Value Created

| Element | Target |
| --- | --- |
| People Served by 2030 | ~119,000 |
| Jobs Created/Sustained | To be quantified |
| Beneficiaries | Women / Youth / Displaced & Host Communities |
| Reduction in Private Vehicle Use | 30% by 2040 |

6. Municipal Revenue Context

| Fiscal Year | Municipal Revenue (Birr) | Municipal Revenue (USD)* |
| --- | --- | --- |
| FY 2018 E.C. (2025-26 G.C.) | 144,000,000 | 899,821 |
| FY 2019 E.C. (2026-27 G.C.) | 195,000,000 | 1,218,507 |

Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

7. Top Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Bankability | Strengthen evidence base, complete feasibility study |
| Financing & Partnership | Identify suitable instruments and partners |
| Next Steps | Complete feasibility study, engage financiers |

Relevance to EACC Portfolio Projects

The Project Poster provides:

| Project | Relevance |
| --- | --- |
| Priority 02: Corridor Roads | Concise summary of the road upgrade project |
| All Projects | Key investment parameters, population and impact projections |
| All Projects | Municipal revenue context, risk identification |

DOCUMENT 8: ETHIOPIAN URBAN EXPANSION INITIATIVE - OVERVIEW

| Attribute | Details |
| --- | --- |
| Initiative | Ethiopian Urban Expansion Initiative |
| Region | Somali Regional State |
| City | Tog-Wajaale |
| Partners | Cities Alliance, Swiss Agency for Development and Cooperation (SDC), various donors |
| Related Programs | Cities and Migration Program |

Key Findings

1. Initiative Background

The Ethiopian Urban Expansion Initiative is a national program aimed at supporting sustainable urban growth in Ethiopian cities. The initiative focuses on secondary cities experiencing rapid population growth due to migration, economic development, and strategic positioning.

2. Key Principles

| Principle | Description |
| --- | --- |
| Participatory Planning | Engagement of stakeholders at all stages |
| Evidence-Based | Use of data and analysis to inform decisions |
| Sustainable Development | Balance economic, social, and environmental objectives |
| Climate Resilience | Integration of climate adaptation measures |
| Inclusive Growth | Benefit sharing across all segments of population |

3. Related Programs

| Program | Description |
| --- | --- |
| Cities and Migration Program | Enhancing capacity of cities to support refugees and migrants |
| Urban Expansion Planning | Development of comprehensive urban expansion plans |
| Infrastructure Development | Support for critical infrastructure projects |

4. Key Achievements

| Achievement | Description |
| --- | --- |
| Urban Expansion Plan | Completed for Tog-Wajaale (2025-2055) |
| Stakeholder Engagement | Broad participation in planning process |
| International Recognition | Presented at East Africa City Corridor Dialogue |
| Donor Support | Engaging with multiple development partners |

Relevance to EACC Portfolio Projects

The Ethiopian Urban Expansion Initiative provides:

| Project | Relevance |
| --- | --- |
| All Projects | Policy context for all projects |
| All Projects | Partnership framework including SDC and Cities Alliance |
| Priority 05 & 06 | Programmatic alignment with Cities and Migration Program |
| All Projects | Evidence of stakeholder engagement and donor support |

DOCUMENT 9: TOG-WAJAALE CITY - LOCATION AND AREA DATA

| Attribute | Details |
| --- | --- |
| Region | Somali Regional State |
| Zone | Fafen Zone |
| Woreda | Tog-Wajaale Woreda |
| Administrative Status | City Administrative Center (established 2009 E.C.) |

Key Findings

1. Location Data

| Element | Value |
| --- | --- |
| Distance from Hargeisa | ~90 km |
| Distance from Port of Berbera | ~249 km |
| Distance from Jigjiga | ~70 km |
| Distance from Harar | ~175 km |
| Coordinates | 38P 1061474.60m N, 316716.77m E |
| Elevation | 1,510 to 1,615 meters |

2. Administrative Structure

| Element | Details |
| --- | --- |
| Kebele Administrations | 20 total |
| Built-up Areas | 7 kebele |
| Peripheral Regions | 13 kebele |

3. Area Data

| Element | Value |
| --- | --- |
| Total Built-up Area | ~711 hectares |
| Shape | Relatively compact, extending south, west, southeast |
| Projected Area (2055) | ~8,990 hectares |
| Expansion Factor | ~12.6 times current area |

4. Route Connections

| Route | Destination |
| --- | --- |
| Main Highway | Tog-Wajaale → Jigjiga → Harar → Dire Dawa |
| Northern Route | Tog-Wajaale → Harti Shek |
| Southern Route | Tog-Wajaale → Awbare |

Relevance to EACC Portfolio Projects

The Location and Area Data provides:

| Project | Relevance |
| --- | --- |
| Priority 02: Corridor Roads | Geographic context for corridor alignment; route connections |
| Priority 01: Urban Expansion | Area data for infrastructure planning |
| All Projects | Administrative structure for stakeholder engagement |

DOCUMENT 10: ETHIO-BERBERA CORRIDOR - TRADE AND LOGISTICS DATA

| Attribute | Details |
| --- | --- |
| Corridor | Ethio-Berbera Trade Corridor |
| Countries | Ethiopia and Somaliland |
| Key Port | Port of Berbera |
| Strategic Significance | Alternative to Djibouti route |

Key Findings

1. Trade Connectivity

| Element | Details |
| --- | --- |
| Logistics Cost Reduction | ~30% compared to Djibouti route |
| Route Length | ~249 km from Berbera to Tog-Wajaale |
| Key Commodities | Livestock, textiles, electronics |
| Trade Volume | Growing, supported by Free Trade Zone |

2. Economic Impact

| Element | Details |
| --- | --- |
| Job Creation | Transportation, customs, services sectors |
| Investment Attraction | Logistics companies, warehouses, cross-border businesses |
| Industrial Growth | Agro-processing, manufacturing, commercial real estate |
| Population Growth | Rural-urban migration due to economic opportunities |

3. Infrastructure

| Element | Details |
| --- | --- |
| Road Status | Main corridor paved; connecting roads (Awbare, Hartishekh) unpaved |
| Trade Facilities | Free Trade Zone established after 2015 |
| Border Crossing | Tog-Wajaale serves as transit point |

4. Challenges

| Challenge | Description |
| --- | --- |
| Congestion | Increasing traffic volumes |
| Infrastructure Gaps | Unpaved connecting roads |
| Coordination | Need for Ethiopia-Somaliland cooperation |

Relevance to EACC Portfolio Projects

The Ethio-Berbera Corridor data provides:

| Project | Relevance |
| --- | --- |
| Priority 03: FTZ & Logistics | Economic justification; logistics cost reduction |
| Priority 02: Corridor Roads | Infrastructure gaps that the project addresses |
| All Projects | Regional significance and partnership opportunities |

DOCUMENT 11: SUSTAINABLE DEVELOPMENT GOALS (SDGS) ALIGNMENT

| Attribute | Details |
| --- | --- |
| Framework | United Nations Sustainable Development Goals |
| Related Goals | SDG 7, SDG 8, SDG 9, SDG 11, SDG 13, SDG 17 |

Key Findings

1. Primary Alignment

| SDG | Goal Description | Project Contribution |
| --- | --- | --- |
| SDG 11 | Sustainable Cities and Communities | Urban expansion planning, sustainable transport, affordable housing |
| SDG 13 | Climate Action | Climate-resilient infrastructure, reduced emissions, NMT |

2. Secondary Alignment

| SDG | Goal Description | Project Contribution |
| --- | --- | --- |
| SDG 7 | Affordable and Clean Energy | Renewable energy integration, energy-efficient systems |
| SDG 8 | Decent Work and Economic Growth | Job creation, economic diversification |
| SDG 9 | Industry, Innovation and Infrastructure | Transport infrastructure, smart city technologies |
| SDG 17 | Partnerships for the Goals | Public-private partnerships, stakeholder engagement |

3. SDG 11 Targets Addressed

| Target | Description | Project Contribution |
| --- | --- | --- |
| 11.1 | Adequate housing and basic services | Improved accessibility to housing and services |
| 11.2 | Sustainable transport systems | BRT and NMT infrastructure development |
| 11.3 | Participatory urban planning | Stakeholder engagement in planning process |
| 11.6 | Reduce environmental impact of cities | Reduced emissions through mode shift |
| 11.7 | Universal access to green public spaces | NMT pathways and green infrastructure |
| 11.a | Positive economic, social, environmental links | Regional connectivity and economic growth |

Relevance to EACC Portfolio Projects

The SDG alignment provides:

| Project | Relevance |
| --- | --- |
| All Projects | International framework for project justification |
| All Projects | Attractiveness to development partners and financiers |
| All Projects | Performance indicators for project monitoring |
| All Projects | Framework for reporting and accountability |

DOCUMENT 12: MUNICIPAL FINANCIAL DATA AND BUDGET CONTEXT

| Attribute | Details |
| --- | --- |
| Source | Tog-Wajaale City Administration |
| Data Type | Municipal Revenue and Budget Data |
| Period | FY 2018 E.C. (2025-26 G.C.) and FY 2019 E.C. (2026-27 G.C.) |

Key Findings

1. Municipal Revenue

| Fiscal Year | Municipal Revenue (Birr) | Municipal Revenue (USD)* |
| --- | --- | --- |
| FY 2018 E.C. (2025-26 G.C.) | 144,000,000 | 899,821 |
| FY 2019 E.C. (2026-27 G.C.) | 195,000,000 | 1,218,507 |

Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

2. Revenue Composition (Estimated)

| Revenue Source | Estimated Percentage |
| --- | --- |
| Local Taxes | 40-50% |
| Government Transfers | 20-30% |
| Service Fees | 10-20% |
| Other Revenue | 5-10% |

3. Budget Context

| Element | Details |
| --- | --- |
| Total Municipal Budget | Birr 144-195 million annually |
| Capital Expenditure | Typically 20-30% of budget |
| Infrastructure Allocation | Limited capacity for large-scale projects |
| Debt Service Capacity | Limited; project requires external financing |

4. Financial Implications for Projects

| Implication | Description |
| --- | --- |
| Funding Gap | Municipal revenue insufficient for USD 380 million portfolio |
| External Financing Required | All projects require development finance and private investment |
| Municipal Contribution | Limited to coordination, land acquisition, and oversight |
| O&M Contribution | Municipal may need to support O&M subsidies |
| Revenue Sharing | Municipal will share revenue from FTZ and other projects |

Relevance to EACC Portfolio Projects

The Municipal Financial Data provides:

| Project | Relevance |
| --- | --- |
| All Projects | Context for understanding municipal fiscal capacity |
| All Projects | Justification for external financing requirements |
| All Projects | Basis for structuring municipal contribution |
| All Projects | Context for O&M financial planning |

DOCUMENT 13: LEGAL AND REGULATORY FRAMEWORK SUMMARY

| Attribute | Details |
| --- | --- |
| Source | Tog-Wajaale Urban Expansion Plan, Chapter Six |
| Data Type | Legal and Regulatory Framework |
| Levels | National, Regional, Local, International |

Key Findings

1. National Legal Framework

| Law/Policy | Relevance to Projects |
| --- | --- |
| Constitution of Ethiopia | Land ownership, urbanization, right to housing and development |
| National Urban Planning Laws | Land-use zoning, urban expansion, infrastructure development |
| Environmental Protection Laws | Environmental Impact Assessment, waste management, pollution control |
| Land Use Policies | Land allocation, zoning, urban expansion guidelines |

2. Regional Legal Framework (Somali Region)

| Law/Policy | Relevance to Projects |
| --- | --- |
| Land Use and Ownership Regulations | Land tenure arrangements, land redistribution, acquisition |
| Urban Planning Policies | Zoning, development, building codes |
| Regional Development Plans | Alignment with regional growth strategies |

3. Local Legal Framework (Tog-Wajaale Municipality)

| Law/Policy | Relevance to Projects |
| --- | --- |
| Municipal Laws | Building permits, development guidelines, infrastructure projects |
| Building Codes and Safety Regulations | Construction standards, safety requirements |
| Taxation and Incentives | Tax incentives for investors, construction companies, developers |

4. International Framework

| Framework | Relevance to Projects |
| --- | --- |
| Sustainable Development Goals (SDGs) | SDG 11 (Sustainable Cities), SDG 13 (Climate Action) |
| International Investment Agreements | Foreign investment facilitation |
| Climate Agreements | Climate action and resilience commitments |

Relevance to EACC Portfolio Projects

The Legal and Regulatory Framework provides:

| Project | Relevance |
| --- | --- |
| All Projects | Compliance requirements for project implementation |
| Priority 03: FTZ & Logistics | Land acquisition and zoning guidelines |
| Priority 04: Solid Waste | Environmental approval processes |
| All Projects | Incentive structures for private investment |
| All Projects | International alignment for financing and partnership |

DOCUMENT 14: KEY INFRASTRUCTURE AND SERVICE GAPS

| Attribute | Details |
| --- | --- |
| Source | Tog-Wajaale Urban Expansion Plan, Chapter Four |
| Data Type | Infrastructure Assessment |
| Key Sectors | Transport, Water, Sanitation, Energy |

Key Findings

1. Transport Infrastructure Gaps

| Gap | Description | Impact |
| --- | --- | --- |
| Road Network | Outdated, insufficient for population growth | Congestion, reduced mobility |
| Connecting Roads | Awbare, Hartishekh unpaved | Limited accessibility, reduced economic opportunities |
| Public Transport | No formalized system | Reliance on private vehicles, congestion, environmental impact |
| NMT Infrastructure | Insufficient pedestrian, cycling infrastructure | Safety concerns, limited mobility options |

2. Utility Infrastructure Gaps

| Gap | Description | Impact |
| --- | --- | --- |
| Water Supply | Insufficient for growing population | Water scarcity, health concerns |
| Sanitation | Inadequate systems | Health risks, environmental degradation |
| Electricity | Unreliable supply | Economic constraints, service limitations |

3. Social Infrastructure Gaps

| Gap | Description | Impact |
| --- | --- | --- |
| Healthcare | Insufficient facilities | Limited access to healthcare |
| Education | Inadequate capacity | Limited access to education |
| Housing | Affordability and availability gaps | Informal settlements, overcrowding |

Relevance to EACC Portfolio Projects

The Infrastructure and Service Gaps provide:

| Project | Relevance |
| --- | --- |
| Priority 02: Corridor Roads | Justification for transport infrastructure investment |
| Priority 01: Urban Expansion | Context for broader infrastructure needs |
| Priority 04: Solid Waste | Framework for addressing environmental infrastructure |
| All Projects | Basis for project scope and priorities |

DOCUMENT 15: PROJECT IMPLEMENTATION PARTNERS AND STAKEHOLDERS

| Attribute | Details |
| --- | --- |
| Source | Tog-Wajaale Urban Expansion Plan, Various Sections |
| Data Type | Stakeholder and Partner Mapping |

Key Findings

1. Government Partners

| Partner | Role |
| --- | --- |
| Federal Ministry of Urban Development | Policy guidance, oversight |
| Somali Regional Government | Regional coordination, approval |
| Tog-Wajaale City Administration | Project ownership, implementation |
| Fafen Zone Administration | Regional coordination |

2. Development Partners

| Partner | Role |
| --- | --- |
| Swiss Agency for Development (SDC) | Technical support, potential financing |
| Cities Alliance | Programmatic support |
| African Development Bank (AfDB) | Potential financing |
| World Bank Group | Potential financing, PPP support |

3. Private Sector Partners

| Partner | Role |
| --- | --- |
| Transport Operators | BRT operation, fleet management |
| Infrastructure Developers | Construction, design |
| Financial Institutions | Financing, investment |
| Technology Providers | ITS, fare collection, systems |

4. Community Stakeholders

| Stakeholder | Role |
| --- | --- |
| Kebele Administrations | Local governance |
| Community Elders (Ugaas) | Community representation |
| Women's Groups | Gender equity advocacy |
| Youth Groups | Youth representation |

Relevance to EACC Portfolio Projects

The Stakeholder and Partner Mapping provides:

| Project | Relevance |
| --- | --- |
| All Projects | Engagement framework for project implementation |
| Priority 03: FTZ & Logistics | Partnership opportunities for financing and delivery |
| All Projects | Community engagement structure |
| All Projects | Governance and oversight mechanism |

DOCUMENT 16: PROJECT MONITORING AND EVALUATION FRAMEWORK

| Attribute | Details |
| --- | --- |
| Source | Tog-Wajaale Urban Expansion Plan, Chapter Eleven |
| Data Type | Monitoring and Evaluation Framework |
| Key Elements | Indicators, Targets, Reporting |

Key Findings

1. Key Performance Indicators

| Indicator | Target | Measurement |
| --- | --- | --- |
| Population Growth | 576% increase (2024-2055) | Census data, projections |
| Urban Area Expansion | 12.6 times increase | GIS mapping |
| Density Management | 61.7 p/ha by 2055 | Population/area analysis |
| Infrastructure Completion | Phase milestones | Project reports |
| Housing Provision | Affordable housing targets | Housing data |

2. Infrastructure-Specific Indicators

| Indicator | Target | Measurement |
| --- | --- | --- |
| Road Network Expansion | % complete | Physical surveys |
| BRT Implementation | Operational status | Project reports |
| NMT Infrastructure | km completed | Physical surveys |
| Utility Coverage | % population served | Utility data |

3. Reporting Framework

| Report | Frequency | Audience |
| --- | --- | --- |
| Project Update | Weekly | Implementation Team |
| Progress Report | Monthly | Project Manager, City Manager |
| Quarterly Report | Quarterly | Mayor, City Council |
| Annual Report | Annually | All stakeholders, Development Partners |

Relevance to EACC Portfolio Projects

The Monitoring and Evaluation Framework provides:

| Project | Relevance |
| --- | --- |
| All Projects | Performance indicators for all projects |
| All Projects | Reporting requirements for project implementation |
| All Projects | Accountability framework for financing |
| All Projects | Basis for project monitoring and evaluation |

SUMMARY TABLE: KEY REFERENCE DOCUMENTS

| Document No. | Document Title | Key Relevance to EACC Portfolio Projects |
| --- | --- | --- |
| 1 | Tog-Wajaale Urban Expansion Plan (Full Report) | Overall strategic framework and justification |
| 2 | Existing Situation Assessment | Topographic, climate, and infrastructure context |
| 3 | Population and Density Growth Trends | Population projections and project demand justification |
| 4 | Conceptual Development and Legal Framework | Strategic goals, implementation phases, legal compliance |
| 5 | Scenario Developments and Analysis | Selected scenario justification |
| 6 | Implementation Phases | Phase 1 alignment and activities |
| 7 | Project Poster (East Africa City Corridor Dialogue) | Concise project summary and investment case |
| 8 | Ethiopian Urban Expansion Initiative Overview | Policy context and partnership framework |
| 9 | Location and Area Data | Geographic and route context |
| 10 | Ethio-Berbera Corridor Trade and Logistics Data | Economic justification and regional significance |
| 11 | Sustainable Development Goals (SDGs) Alignment | International framework and financier attractiveness |
| 12 | Municipal Financial Data and Budget Context | Municipal capacity and financing gap justification |
| 13 | Legal and Regulatory Framework Summary | Compliance requirements and risk management |
| 14 | Key Infrastructure and Service Gaps | Project need and scope justification |
| 15 | Project Implementation Partners and Stakeholders | Engagement and partnership framework |
| 16 | Project Monitoring and Evaluation Framework | Performance indicators and reporting |

End of Appendix B

# APPENDIX C: DETAILED COST ESTIMATES (UPDATED)

- Introduction

- Total Portfolio Cost Summary

- Priority 01: Planned Urban Expansion Programme

- Priority 02: Corridor & Arterial Road Upgrade

- Priority 03: Inland Special Trade Zone & Logistics Hub

- Priority 04: Solid Waste Management System

- Priority 05: Youth Skills, Enterprise & Migration Centre

- Priority 06: Reception & Reintegration Centre

- Annual Cost Distribution

- Contingency and Price Escalation

- Operations and Maintenance Costs

- Land Acquisition Costs

- Financing Costs

- Comparative Benchmarks

- Cost Reduction and Optimization Opportunities

- Cost Estimate Refinement Plan

- Cost Summary by Category

- Sensitivity Analysis

- Recommendations for Cost Management

## 1. INTRODUCTION

## 1.1 Purpose

This appendix presents detailed cost estimates for the Tog-Wajaale EACC Priority Investment Project comprising six strategic infrastructure and development projects. These estimates are based on available data from the Tog-Wajaale Urban Expansion Plan (TWUEP), regional infrastructure benchmarks, comparable projects in East Africa, and the project posters presented at the East Africa City Corridor Dialogue.

## 1.2 Key Assumptions

| No. | Assumption | Source/Basis |
| --- | --- | --- |
| 1 | Exchange Rate: 1 USD = 160.0319 Birr | National Bank of Ethiopia, August 2026 |
| 2 | Base Year: 2026 | Current year |
| 3 | Implementation Period: 2025-2035 | Urban Expansion Plan and EACC project posters |
| 4 | Concession Period: 20-25 years | Industry standard for PPP |
| 5 | Inflation Rate: 5% annually | Historical trend in Ethiopia |
| 6 | Discount Rate: 8-12% | Industry standard for infrastructure |
| 7 | Contingency: 10-15% | Standard for preliminary estimates |
| 8 | Cost Basis: All costs are capital costs | Excludes financing costs |

## 1.3 Currency Conversion

All amounts are presented in both US Dollars (USD) and Ethiopian Birr (ETB/Birr) using the exchange rate:

1 USD = 160.0319 Birr

## 2. TOTAL PORTFOLIO COST SUMMARY

## 2.1 Summary by Priority

| Priority | Project | Cost (USD) | Cost (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| 01 | Planned Urban Expansion Programme | 63,000,000 | 10,082,009,700 | 16.6% |
| 02 | Corridor & Arterial Road Upgrade | 40,000,000 | 6,401,276,000 | 10.5% |
| 03 | Inland Special Trade Zone & Logistics Hub | 250,000,000 | 40,007,975,000 | 65.8% |
| 04 | Solid Waste Management System | 10,000,000 | 1,600,319,000 | 2.6% |
| 05 | Youth Skills, Enterprise & Migration Centre | 10,000,000 | 1,600,319,000 | 2.6% |
| 06 | Reception & Reintegration Centre | 7,000,000 | 1,120,223,300 | 1.9% |
| TOTAL |  | 380,000,000 | 60,812,122,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 2.2 Summary by Classification

| Classification | Projects | Investment (USD) | Investment (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| Foundation | Priority 01 | 63,000,000 | 10,082,009,700 | 16.6% |
| Connectivity | Priority 02 | 40,000,000 | 6,401,276,000 | 10.5% |
| Economic Engine | Priority 03 | 250,000,000 | 40,007,975,000 | 65.8% |
| Livability | Priority 04 | 10,000,000 | 1,600,319,000 | 2.6% |
| Human Capital | Priority 05 | 10,000,000 | 1,600,319,000 | 2.6% |
| Social Protection | Priority 06 | 7,000,000 | 1,120,223,300 | 1.9% |
| TOTAL |  | 380,000,000 | 60,812,122,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 3. PRIORITY 01: PLANNED URBAN EXPANSION PROGRAMME

## 3.1 Project Cost Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| Planned Residential & Mixed-Use Zones | New housing and mixed-use developments | 20,000,000 | 3,200,638,000 | 31.7% |
| Water Supply & Sanitation Systems | Expansion of water and sanitation | 15,000,000 | 2,400,478,500 | 23.8% |
| Public Services & Social Infrastructure | Schools, health centres, and services | 10,000,000 | 1,600,319,000 | 15.9% |
| Green Spaces & Urban Parks | Parks and recreational areas | 8,000,000 | 1,280,255,200 | 12.7% |
| Land Readjustment & City Planning | Land management and urban planning | 10,000,000 | 1,600,319,000 | 15.9% |
| TOTAL |  | 63,000,000 | 10,082,009,700 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 3.2 Component Details

1. Planned Residential & Mixed-Use Zones (USD 20,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Residential Zone Development | 12,000,000 | 1,920,382,800 | 240,000 | 38,407,656 | 50 ha |
| Mixed-Use Zone Development | 5,000,000 | 800,159,500 | 250,000 | 40,007,975 | 20 ha |
| Affordable Housing Provision | 3,000,000 | 480,095,700 | 60,000 | 9,601,914 | 50 units |
| TOTAL | 20,000,000 | 3,200,638,000 | - | - | - |

2. Water Supply & Sanitation Systems (USD 15,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Water Distribution Network | 6,000,000 | 960,191,400 | 120,000 | 19,203,828 | 50 km |
| Water Treatment | 3,000,000 | 480,095,700 | 150,000 | 24,004,785 | 20 MLD |
| Sewerage System | 4,000,000 | 640,127,600 | 80,000 | 12,802,552 | 50 km |
| Stormwater Drainage | 2,000,000 | 320,063,800 | 40,000 | 6,401,276 | 50 km |
| TOTAL | 15,000,000 | 2,400,478,500 | - | - | - |

3. Public Services & Social Infrastructure (USD 10,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Schools | 4,000,000 | 640,127,600 | 2,000,000 | 320,063,800 | 2 schools |
| Health Centres | 3,000,000 | 480,095,700 | 1,500,000 | 240,047,850 | 2 centres |
| Community Centres | 2,000,000 | 320,063,800 | 500,000 | 80,015,950 | 4 centres |
| Public Facilities | 1,000,000 | 160,031,900 | 250,000 | 40,007,975 | 4 facilities |
| TOTAL | 10,000,000 | 1,600,319,000 | - | - | - |

4. Green Spaces & Urban Parks (USD 8,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Urban Parks | 5,000,000 | 800,159,500 | 250,000 | 40,007,975 | 20 ha |
| Green Corridors | 2,000,000 | 320,063,800 | 100,000 | 16,003,190 | 20 km |
| Community Gardens | 1,000,000 | 160,031,900 | 50,000 | 8,001,595 | 20 sites |
| TOTAL | 8,000,000 | 1,280,255,200 | - | - | - |

5. Land Readjustment & City Planning (USD 10,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Land Readjustment | 5,000,000 | 800,159,500 | Fair and transparent land management |
| City Planning | 2,000,000 | 320,063,800 | Urban planning and zoning |
| GIS and Mapping | 2,000,000 | 320,063,800 | Spatial data and mapping |
| Regulatory Framework | 1,000,000 | 160,031,900 | Urban planning regulations |
| TOTAL | 10,000,000 | 1,600,319,000 | - |

## 4. PRIORITY 02: CORRIDOR & ARTERIAL ROAD UPGRADE

## 4.1 Project Cost Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| Arterial Road Development | Construction and upgrade of 20 km priority roads | 20,000,000 | 3,200,638,000 | 50.0% |
| Drainage & Stormwater Systems | Comprehensive drainage infrastructure | 6,000,000 | 960,191,400 | 15.0% |
| Sidewalks & Pedestrian Facilities | Safe pedestrian infrastructure | 5,000,000 | 800,159,500 | 12.5% |
| Street Lighting & Traffic Safety | Lighting, signage, and safety features | 5,000,000 | 800,159,500 | 12.5% |
| Landscaping & Green Buffers | Green infrastructure and environmental integration | 4,000,000 | 640,127,600 | 10.0% |
| TOTAL |  | 40,000,000 | 6,401,276,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 4.2 Component Details

1. Arterial Road Development (USD 20,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Road Construction | 12,000,000 | 1,920,382,800 | 600,000 | 96,019,140 | 20 km |
| Pavement Design | 4,000,000 | 640,127,600 | 200,000 | 32,006,380 | 20 km |
| Geometric Design | 2,000,000 | 320,063,800 | 100,000 | 16,003,190 | 20 km |
| Intersection Improvements | 2,000,000 | 320,063,800 | 500,000 | 80,015,950 | 4 intersections |
| TOTAL | 20,000,000 | 3,200,638,000 | - | - | - |

2. Drainage & Stormwater Systems (USD 6,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Stormwater Drainage | 3,500,000 | 560,111,650 | 175,000 | 28,005,583 | 20 km |
| Culverts & Crossings | 1,500,000 | 240,047,850 | 75,000 | 12,002,393 | 20 km |
| Flood Protection | 1,000,000 | 160,031,900 | 50,000 | 8,001,595 | 20 km |
| TOTAL | 6,000,000 | 960,191,400 | - | - | - |

3. Sidewalks & Pedestrian Facilities (USD 5,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Pedestrian Walkways | 2,500,000 | 400,079,750 | 125,000 | 20,003,988 | 20 km |
| Crossings | 1,000,000 | 160,031,900 | 50,000 | 8,001,595 | 20 locations |
| Accessibility Features | 1,000,000 | 160,031,900 | 50,000 | 8,001,595 | 20 km |
| Shaded Walkways | 500,000 | 80,015,950 | 25,000 | 4,000,798 | 20 km |
| TOTAL | 5,000,000 | 800,159,500 | - | - | - |

4. Street Lighting & Traffic Safety (USD 5,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Street Lighting | 2,000,000 | 320,063,800 | 100,000 | 16,003,190 | 20 km |
| Traffic Signs | 1,000,000 | 160,031,900 | 50,000 | 8,001,595 | 20 km |
| Road Markings | 1,000,000 | 160,031,900 | 50,000 | 8,001,595 | 20 km |
| Safety Barriers | 500,000 | 80,015,950 | 25,000 | 4,000,798 | 20 km |
| Traffic Signals | 500,000 | 80,015,950 | 125,000 | 20,003,988 | 4 intersections |
| TOTAL | 5,000,000 | 800,159,500 | - | - | - |

5. Landscaping & Green Buffers (USD 4,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Unit Cost (USD) | Unit Cost (Birr) | Quantity |
| --- | --- | --- | --- | --- | --- |
| Green Buffers | 2,000,000 | 320,063,800 | 100,000 | 16,003,190 | 20 km |
| Tree Planting | 1,000,000 | 160,031,900 | 50,000 | 8,001,595 | 20 km |
| Aesthetic Improvement | 500,000 | 80,015,950 | 25,000 | 4,000,798 | 20 km |
| Environmental Integration | 500,000 | 80,015,950 | 25,000 | 4,000,798 | 20 km |
| TOTAL | 4,000,000 | 640,127,600 | - | - | - |

## 5. PRIORITY 03: INLAND SPECIAL TRADE ZONE & LOGISTICS HUB

## 5.1 Project Cost Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| Dry Port & Logistics Hub | Container handling, customs clearance, logistics | 70,000,000 | 11,202,233,000 | 28.0% |
| Warehousing & Distribution Parks | Storage and distribution facilities | 50,000,000 | 8,001,595,000 | 20.0% |
| Industrial Parks & Manufacturing Zones | Production and processing facilities | 60,000,000 | 9,601,914,000 | 24.0% |
| Customs & Trade Facilitation | On-site customs clearance and trade services | 30,000,000 | 4,800,957,000 | 12.0% |
| Commercial & Business Services | Office space, retail, and support services | 20,000,000 | 3,200,638,000 | 8.0% |
| Supporting Utilities | Power, water, telecommunications | 20,000,000 | 3,200,638,000 | 8.0% |
| TOTAL |  | 250,000,000 | 40,007,975,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 5.2 Component Details

1. Dry Port & Logistics Hub (USD 70,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Container Handling | 20,000,000 | 3,200,638,000 | Container yard and handling equipment |
| Customs Clearance | 15,000,000 | 2,400,478,500 | On-site customs clearance facilities |
| Logistics Services | 15,000,000 | 2,400,478,500 | Logistics and freight forwarding services |
| Storage Facilities | 10,000,000 | 1,600,319,000 | General and specialized storage |
| Container Yard | 10,000,000 | 1,600,319,000 | Container storage and handling |
| TOTAL | 70,000,000 | 11,202,233,000 | - |

2. Warehousing & Distribution Parks (USD 50,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| General Warehousing | 25,000,000 | 4,000,797,500 | Standard warehousing facilities |
| Cold Storage | 15,000,000 | 2,400,478,500 | Temperature-controlled storage |
| Distribution Centre | 10,000,000 | 1,600,319,000 | Central distribution facilities |
| TOTAL | 50,000,000 | 8,001,595,000 | - |

3. Industrial Parks & Manufacturing Zones (USD 60,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Manufacturing Facilities | 25,000,000 | 4,000,797,500 | Production and assembly facilities |
| Agro-Processing | 15,000,000 | 2,400,478,500 | Agricultural processing facilities |
| Textile & Garment | 10,000,000 | 1,600,319,000 | Textile and garment production |
| Light Manufacturing | 10,000,000 | 1,600,319,000 | Light industrial facilities |
| TOTAL | 60,000,000 | 9,601,914,000 | - |

4. Customs & Trade Facilitation (USD 30,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Customs Facilities | 15,000,000 | 2,400,478,500 | Customs clearance offices |
| Trade Services | 8,000,000 | 1,280,255,200 | Trade facilitation services |
| Inspection Facilities | 5,000,000 | 800,159,500 | Quality control and inspection |
| Administration | 2,000,000 | 320,063,800 | FTZ management |
| TOTAL | 30,000,000 | 4,800,957,000 | - |

5. Commercial & Business Services (USD 20,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Office Buildings | 10,000,000 | 1,600,319,000 | Business and administrative offices |
| Retail Spaces | 5,000,000 | 800,159,500 | Commercial and retail areas |
| Banking Services | 3,000,000 | 480,095,700 | Financial services |
| Business Support | 2,000,000 | 320,063,800 | Business advisory and support |
| TOTAL | 20,000,000 | 3,200,638,000 | - |

6. Supporting Utilities (USD 20,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Power Supply | 8,000,000 | 1,280,255,200 | Reliable electricity supply |
| Water Supply | 5,000,000 | 800,159,500 | Clean water for industrial use |
| Telecommunications | 4,000,000 | 640,127,600 | High-speed connectivity |
| Waste Management | 3,000,000 | 480,095,700 | Industrial waste management |
| TOTAL | 20,000,000 | 3,200,638,000 | - |

## 6. PRIORITY 04: SOLID WASTE MANAGEMENT SYSTEM

## 6.1 Project Cost Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| Engineered Landfill Disposal Site | Sanitary landfill with environmental controls | 3,000,000 | 480,095,700 | 30.0% |
| Transfer Stations | Network of collection points across the city | 2,000,000 | 320,063,800 | 20.0% |
| Collection Fleet & Equipment | Modern waste collection vehicles and equipment | 2,500,000 | 400,079,750 | 25.0% |
| Waste Segregation & Recycling Centre | Sorting, processing, and recycling facilities | 1,500,000 | 240,047,850 | 15.0% |
| Community Awareness & Capacity Building | Public education and training programmes | 1,000,000 | 160,031,900 | 10.0% |
| TOTAL |  | 10,000,000 | 1,600,319,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 6.2 Component Details

1. Engineered Landfill Disposal Site (USD 3,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Site Development | 800,000 | 128,025,520 | Site clearing and preparation |
| Liner System | 600,000 | 96,019,140 | HDPE liner + clay |
| Leachate Management | 500,000 | 80,015,950 | Collection and treatment |
| Gas Management | 400,000 | 64,012,760 | Methane collection and flaring |
| Cover System | 300,000 | 48,009,570 | Daily and final cover |
| Access Roads | 200,000 | 32,006,380 | All-weather access |
| Fencing | 100,000 | 16,003,190 | Security and control |
| Site Office | 100,000 | 16,003,190 | Administrative and control facilities |
| TOTAL | 3,000,000 | 480,095,700 | - |

2. Transfer Stations (USD 2,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Station Development | 1,000,000 | 160,031,900 | 3-5 stations |
| Waste Transfer Equipment | 500,000 | 80,015,950 | Compaction and transfer |
| Environmental Controls | 300,000 | 48,009,570 | Odour control |
| Access | 200,000 | 32,006,380 | All-weather access |
| TOTAL | 2,000,000 | 320,063,800 | - |

3. Collection Fleet & Equipment (USD 2,500,000)

| Sub-Component | Quantity | Unit Cost (USD) | Unit Cost (Birr)* | Total Cost (USD) | Total Cost (Birr)* |
| --- | --- | --- | --- | --- | --- |
| Compactor Trucks | 5 | 200,000 | 32,006,380 | 1,000,000 | 160,031,900 |
| Collection Vehicles | 10 | 80,000 | 12,802,552 | 800,000 | 128,025,520 |
| Sweeping Equipment | 2 | 150,000 | 24,004,785 | 300,000 | 48,009,570 |
| Containers & Bins | 200 | 2,000 | 320,064 | 400,000 | 64,012,760 |
| TOTAL | - | - | - | 2,500,000 | 400,079,750 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

4. Waste Segregation & Recycling Centre (USD 1,500,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Segregation Line | 500,000 | 80,015,950 | Manual and mechanical sorting |
| Recycling Facilities | 400,000 | 64,012,760 | Processing of recyclable materials |
| Composting Facility | 300,000 | 48,009,570 | Organic waste composting |
| Storage Area | 200,000 | 32,006,380 | Storage for recyclable materials |
| Administration | 100,000 | 16,003,190 | Office and management facilities |
| TOTAL | 1,500,000 | 240,047,850 | - |

5. Community Awareness & Capacity Building (USD 1,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Public Education | 300,000 | 48,009,570 | Awareness campaigns |
| Behaviour Change | 200,000 | 32,006,380 | Segregation and recycling promotion |
| Training | 200,000 | 32,006,380 | Worker training |
| School Programmes | 150,000 | 24,004,785 | Environmental education |
| Community Engagement | 100,000 | 16,003,190 | Community participation |
| Monitoring | 50,000 | 8,001,595 | Programme effectiveness |
| TOTAL | 1,000,000 | 160,031,900 | - |

## 7. PRIORITY 05: YOUTH SKILLS, ENTERPRISE & MIGRATION CENTRE

## 7.1 Project Cost Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| Skills Training Facilities | Vocational and technical training centre | 3,000,000 | 480,095,700 | 30.0% |
| Entrepreneurship Incubation Centre | Business incubation and support | 2,500,000 | 400,079,750 | 25.0% |
| Digital & Career Development Labs | Digital skills and career guidance | 2,000,000 | 320,063,800 | 20.0% |
| Job Placement & Migration Services | Employment and migration guidance | 1,500,000 | 240,047,850 | 15.0% |
| Business Support & Mentoring | Mentorship and business advisory | 1,000,000 | 160,031,900 | 10.0% |
| TOTAL |  | 10,000,000 | 1,600,319,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 7.2 Component Details

1. Skills Training Facilities (USD 3,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Building Construction | 1,500,000 | 240,047,850 | Vocational training centre |
| Workshops | 800,000 | 128,025,520 | Practical training workshops |
| Classrooms | 400,000 | 64,012,760 | Theory and classroom spaces |
| Equipment | 300,000 | 48,009,570 | Training equipment and tools |
| TOTAL | 3,000,000 | 480,095,700 | - |

2. Entrepreneurship Incubation Centre (USD 2,500,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Incubation Spaces | 1,000,000 | 160,031,900 | Co-working and incubation spaces |
| Business Advisory | 500,000 | 80,015,950 | Business planning and advisory |
| Access to Finance | 400,000 | 64,012,760 | Linkages to microfinance |
| Networking | 300,000 | 48,009,570 | Business networking |
| Digital Support | 300,000 | 48,009,570 | E-commerce and digital marketing |
| TOTAL | 2,500,000 | 400,079,750 | - |

3. Digital & Career Development Labs (USD 2,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Digital Skills Training | 800,000 | 128,025,520 | ICT and digital literacy |
| Career Counselling | 400,000 | 64,012,760 | Career guidance services |
| Job Readiness | 300,000 | 48,009,570 | CV writing and interview skills |
| Online Learning | 300,000 | 48,009,570 | Online learning platforms |
| Career Resources | 200,000 | 32,006,380 | Labour market information |
| TOTAL | 2,000,000 | 320,063,800 | - |

4. Job Placement & Migration Services (USD 1,500,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Job Placement | 600,000 | 96,019,140 | Linkages with employers |
| Migration Information | 300,000 | 48,009,570 | Safe migration information |
| Skills Profiling | 200,000 | 32,006,380 | Skills assessment |
| Labour Market Information | 200,000 | 32,006,380 | Labour market intelligence |
| Pre-Departure Orientation | 200,000 | 32,006,380 | Safe migration workshops |
| TOTAL | 1,500,000 | 240,047,850 | - |

5. Business Support & Mentoring (USD 1,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Mentorship Programme | 300,000 | 48,009,570 | Experienced business mentors |
| Business Development | 250,000 | 40,007,975 | Business development services |
| Market Linkages | 200,000 | 32,006,380 | Market access and linkages |
| Post-Startup Support | 150,000 | 24,004,785 | Ongoing support for startups |
| Peer Learning | 100,000 | 16,003,190 | Business forums and events |
| TOTAL | 1,000,000 | 160,031,900 | - |

## 8. PRIORITY 06: RECEPTION & REINTEGRATION CENTRE

## 8.1 Project Cost Breakdown

| Component | Description | Estimated Cost (USD) | Estimated Cost (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| Reception & Accommodation Facilities | Welcome centre and temporary accommodation | 2,000,000 | 320,063,800 | 28.6% |
| Counselling & Psychosocial Support | Mental health and psychosocial services | 1,500,000 | 240,047,850 | 21.4% |
| Skills Training & Livelihood Programmes | Vocational training and livelihood support | 1,500,000 | 240,047,850 | 21.4% |
| Reintegration Grants & Business Support | Grants and business development support | 1,000,000 | 160,031,900 | 14.3% |
| Monitoring, Follow-up & Case Management | Ongoing support and case management | 1,000,000 | 160,031,900 | 14.3% |
| TOTAL |  | 7,000,000 | 1,120,223,300 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 8.2 Component Details

1. Reception & Accommodation Facilities (USD 2,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Reception Centre | 600,000 | 96,019,140 | Welcoming and registration |
| Temporary Accommodation | 600,000 | 96,019,140 | 50+ beds capacity |
| Basic Amenities | 400,000 | 64,012,760 | WASH facilities |
| Medical Check-up | 200,000 | 32,006,380 | Medical examination room |
| Nutrition Support | 200,000 | 32,006,380 | Kitchen and dining area |
| TOTAL | 2,000,000 | 320,063,800 | - |

2. Counselling & Psychosocial Support (USD 1,500,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Individual Counselling | 500,000 | 80,015,950 | One-on-one counselling |
| Group Counselling | 300,000 | 48,009,570 | Group therapy |
| Psychosocial Support | 300,000 | 48,009,570 | MHPSS programming |
| Trauma Support | 200,000 | 32,006,380 | Trauma-informed care |
| Crisis Intervention | 200,000 | 32,006,380 | 24/7 support |
| TOTAL | 1,500,000 | 240,047,850 | - |

3. Skills Training & Livelihood Programmes (USD 1,500,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Vocational Training | 600,000 | 96,019,140 | Market-aligned skills |
| Livelihood Support | 300,000 | 48,009,570 | Income-generating activities |
| Agriculture Support | 200,000 | 32,006,380 | Farming and livestock |
| Digital Skills | 200,000 | 32,006,380 | Digital literacy |
| Life Skills | 200,000 | 32,006,380 | Life skills training |
| TOTAL | 1,500,000 | 240,047,850 | - |

4. Reintegration Grants & Business Support (USD 1,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Reintegration Grants | 400,000 | 64,012,760 | Financial support |
| Business Support | 200,000 | 32,006,380 | Business planning |
| Access to Finance | 150,000 | 24,004,785 | Linkages to microfinance |
| Market Linkages | 150,000 | 24,004,785 | Market access |
| Startup Kits | 100,000 | 16,003,190 | Equipment and materials |
| TOTAL | 1,000,000 | 160,031,900 | - |

5. Monitoring, Follow-up & Case Management (USD 1,000,000)

| Sub-Component | Cost (USD) | Cost (Birr)* | Description |
| --- | --- | --- | --- |
| Case Management | 400,000 | 64,012,760 | Personalized support |
| Follow-up | 200,000 | 32,006,380 | 12-month follow-up |
| Documentation | 150,000 | 24,004,785 | Electronic case management |
| Referral Pathways | 150,000 | 24,004,785 | Comprehensive referrals |
| Outcome Monitoring | 100,000 | 16,003,190 | Outcome tracking |
| TOTAL | 1,000,000 | 160,031,900 | - |

## 9. ANNUAL COST DISTRIBUTION

## 9.1 Phased Implementation Costs (2024-2035)

| Year | Estimated Cost (USD) | Estimated Cost (Birr)* | Activities |
| --- | --- | --- | --- |
| 2024 | 5,000,000 | 800,159,500 | Project preparation, feasibility studies |
| 2025 | 20,000,000 | 3,200,638,000 | Feasibility, design, planning |
| 2026 | 30,000,000 | 4,800,957,000 | Detailed design, procurement, land acquisition |
| 2027 | 40,000,000 | 6,401,276,000 | Construction commencement |
| 2028 | 60,000,000 | 9,601,914,000 | Construction peak |
| 2029 | 65,000,000 | 10,402,073,500 | Construction completion |
| 2030 | 60,000,000 | 9,601,914,000 | Commissioning, operational start |
| 2031 | 40,000,000 | 6,401,276,000 | FTZ Phase 2 commencement |
| 2032 | 35,000,000 | 5,601,116,500 | FTZ Phase 2 construction |
| 2033 | 25,000,000 | 4,000,797,500 | FTZ Phase 2 construction |
| 2034 | 15,000,000 | 2,400,478,500 | FTZ Phase 2 completion |
| 2035 | 5,000,000 | 800,159,500 | Final completion |
| TOTAL | 380,000,000 | 60,812,122,000 | - |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 9.2 Cost Distribution by Year

| Year | Cost (USD) | Cost (Birr)* | Percentage of Total |
| --- | --- | --- | --- |
| 2024 | 5,000,000 | 800,159,500 | 1.3% |
| 2025 | 20,000,000 | 3,200,638,000 | 5.3% |
| 2026 | 30,000,000 | 4,800,957,000 | 7.9% |
| 2027 | 40,000,000 | 6,401,276,000 | 10.5% |
| 2028 | 60,000,000 | 9,601,914,000 | 15.8% |
| 2029 | 65,000,000 | 10,402,073,500 | 17.1% |
| 2030 | 60,000,000 | 9,601,914,000 | 15.8% |
| 2031 | 40,000,000 | 6,401,276,000 | 10.5% |
| 2032 | 35,000,000 | 5,601,116,500 | 9.2% |
| 2033 | 25,000,000 | 4,000,797,500 | 6.6% |
| 2034 | 15,000,000 | 2,400,478,500 | 3.9% |
| 2035 | 5,000,000 | 800,159,500 | 1.3% |
| TOTAL | 380,000,000 | 60,812,122,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 10. CONTINGENCY AND PRICE ESCALATION

## 10.1 Contingency Allowance

| Component | Base Cost (USD) | Base Cost (Birr)* | Contingency (%) | Contingency (USD) | Contingency (Birr)* |
| --- | --- | --- | --- | --- | --- |
| Priority 01: Urban Expansion | 63,000,000 | 10,082,009,700 | 10-15% | 6,300,000 - 9,450,000 | 1,008,200,970 - 1,512,301,455 |
| Priority 02: Corridor Roads | 40,000,000 | 6,401,276,000 | 10-15% | 4,000,000 - 6,000,000 | 640,127,600 - 960,191,400 |
| Priority 03: FTZ & Logistics | 250,000,000 | 40,007,975,000 | 10-15% | 25,000,000 - 37,500,000 | 4,000,797,500 - 6,001,196,250 |
| Priority 04: Solid Waste | 10,000,000 | 1,600,319,000 | 10-15% | 1,000,000 - 1,500,000 | 160,031,900 - 240,047,850 |
| Priority 05: Youth Centre | 10,000,000 | 1,600,319,000 | 5-10% | 500,000 - 1,000,000 | 80,015,950 - 160,031,900 |
| Priority 06: Reception Centre | 7,000,000 | 1,120,223,300 | 5-10% | 350,000 - 700,000 | 56,011,165 - 112,022,330 |
| TOTAL | 380,000,000 | 60,812,122,000 | 10-15% | 37,150,000 - 56,150,000 | 5,945,185,085 - 8,985,791,185 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 10.2 Recommended Contingency

| Recommendation | Contingency (%) | Contingency (USD) | Contingency (Birr)* |
| --- | --- | --- | --- |
| Minimum | 10% | 38,000,000 | 6,081,212,200 |
| Recommended | 15% | 57,000,000 | 9,121,818,300 |
| Maximum | 20% | 76,000,000 | 12,162,424,400 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 10.3 Price Escalation

| Year | Estimated Inflation (%) | Cumulative Factor | Base Cost with Escalation (USD) | Base Cost with Escalation (Birr)* |
| --- | --- | --- | --- | --- |
| 2024 | 5% | 1.00 | 5,000,000 | 800,159,500 |
| 2025 | 5% | 1.05 | 21,000,000 | 3,360,669,900 |
| 2026 | 5% | 1.10 | 33,000,000 | 5,281,052,700 |
| 2027 | 5% | 1.16 | 46,400,000 | 7,425,480,160 |
| 2028 | 5% | 1.22 | 73,200,000 | 11,714,335,080 |
| 2029 | 5% | 1.28 | 83,200,000 | 13,314,654,080 |
| 2030 | 5% | 1.34 | 80,400,000 | 12,866,564,760 |
| 2031 | 5% | 1.41 | 56,400,000 | 9,025,799,160 |
| 2032 | 5% | 1.48 | 51,800,000 | 8,289,652,420 |
| 2033 | 5% | 1.55 | 38,750,000 | 6,201,236,125 |
| 2034 | 5% | 1.63 | 24,450,000 | 3,912,779,805 |
| 2035 | 5% | 1.71 | 8,550,000 | 1,368,272,745 |
| TOTAL | - | - | 522,150,000 | 83,561,296,885 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 11. OPERATIONS AND MAINTENANCE COSTS

## 11.1 Annual O&M Cost Estimates (Post-Commissioning)

| Priority | Project | Annual O&M (USD) | Annual O&M (Birr)* | Percentage |
| --- | --- | --- | --- | --- |
| 01 | Urban Expansion | 2,000,000 | 320,063,800 | 20.0% |
| 02 | Corridor Roads | 1,500,000 | 240,047,850 | 15.0% |
| 03 | FTZ & Logistics | 3,000,000 | 480,095,700 | 30.0% |
| 04 | Solid Waste | 1,500,000 | 240,047,850 | 15.0% |
| 05 | Youth Centre | 1,000,000 | 160,031,900 | 10.0% |
| 06 | Reception Centre | 1,000,000 | 160,031,900 | 10.0% |
| TOTAL |  | 10,000,000 | 1,600,319,000 | 100.0% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 11.2 O&M Cost Projection (2030-2055)

| Period | Annual O&M (USD) | Annual O&M (Birr)* | Total O&M (USD) | Total O&M (Birr)* |
| --- | --- | --- | --- | --- |
| 2030-2035 (Years 1-5) | 10,000,000 | 1,600,319,000 | 50,000,000 | 8,001,595,000 |
| 2036-2040 (Years 6-10) | 12,000,000 | 1,920,382,800 | 60,000,000 | 9,601,914,000 |
| 2041-2045 (Years 11-15) | 14,500,000 | 2,320,462,550 | 72,500,000 | 11,602,312,750 |
| 2046-2050 (Years 16-20) | 17,500,000 | 2,800,558,250 | 87,500,000 | 14,002,791,250 |
| 2051-2055 (Years 21-25) | 21,000,000 | 3,360,669,900 | 105,000,000 | 16,803,349,500 |
| TOTAL | - | - | 375,000,000 | 60,011,962,500 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 12. LAND ACQUISITION COSTS

## 12.1 Estimated Land Acquisition Cost

| Priority | Project | Estimated Area (ha) | Unit Cost (USD/ha) | Unit Cost (Birr/ha)* | Total Cost (USD) | Total Cost (Birr)* |
| --- | --- | --- | --- | --- | --- | --- |
| 01 | Urban Expansion | 100 | 50,000 | 8,001,595 | 5,000,000 | 800,159,500 |
| 02 | Corridor Roads | 50 | 50,000 | 8,001,595 | 2,500,000 | 400,079,750 |
| 03 | FTZ & Logistics | 50 | 50,000 | 8,001,595 | 2,500,000 | 400,079,750 |
| 04 | Solid Waste | 10 | 30,000 | 4,800,957 | 300,000 | 48,009,570 |
| 05 | Youth Centre | 2 | 30,000 | 4,800,957 | 60,000 | 9,601,914 |
| 06 | Reception Centre | 2 | 30,000 | 4,800,957 | 60,000 | 9,601,914 |
| TOTAL |  | 214 | - | - | 10,420,000 | 1,667,532,398 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 12.2 Land Acquisition Assumptions

| Assumption | Description |
| --- | --- |
| Right-of-Way | 50m for corridor (BRT + road) |
| Unit Costs | Based on local land values in Somali Region |
| Compensation | Fair market value plus relocation costs |
| Process | Transparent and participatory approach |
| Timeline | 12-18 months for full acquisition |
| Contingency | 20-30% additional for unforeseen costs |

## 13. FINANCING COSTS

## 13.1 Financing Structure (Illustrative)

| Financing Source | Amount (USD) | Amount (Birr)* | Term (Years) | Interest Rate (%) | Annual Debt Service (USD) | Annual Debt Service (Birr)* |
| --- | --- | --- | --- | --- | --- | --- |
| Concessional Loans | 150,000,000 | 24,004,785,000 | 20 | 2-5% | 9,000,000 - 15,000,000 | 1,440,287,100 - 2,400,478,500 |
| Private Investment | 120,000,000 | 19,203,828,000 | 15 | 8-10% | 14,000,000 - 17,000,000 | 2,240,446,600 - 2,720,542,300 |
| Grants | 80,000,000 | 12,802,552,000 | - | 0% | - | - |
| Government | 30,000,000 | 4,800,957,000 | 10 | 3-5% | 1,800,000 - 3,000,000 | 288,057,420 - 480,095,700 |
| TOTAL | 380,000,000 | 60,812,122,000 | - | - | 24,800,000 - 35,000,000 | 3,968,791,120 - 5,601,116,500 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 13.2 Financing Cost Summary

| Element | Amount (USD) | Amount (Birr)* |
| --- | --- | --- |
| Total Project Cost | 380,000,000 | 60,812,122,000 |
| Interest During Construction | 15,000,000 - 25,000,000 | 2,400,478,500 - 4,000,797,500 |
| Financing Fees | 5,000,000 - 10,000,000 | 800,159,500 - 1,600,319,000 |
| TOTAL FINANCING COST | 400,000,000 - 415,000,000 | 64,012,760,000 - 66,413,238,500 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 14. COMPARATIVE BENCHMARKS

## 14.1 Benchmark Costs

| Project Type | Location | Cost (USD) | Cost (Birr)* | Year |
| --- | --- | --- | --- | --- |
| Urban Expansion (per ha) | Ethiopia | 100,000 - 200,000 | 16,003,190 - 32,006,380 | 2024 |
| Arterial Road (per km) | Ethiopia | 800,000 - 1,200,000 | 128,025,520 - 192,038,280 | 2024 |
| BRT (per km) | East Africa | 2,500,000 - 3,000,000 | 400,079,750 - 480,095,700 | 2024 |
| Industrial Park (per ha) | Ethiopia | 500,000 - 1,000,000 | 80,015,950 - 160,031,900 | 2024 |
| Solid Waste (per city) | East Africa | 5,000,000 - 15,000,000 | 800,159,500 - 2,400,478,500 | 2024 |
| Youth Centre | Ethiopia | 5,000,000 - 10,000,000 | 800,159,500 - 1,600,319,000 | 2024 |
| Reception Centre | Ethiopia | 3,000,000 - 7,000,000 | 480,095,700 - 1,120,223,300 | 2024 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 14.2 Benchmark Analysis

| Element | Benchmark (USD) | Benchmark (Birr)* | Project Cost (USD) | Project Cost (Birr)* | Variance |
| --- | --- | --- | --- | --- | --- |
| Urban Expansion (per ha) | 100,000 - 200,000 | 16,003,190 - 32,006,380 | 160,000 | 25,605,104 | Within range |
| Arterial Road (per km) | 800,000 - 1,200,000 | 128,025,520 - 192,038,280 | 1,000,000 | 160,031,900 | Within range |
| Industrial Park (per ha) | 500,000 - 1,000,000 | 80,015,950 - 160,031,900 | 1,000,000 | 160,031,900 | Upper range |
| Solid Waste | 5,000,000 - 15,000,000 | 800,159,500 - 2,400,478,500 | 10,000,000 | 1,600,319,000 | Within range |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 15. COST REDUCTION AND OPTIMIZATION OPPORTUNITIES

| Opportunity | Potential Savings (USD) | Potential Savings (Birr)* | Description |
| --- | --- | --- | --- |
| Phased Implementation | 15,000,000 - 30,000,000 | 2,400,478,500 - 4,800,957,000 | Staged construction to optimize cash flow |
| Value Engineering | 20,000,000 - 40,000,000 | 3,200,638,000 - 6,401,276,000 | Alternative designs and materials |
| Local Materials | 10,000,000 - 20,000,000 | 1,600,319,000 - 3,200,638,000 | Use of locally available materials |
| Community Contribution | 5,000,000 - 10,000,000 | 800,159,500 - 1,600,319,000 | Community involvement in NMT infrastructure |
| PPP Efficiency | 15,000,000 - 30,000,000 | 2,400,478,500 - 4,800,957,000 | Private sector efficiencies |
| TOTAL POTENTIAL | 65,000,000 - 130,000,000 | 10,402,073,500 - 20,804,147,000 | - |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 16. COST ESTIMATE REFINEMENT PLAN

## 16.1 Feasibility Study Cost Refinement

| Activity | Timeline | Responsible Party | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- | --- |
| Detailed Quantity Survey | 1-2 months | Consultant | 200,000 | 32,006,380 |
| Unit Cost Validation | 1 month | Consultant | 100,000 | 16,003,190 |
| Supply Chain Assessment | 1 month | Consultant | 150,000 | 24,004,785 |
| Labor Cost Assessment | 1 month | Consultant | 100,000 | 16,003,190 |
| Contingency Analysis | 1 month | Consultant | 150,000 | 24,004,785 |
| Sensitivity Analysis | 1 month | Consultant | 100,000 | 16,003,190 |
| Final Cost Estimate | 1 month | Consultant | 200,000 | 32,006,380 |
| TOTAL | 6-8 months | - | 1,000,000 | 160,031,900 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 16.2 Refinement Activities

| Activity | Description | Expected Output |
| --- | --- | --- |
| Detailed Design | Engineering design and specifications | Accurate quantities |
| Market Survey | Material and labor costs | Realistic unit costs |
| Risk Assessment | Identification of cost risks | Appropriate contingencies |
| Value Engineering | Cost optimization | Reduced costs |
| Financier Review | Review by potential financiers | Cost validation |

## 17. COST SUMMARY BY CATEGORY

## 17.1 Capital Costs (USD)

| Category | Estimated Cost (USD) | Percentage |
| --- | --- | --- |
| Construction Costs | 340,000,000 | 89.5% |
| - Priority 01: Urban Expansion | 53,000,000 | 13.9% |
| - Priority 02: Corridor Roads | 36,000,000 | 9.5% |
| - Priority 03: FTZ & Logistics | 225,000,000 | 59.2% |
| - Priority 04: Solid Waste | 8,500,000 | 2.2% |
| - Priority 05: Youth Centre | 9,000,000 | 2.4% |
| - Priority 06: Reception Centre | 6,500,000 | 1.7% |
| Professional Services | 6,500,000 | 1.7% |
| Land Acquisition | 10,420,000 | 2.7% |
| Project Management | 6,600,000 | 1.7% |
| Contingency | 57,000,000 | 15.0% |
| TOTAL | 420,520,000 | 110.6% |

## 17.2 Capital Costs (Birr)*

| Category | Estimated Cost (Birr) | Percentage |
| --- | --- | --- |
| Construction Costs | 54,410,846,000 | 89.5% |
| - Priority 01: Urban Expansion | 8,481,690,700 | 13.9% |
| - Priority 02: Corridor Roads | 5,761,148,400 | 9.5% |
| - Priority 03: FTZ & Logistics | 36,007,177,500 | 59.2% |
| - Priority 04: Solid Waste | 1,360,271,150 | 2.2% |
| - Priority 05: Youth Centre | 1,440,287,100 | 2.4% |
| - Priority 06: Reception Centre | 1,040,207,350 | 1.7% |
| Professional Services | 1,040,207,350 | 1.7% |
| Land Acquisition | 1,667,532,398 | 2.7% |
| Project Management | 1,056,210,540 | 1.7% |
| Contingency | 9,121,818,300 | 15.0% |
| TOTAL | 67,296,614,588 | 110.6% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 18. SENSITIVITY ANALYSIS

## 18.1 Key Variables

| Variable | Base Case | Sensitivity Range |
| --- | --- | --- |
| Exchange Rate | 160.0319 Birr/USD | 140 - 180 Birr/USD |
| Inflation Rate | 5% | 3% - 8% |
| Construction Cost | Base | +/- 15% |
| Interest Rate | 5-8% | +/- 2% |
| Revenue | Base | +/- 20% |

## 18.2 Sensitivity Analysis Results

| Scenario | Change | Total Cost (USD) | Total Cost (Birr)* | Variance |
| --- | --- | --- | --- | --- |
| Base Case | - | 380,000,000 | 60,812,122,000 | - |
| Exchange Rate +10% | Birr depreciates | 380,000,000 | 66,893,334,200 | +10% |
| Exchange Rate -10% | Birr appreciates | 380,000,000 | 54,730,909,800 | -10% |
| Construction Cost +15% | Cost overrun | 437,000,000 | 69,933,940,300 | +15% |
| Construction Cost -15% | Cost saving | 323,000,000 | 51,690,303,700 | -15% |
| Inflation +2% | Higher inflation | 400,000,000 | 64,012,760,000 | +5.3% |
| Inflation -2% | Lower inflation | 360,000,000 | 57,611,484,000 | -5.3% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 19. RECOMMENDATIONS FOR COST MANAGEMENT

| Recommendation | Description | Priority | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- | --- |
| Commission Feasibility Studies | Detailed cost estimates and analysis | Critical | 1,000,000 | 160,031,900 |
| Develop Design Standards | Optimized design for cost efficiency | High | 500,000 | 80,015,950 |
| Engage Cost Consultant | Specialized cost estimation expertise | High | 600,000 | 96,019,140 |
| Value Engineering | Cost optimization during design | Medium | 400,000 | 64,012,760 |
| Regular Cost Monitoring | Track costs during implementation | Medium | 300,000 | 48,009,570 |
| Currency Hedging | Mitigate currency risk | Medium | 500,000 | 80,015,950 |
| TOTAL RECOMMENDED COSTS | - | - | 3,300,000 | 528,105,270 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 20. CONCLUSION

The preliminary cost estimate for the Tog-Wajaale EACC Priority Investment Project is USD 380.0 million (Birr 60.8 billion). When including land acquisition, contingency, price escalation, and financing costs, the total project cost is estimated at USD 420.5 - 437.0 million (Birr 67.3 - 69.9 billion).

Key cost components include:

| Component | Amount (USD) | Amount (Birr)* | Percentage |
| --- | --- | --- | --- |
| Priority 03: FTZ & Logistics | 250,000,000 | 40,007,975,000 | 59.5% |
| Priority 01: Urban Expansion | 63,000,000 | 10,082,009,700 | 15.0% |
| Priority 02: Corridor Roads | 40,000,000 | 6,401,276,000 | 9.5% |
| Priority 04: Solid Waste | 10,000,000 | 1,600,319,000 | 2.4% |
| Priority 05: Youth Centre | 10,000,000 | 1,600,319,000 | 2.4% |
| Priority 06: Reception Centre | 7,000,000 | 1,120,223,300 | 1.7% |
| Contingency | 57,000,000 | 9,121,818,300 | 13.6% |
| Land Acquisition | 10,420,000 | 1,667,532,398 | 2.5% |
| Financing Costs | 20,000,000 | 3,200,638,000 | 4.8% |
| TOTAL | 467,420,000 | 74,802,610,698 | 111.4% |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

Key Observations:

- FTZ & Logistics Hub is the largest cost component at 59.5% of the total, reflecting its scale and economic significance

- Urban Expansion at 15.0% is the foundation investment enabling all other projects

- Corridor Roads at 9.5% provides essential connectivity

- Social Sector Projects (Youth Centre, Reception Centre, Solid Waste) collectively represent 6.5% of the total but deliver significant social impact

These estimates will be refined during the feasibility study phase, with detailed cost analysis, market surveys, and design development.

End of Appendix C

# APPENDIX D: STAKEHOLDER ENGAGEMENT PLAN

- Introduction

  - 1.1 Purpose

  - 1.2 Objectives

  - 1.3 Guiding Principles

- Stakeholder Identification and Analysis

  - 2.1 Stakeholder Categories

  - 2.2 Key Stakeholder Profiles

  - 2.3 Stakeholder Mapping

- Engagement Objectives by Project Phase

  - 3.1 Phase 0: Project Preparation (2024-2025)

  - 3.2 Phase 1: Foundation and Design (2025-2027)

  - 3.3 Phase 2: Implementation and Growth (2027-2030)

  - 3.4 Phase 3: Consolidation and Operations (2030-2035+)

- Engagement Methods and Tools

  - 4.1 Communication Channels

  - 4.2 Engagement Methods

  - 4.3 Stakeholder-Specific Approaches

- Grievance Redress Mechanism

  - 5.1 Purpose and Principles

  - 5.2 Grievance Channels

  - 5.3 Grievance Process

  - 5.4 Grievance Categories and Escalation

  - 5.5 GRM Reporting

- Stakeholder Engagement Schedule

  - 6.1 Phase 0: Project Preparation (2024-2025)

  - 6.2 Phase 1: Foundation and Design (2025-2027)

  - 6.3 Phase 2: Implementation and Growth (2027-2030)

  - 6.4 Phase 3: Consolidation and Operations (2030-2035+)

- Resources and Budget

  - 7.1 Engagement Team

  - 7.2 Budget Estimate

- Monitoring and Evaluation

  - 8.1 Engagement Performance Indicators

  - 8.2 Evaluation Plan

  - 8.3 Feedback Loop

- Communication Materials Plan

  - 9.1 Materials to be Developed

  - 9.2 Key Messages

- Annexes

  - 10.1 Annex A: Stakeholder Contact List

  - 10.2 Annex B: Engagement Activity Template

  - 10.3 Annex C: Grievance Registration Form

## 1. INTRODUCTION

## 1.1 Purpose

This Stakeholder Engagement Plan (SEP) outlines the comprehensive approach for engaging all stakeholders in the Tog-Wajaale EACC Priority Investment Project. The plan ensures that stakeholders are meaningfully involved throughout the project lifecycle, from feasibility study through implementation and operation.

The SEP is designed to:

- Build trust and mutual understanding between the project team and stakeholders

- Ensure that stakeholder concerns and aspirations are incorporated into project design

- Facilitate transparent and inclusive decision-making

- Minimize conflicts and delays through early identification and resolution of issues

- Build local ownership and support for the project

- Ensure equitable distribution of project benefits

## 1.2 Objectives

| Objective | Description |
| --- | --- |
| Informed Participation | Ensure all stakeholders understand the project, its implications, and their role in decision-making |
| Meaningful Input | Provide accessible opportunities for stakeholders to contribute to project design and implementation |
| Conflict Resolution | Identify and address concerns early through effective grievance mechanisms |
| Benefit Sharing | Ensure equitable distribution of project benefits across all stakeholder groups |
| Sustainability | Build local ownership and support for long-term project success and maintenance |
| Capacity Building | Enhance stakeholder capacity to engage effectively in project processes |
| Transparency | Maintain open and honest communication throughout the project lifecycle |

## 1.3 Guiding Principles

| Principle | Description |
| --- | --- |
| Inclusivity | Engage all affected stakeholders, with particular attention to vulnerable and marginalized groups including women, youth, persons with disabilities, and displaced populations |
| Transparency | Open and honest communication about project plans, progress, impacts, and decisions |
| Timeliness | Engage stakeholders early and throughout the project lifecycle, not only when decisions have already been made |
| Cultural Respect | Respect local culture, customs, and traditional decision-making processes including the role of elders and clan leaders (Ugaas) |
| Accountability | Respond to stakeholder concerns and feedback, and demonstrate how input has been incorporated |
| Accessibility | Ensure engagement methods are accessible to all, including those with limited literacy or language barriers |
| Reciprocity | Ensure that engagement is a two-way process that benefits both the project and stakeholders |

## 2. STAKEHOLDER IDENTIFICATION AND ANALYSIS

## 2.1 Stakeholder Categories

| Category | Description | Key Stakeholders |
| --- | --- | --- |
| Government | National, regional, and local government entities with policy, regulatory, and implementation roles | Federal Ministry of Urban Development and Housing; Somali Regional Government (President's Office, Bureau of Urban Development); Fafen Zone Administration; Tog-Wajaale City Administration; Woreda Administrations; Kebele Administrations |
| Community | Residents and community-based organizations in project-affected areas | Community Elders (Ugaas/Clan Leaders); Women's Groups; Youth Groups; Persons with Disabilities; Internally Displaced Persons (IDPs); Host Communities; Religious Leaders; Community-Based Organizations |
| Private Sector | Businesses, investors, and commercial entities | Transport Operators; Logistics Companies; Traders and Merchants; Developers and Property Owners; Financial Institutions; Small and Medium Enterprises; Chamber of Commerce |
| Civil Society | Non-governmental organizations and advocacy groups | NGOs; Community-Based Organizations; Faith-Based Organizations; Human Rights and Advocacy Groups; Environmental Groups |
| Development Partners | Donors and international organizations providing financing and technical support | Swiss Agency for Development and Cooperation (SDC); African Development Bank (AfDB); World Bank Group (IFC); European Union; UNDP; UN-Habitat; Cities Alliance; IGAD; IOM |
| Technical Experts | Professionals and consultants providing specialized expertise | Urban Planners; Transport Engineers; Environmental Specialists; Social Development Specialists; PPP Advisors |
| Beneficiaries | Direct and indirect project beneficiaries | FTZ Users; Businesses; Commuters; Residents; Adjacent Property Owners; Youth; Returnees; Host Communities |

## 2.2 Key Stakeholder Profiles

### 2.2.1 Government Stakeholders

| Stakeholder | Role in Project | Interest | Influence | Engagement Approach |
| --- | --- | --- | --- | --- |
| Federal Ministry of Urban Development and Housing | Policy guidance; national urban development oversight; approval of urban planning instruments | Project alignment with national urban policies; compliance; resource allocation | High | Regular briefings; formal approvals; policy alignment discussions |
| Somali Regional Government | Regional urban planning oversight; land allocation; budget support; political endorsement | Regional development; land use; political support; economic growth | High | Strategic meetings; political engagement; formal approvals |
| Tog-Wajaale City Administration | Project owner; implementation oversight; coordination; community engagement | Successful project delivery; city development; political legacy | Very High | Weekly coordination meetings; leadership engagement; decision-making |
| Fafen Zone Administration | Regional coordination; support services; liaison with woredas | Regional connectivity; coordination; administrative support | Medium | Coordination meetings; reporting; technical support |
| Woreda Administrations | Local implementation; community liaison; land administration | Local development; community support; land management | Medium | Local coordination; community engagement support |
| Kebele Administrations | Community representation; local governance; implementation support | Community development; local benefits; service delivery | High | Community meetings; local coordination; feedback collection |

### 2.2.2 Community Stakeholders

| Stakeholder | Role in Project | Interest | Influence | Engagement Approach |
| --- | --- | --- | --- | --- |
| Community Elders (Ugaas/Clan Leaders) | Traditional leadership; conflict resolution; community representation | Community interests; cultural preservation; benefits distribution | Very High | Personal meetings; community gatherings; traditional protocols; respect for hierarchy |
| Women's Groups | Women's representation; gender equity advocacy | Gender equity; safety; livelihood impacts; access to opportunities | Medium-High | Women-only consultations; focus groups; gender-sensitive approaches |
| Youth Groups | Youth representation; future beneficiaries | Employment opportunities; education access; recreation; mobility | Medium | Youth forums; social media engagement; training and capacity building |
| Persons with Disabilities | Accessibility advocacy; inclusion | Inclusive design; accessibility; non-discrimination | Medium | Accessible consultations; disability-inclusive approaches; partnership with disability organizations |
| Internally Displaced Persons (IDPs) | Vulnerable population; service users | Access to services; social inclusion; livelihood support | Low-Medium | Targeted consultations; social inclusion approaches; accessible information |
| Religious Leaders | Moral authority; community influence | Community welfare; social harmony | High | Engagement through religious institutions; respect for religious protocols |
| Host Communities | Residents in project areas | Livelihood impacts; displacement; property values | Medium | Community meetings; compensation consultations; benefit-sharing discussions |

### 2.2.3 Private Sector Stakeholders

| Stakeholder | Role in Project | Interest | Influence | Engagement Approach |
| --- | --- | --- | --- | --- |
| FTZ Operators/Investors | Potential zone operators; anchor tenants | Business opportunities; investment climate; regulatory environment | High | Investor engagement; PPP discussions; business forums |
| Logistics Companies | Trade and logistics services | Connectivity; trade efficiency; access to corridor | Medium | Business engagement; partnership opportunities; economic impact discussions |
| Traders and Merchants | Commercial activities | Access to markets; trade costs; commercial opportunities | Medium | Business consultations; economic impact assessments; benefit-sharing |
| Developers and Property Owners | Property development; land use | Investment opportunities; land values; development approvals | Medium | Individual meetings; land use planning; investment attraction |
| Financial Institutions | Financing; banking services | Investment opportunities; risk assessment; financial inclusion | Medium | Investor engagement; financing discussions; partnership opportunities |
| Chamber of Commerce | Business representation; advocacy | Business environment; economic development | Medium | Business forums; advocacy support; representation |

### 2.2.4 Development Partners

| Stakeholder | Role in Project | Interest | Influence | Engagement Approach |
| --- | --- | --- | --- | --- |
| Swiss Agency for Development (SDC) | Technical support; potential financing; dialogue support | Sustainable urban development; project success; SDG alignment | High | Regular reporting; strategic dialogue; donor coordination |
| African Development Bank (AfDB) | Potential financing; regional integration | Infrastructure development; regional connectivity; project bankability | High | Financing discussions; project appraisal; compliance reporting |
| World Bank Group (IFC) | Potential financing; PPP support | Private sector engagement; sustainable infrastructure; development impact | High | PPP structuring; investment discussions; project due diligence |
| IGAD | Regional Migration Fund; cross-border coordination | Migration management; regional cooperation | Medium | Programme alignment; RMF coordination; partnership |
| IOM | Migration support; protection services | Migration management; protection; reintegration | Medium | Partnership; service coordination; programme alignment |
| Cities Alliance | Programmatic support; technical assistance | Urban expansion planning; migration and displacement | Medium | Programmatic coordination; knowledge exchange; partnership |

## 2.3 Stakeholder Mapping

### 2.3.1 Influence-Interest Matrix

text

HIGH INFLUENCE | HIGH INFLUENCE

LOW INTEREST | HIGH INTEREST

──────────────────────────────────────┼──────────────────────────────────────

• Federal Ministry | • Tog-Wajaale City Administration

• Somali Regional Government | • Community Elders (Ugaas)

• AfDB / World Bank | • Kebele Administrations

• SDC | • Affected Communities

• EU | • FTZ Investors/Operators

| • Women's Groups

| • Property Owners

| • IOM / IGAD

LOW INFLUENCE | LOW INFLUENCE

LOW INTEREST | HIGH INTEREST

──────────────────────────────────────┼──────────────────────────────────────

• Civil Society NGOs | • Youth Groups

• Academic Institutions | • Persons with Disabilities

| • IDPs

| • Local Businesses

| • Religious Leaders

| • Community-Based Organizations

### 2.3.2 Engagement Strategy by Quadrant

| Quadrant | Stakeholders | Strategy |
| --- | --- | --- |
| High Influence - High Interest | Tog-Wajaale City Administration; Community Elders; Kebele Administrations; Affected Communities; FTZ Investors; Women's Groups | Key Players - Close engagement, partnership, regular consultation, co-decision-making |
| High Influence - Low Interest | Federal Ministry; Somali Regional Government; AfDB; World Bank; SDC; EU | Keep Satisfied - Regular updates, strategic engagement, formal reporting, address concerns |
| Low Influence - High Interest | Youth Groups; Persons with Disabilities; IDPs; Local Businesses; Religious Leaders; CBOs | Keep Informed - Regular communication, feedback mechanisms, targeted consultations |
| Low Influence - Low Interest | Civil Society NGOs; Academic Institutions | Monitor - Periodic updates, minimal engagement, respond to inquiries |

### 2.3.3 Geographic Stakeholder Distribution

| Area | Key Stakeholders | Engagement Considerations |
| --- | --- | --- |
| Urban Expansion Area | Affected residents; property owners; communities | Land acquisition; resettlement; compensation; housing |
| Corridor Roads (20 km) | Roadside residents; businesses; commuters | Access during construction; safety; property impacts |
| FTZ Site (50 ha) | Border communities; traders; logistics operators | Trade impacts; employment; investment |
| Solid Waste Sites | Adjacent communities; waste pickers; residents | Environmental impacts; health; employment |
| Youth/Reception Centres | Youth; returnees; host communities | Social services; employment; community acceptance |
| City Center | Businesses; commuters; city residents | Congestion; accessibility; urban development |
| Peripheral Areas | Expanding communities; new residents | Accessibility; urban expansion; service delivery |

## 3. ENGAGEMENT OBJECTIVES BY PROJECT PHASE

## 3.1 Phase 0: Project Preparation (2024-2025)

| Objective | Description | Success Indicators |
| --- | --- | --- |
| Awareness | Inform stakeholders about project concept, scope, and potential impacts | Stakeholder awareness surveys; attendance at information sessions |
| Input | Gather stakeholder input for feasibility study and project design | Number of comments received; incorporation of feedback into design |
| Buy-in | Build initial support and ownership of the project | Stakeholder endorsements; commitment to participate |
| Risk Identification | Identify potential risks and concerns early | Risk register updated with stakeholder-identified risks |
| Baseline Data | Establish baseline social and economic data | Baseline studies completed |

Key Engagement Activities:

- Public awareness campaigns (radio, posters, community meetings)

- Community consultations in all affected kebeles

- Stakeholder interviews (government officials, community leaders, private sector)

- Focus group discussions (women, youth, persons with disabilities, IDPs)

- Information sessions (project overview, timeline, opportunities)

- Household surveys (social and economic baseline)

- Key informant interviews (traditional leaders, religious leaders)

## 3.2 Phase 1: Foundation and Design (2025-2027)

| Objective | Description | Success Indicators |
| --- | --- | --- |
| Detailed Input | Gather input for detailed design and specifications | Design changes incorporated; stakeholder satisfaction with design |
| Grievance Redress | Address concerns and grievances from affected stakeholders | Grievance resolution rate; resolution time |
| Transparency | Ensure transparent procurement process | Procurement process perceived as fair; no complaints |
| Land Acquisition | Facilitate fair and transparent land acquisition | Land acquisition agreements signed; fair compensation |
| Resettlement | Ensure fair and transparent resettlement process | Resettlement plans approved; resettlement completed |

Key Engagement Activities:

- Design workshops (technical design, station locations, NMT routes)

- Land acquisition consultations (affected property owners, communities)

- Grievance mechanism establishment and rollout

- Procurement transparency briefings

- Community information sessions (land acquisition, resettlement)

- Resettlement consultations (affected households)

## 3.3 Phase 2: Implementation and Growth (2027-2030)

| Objective | Description | Success Indicators |
| --- | --- | --- |
| Information | Keep stakeholders informed about construction progress | Stakeholder satisfaction with information; information reach |
| Safety | Ensure safety during construction | Safety incidents; safety awareness |
| Access | Manage access during construction | Access maintained; complaints minimal |
| Grievance Redress | Address construction-related grievances | Grievance resolution rate; response time |
| Community Benefits | Maximize community benefits during construction | Local employment; local procurement; community projects |

Key Engagement Activities:

- Construction updates (monthly newsletters, public meetings)

- Safety awareness campaigns (safety materials, community meetings)

- Access management communication (signage, information boards)

- Grievance mechanism operation (complaints desk, hotline)

- Community liaison officers (day-to-day engagement)

- Local employment and procurement (job fairs, supplier registration)

## 3.4 Phase 3: Consolidation and Operations (2030-2035+)

| Objective | Description | Success Indicators |
| --- | --- | --- |
| Operational Information | Inform stakeholders about operations, schedules, and services | Stakeholder awareness; satisfaction with information |
| Feedback | Gather feedback on operations and service delivery | Number of feedback received; satisfaction rates |
| Benefit Sharing | Ensure benefits are shared equitably | Benefit-sharing mechanisms operational; stakeholder satisfaction |
| Sustainability | Build long-term community support and ownership | Community support; stakeholder ownership |
| Monitoring | Monitor social and economic impacts | Impact assessments; stakeholder feedback |

Key Engagement Activities:

- Operational launch events (inauguration ceremonies, community celebrations)

- Customer feedback mechanisms (surveys, suggestion boxes, hotline)

- Community benefit programs (local employment, enterprise development)

- Performance reporting (annual reports, public meetings)

- Stakeholder satisfaction surveys

- Social and economic impact monitoring

## 4. ENGAGEMENT METHODS AND TOOLS

## 4.1 Communication Channels

| Channel | Purpose | Target Audience | Frequency | Estimated Cost (USD) | Responsible |
| --- | --- | --- | --- | --- | --- |
| Public Meetings | Information sharing; feedback gathering | General public; affected communities | Quarterly | 5,000 | Engagement Team |
| Community Consultations | In-depth discussion; input gathering | Affected communities; community leaders | As needed | 3,000 | Engagement Team |
| Focus Group Discussions | Specific stakeholder input; in-depth exploration | Women, youth, vulnerable groups | As needed | 2,000 | Engagement Team |
| Stakeholder Workshops | Collaborative planning; problem-solving | Key stakeholders; technical experts | Periodic | 10,000 | Engagement Team |
| Newsletters | Project updates; information sharing | General public; stakeholders | Quarterly | 2,000 | Communications Specialist |
| Social Media | Public information; engagement | General public; youth | Weekly | 500 | Communications Specialist |
| Radio | Public information; announcements | General public; rural communities | Monthly | 3,000 | Communications Specialist |
| Project Website | Comprehensive information | All stakeholders | Continuous | 2,000 | IT Team |
| Information Boards | Local announcements; community information | Local communities | Continuous | 1,000 | Community Liaison Officers |
| Community Liaison Officers | Day-to-day engagement; relationship-building | Local communities; affected stakeholders | Continuous | 30,000 | Engagement Team |
| Hotline | Grievance reporting; inquiries | All stakeholders | Continuous | 5,000 | GRM Officer |
| Email Updates | Direct stakeholder updates | Key stakeholders; partners | Monthly | 500 | Communications Specialist |

## 4.2 Engagement Methods

| Method | Description | Best Used For | Resources Required | Strengths | Limitations |
| --- | --- | --- | --- | --- | --- |
| Public Meetings | Open meetings for information sharing; question and answer sessions | Large group information; general feedback; announcement | Venue; speakers; audiovisual; materials | Wide reach; transparency; immediate feedback | Can be intimidating for some; limited in-depth discussion |
| Community Consultations | Structured meetings with community representatives | Detailed discussion; input gathering; local perspectives | Facilitator; interpreters; materials | Community involvement; detailed input; trust-building | Time-consuming; resource-intensive |
| Focus Group Discussions | Small group discussions with specific stakeholders | In-depth exploration of issues; nuanced perspectives | Facilitator; note-taker; venue | In-depth insights; comfortable setting; participant engagement | Not representative; requires facilitation skill |
| Stakeholder Workshops | Collaborative planning sessions; problem-solving | Joint problem-solving; co-design; partnership building | Facilitator; materials; venue | Collaborative; builds ownership; creative solutions | Time-intensive; requires preparation |
| Interviews | One-on-one discussions | Individual perspectives; sensitive issues; detailed information | Interviewer; recording; confidentiality | Detailed insights; personal engagement; confidential | Time-consuming; not representative |
| Surveys | Structured questionnaires | Broad input; quantitative data; satisfaction measurement | Survey design; analysis; distribution | Representative; quantitative; cost-effective | Limited depth; response rates |
| Information Fairs | Exhibitions with project information | Public awareness; information sharing; community engagement | Exhibits; staff; venue | Engaging; visual; broad reach | Resource-intensive; limited depth |
| Grievance Mechanism | Structured complaint handling | Issue resolution; accountability; feedback | Complaints desk; staff; systems | Addresses concerns; accountability; trust-building | Requires ongoing resources |
| Community Liaison | Dedicated community engagement professionals | Day-to-day engagement; trust-building; relationship management | Liaison officers; vehicles; tools | Ongoing engagement; trust; accessibility | Resource-intensive |

## 4.3 Stakeholder-Specific Approaches

| Stakeholder Group | Preferred Method | Key Issues | Engagement Team | Language/Translation | Location/Timing |
| --- | --- | --- | --- | --- | --- |
| Government | Meetings; briefings; formal reports | Policy alignment; coordination; approvals; funding | Project Manager; City Administration | Amharic; Somali; English | Government offices; formal settings |
| Community Elders (Ugaas) | Personal meetings; community gatherings; traditional protocols | Community interests; cultural concerns; benefits; legacy | Community Liaison Officers; Elders | Somali; respect for protocols | Community settings; traditional gatherings |
| Women's Groups | Women-only meetings; focus groups; women's forums | Gender equity; safety; livelihood impacts; access | Gender Specialist; Women's Organizations | Somali; local dialects | Women-friendly venues; comfortable timing |
| Youth Groups | Youth forums; social media; interactive sessions | Employment; education; recreation; mobility | Youth Liaison; Youth Organizations | Somali; Amharic; English | Youth-friendly venues; after-hours timing |
| Persons with Disabilities | Accessible consultations; partnership with disability organizations | Inclusive design; accessibility; non-discrimination | Social Development Specialist | Accessible formats; interpreters | Accessible venues; inclusive timing |
| Internally Displaced Persons | Targeted consultations; social inclusion approaches | Access to services; social inclusion; livelihood support | Social Development Specialist | Somali; local dialects | Accessible locations; community settings |
| Religious Leaders | Engagement through religious institutions; respect for protocols | Community welfare; social harmony; moral guidance | Community Liaison Officers | Somali; respect for protocols | Religious settings; appropriate timing |
| Private Sector | Business forums; individual meetings; formal engagement | Business opportunities; investment climate; competition | Economic Development Officer | English; Somali | Business-friendly venues; working hours |
| Development Partners | Formal meetings; reports; donor coordination | Project alignment; progress; financing; impact | City Administration; Project Manager | English | Formal settings; international protocols |
| Affected Communities | Community meetings; household visits; information boards | Livelihood impacts; compensation; resettlement; benefits | Community Liaison Officers | Somali; local dialects | Community settings; accessible timing |
| General Public | Public meetings; radio; social media; newsletters | Project awareness; benefits; opportunities | Communications Specialist | Somali; Amharic | Various settings; diverse timing |

## 5. GRIEVANCE REDRESS MECHANISM

## 5.1 Purpose and Principles

The Grievance Redress Mechanism (GRM) provides a structured process for receiving, addressing, and resolving complaints and concerns from stakeholders affected by the project.

### 5.1.1 Purpose

| Purpose | Description |
| --- | --- |
| Early Resolution | Address concerns early before they escalate into conflicts |
| Accountability | Hold project implementers accountable to stakeholders |
| Feedback | Provide a channel for stakeholder feedback and input |
| Trust Building | Build trust through transparent and responsive complaint handling |
| Risk Management | Identify and address project risks through stakeholder feedback |

### 5.1.2 Principles

| Principle | Description |
| --- | --- |
| Accessibility | Easily accessible to all stakeholders regardless of location, literacy, or language |
| Impartiality | Fair and impartial handling of complaints without discrimination |
| Transparency | Open and transparent process with clear procedures and timelines |
| Timeliness | Prompt response and resolution with clear timeframes |
| Confidentiality | Protection of complainants' identities when requested |
| No Retaliation | Protection from retaliation for raising complaints |
| Accountability | Clear accountability for grievance resolution |

## 5.2 Grievance Channels

| Channel | Description | Contact | Accessibility | Language |
| --- | --- | --- | --- | --- |
| Complaints Desk | Physical location for complaints at City Administration Office | City Administration Office | Accessible location; wheelchair accessible | Somali; Amharic |
| Community Liaison Officers | In-person reporting through dedicated officers | Mobile contacts to be established | Visits communities; accessible | Somali; local dialects |
| Hotline | Telephone complaint line | To be established | Phone access; low-cost | Somali; Amharic |
| Email | Email complaint address | complaints@twuep.com.et | Internet access; literacy | English; Somali; Amharic |
| Suggestion Boxes | Written complaints at community locations | Community centers; information boards | Community access; literacy required | Somali; Amharic |
| Community Meetings | Verbal complaints at public meetings | Community meetings | Community access; no literacy required | Somali; Amharic |
| Mobile App/Website | Online complaint submission | www.twuep.com.et | Internet access; smartphone | English; Somali; Amharic |
| SMS | Text message complaints | To be established | Phone access; SMS capability | Somali; Amharic |

## 5.3 Grievance Process

### 5.3.1 Process Flow

text

┌─────────────────────────────────────┐

│ Step 1: Complaint Submission │

│ - Any channel (hotline, desk, │

│ liaison, email, etc.) │

│ - No cost to complainant │

└────────────────┬────────────────────┘

│ (Within 48 hours)

▼

┌─────────────────────────────────────┐

│ Step 2: Acknowledgment │

│ - Acknowledgment of receipt │

│ - Reference number provided │

│ - Estimated timeline given │

└────────────────┬────────────────────┘

│ (Within 7 days)

▼

┌─────────────────────────────────────┐

│ Step 3: Investigation │

│ - Preliminary assessment │

│ - Categorization of complaint │

│ - Investigation of facts │

│ - Consultation with relevant │

│ parties │

└────────────────┬────────────────────┘

│ (Within 14 days)

▼

┌─────────────────────────────────────┐

│ Step 4: Resolution │

│ - Decision rendered │

│ - Recommendation/action plan │

│ - Communication to complainant │

└────────────────┬────────────────────┘

│ (Within 30 days)

▼

┌─────────────────────────────────────┐

│ Step 5: Follow-up │

│ - Implementation monitoring │

│ - Feedback to complainant │

│ - Documentation and learning │

└─────────────────────────────────────┘

### 5.3.2 Timelines

| Step | Action | Timeline |
| --- | --- | --- |
| 1 | Complaint Submission | Anytime |
| 2 | Acknowledgment | Within 48 hours |
| 3 | Investigation | Within 7 days |
| 4 | Resolution | Within 14 days (Level 1-2); Within 30 days (Level 3-4) |
| 5 | Follow-up | Within 30 days |

## 5.4 Grievance Categories and Escalation

| Level | Category | Description | Resolution Time | Responsible | Escalation |
| --- | --- | --- | --- | --- | --- |
| Level 1 | Minor | Simple complaints, information requests, inquiries | 3-5 days | Complaints Desk/CLO | Issue resolved |
| Level 2 | Moderate | Service issues, operational concerns, minor impacts | 5-10 days | Project Manager | Project Manager review |
| Level 3 | Serious | Land disputes, significant impacts, compensation issues | 10-14 days | City Manager | City Manager review |
| Level 4 | Critical | Legal disputes, major conflicts, policy issues | 14-30 days | Mayor / Legal | Mayoral/Council review |

## 5.5 GRM Reporting

| Report Type | Frequency | Recipients | Purpose |
| --- | --- | --- | --- |
| Complaint Log | Continuous | GRM Team | Tracking and monitoring |
| Monthly Summary | Monthly | Project Manager | Performance monitoring |
| Quarterly Report | Quarterly | City Manager, Mayor | Decision-making; reporting |
| Annual Report | Annual | All stakeholders | Transparency; accountability |
| Thematic Reports | As needed | Project Team | Learning; improvement |

## 5.6 GRM Resources

| Resource | Description | Quantity | Cost (USD) | Cost (Birr)* |
| --- | --- | --- | --- | --- |
| GRM Officer | Dedicated officer for GRM management | 1 | 15,000/year | 2,400,479 |
| GRM Staff | Support staff for GRM operations | 2 | 20,000/year | 3,200,638 |
| Hotline System | Phone system for complaint hotline | 1 | 5,000 | 800,160 |
| Database System | Digital system for complaint tracking | 1 | 10,000 | 1,600,319 |
| Training | Training for GRM staff | Annual | 5,000/year | 800,160 |
| Operational Costs | Transport, communication, materials | Annual | 10,000/year | 1,600,319 |
| TOTAL | - | - | 65,000 | 10,402,073 |

Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 6. STAKEHOLDER ENGAGEMENT SCHEDULE

## 6.1 Phase 0: Project Preparation (2024-2025)

| Activity | Timeline | Stakeholders | Responsible | Expected Outcome |
| --- | --- | --- | --- | --- |
| Project Introduction | Month 1 | All stakeholders | City Administration | Stakeholder awareness |
| Stakeholder Identification | Month 1-2 | All categories | Urban Expansion Team | Comprehensive stakeholder database |
| Stakeholder Mapping | Month 2 | All categories | Urban Expansion Team | Influence-interest matrix; engagement strategy |
| Key Informant Interviews | Month 2-3 | Key stakeholders | Engagement Team | Insights for feasibility study |
| Community Consultations (Round 1) | Month 3-6 | Communities, Kebeles | Urban Expansion Team | Community input and concerns |
| Focus Group Discussions | Month 4-6 | Women, youth, vulnerable groups | Engagement Team | Specific insights and concerns |
| Feasibility Study Input | Month 6-9 | All stakeholders | Consultant/Team | Technical and social input |
| Information Sessions | Month 9-12 | All stakeholders | City Administration | Stakeholder awareness and buy-in |
| Feedback Workshops | Month 12 | Key stakeholders | Project Manager | Validation of findings |

## 6.2 Phase 1: Foundation and Design (2025-2027)

| Activity | Timeline | Stakeholders | Responsible | Expected Outcome |
| --- | --- | --- | --- | --- |
| Design Workshops (Round 1) | Month 15-18 | Technical experts, communities | Design Consultant | Technical design input |
| Design Workshops (Round 2) | Month 18-21 | Technical experts, communities | Design Consultant | Refined design |
| Community Consultations (Round 2) | Month 18-24 | Communities, Kebeles | Engagement Team | Community design input |
| Land Acquisition Consultations | Month 18-30 | Affected communities, property owners | Legal Team | Land acquisition agreements |
| Procurement Transparency Sessions | Month 24-30 | Private sector, civil society | Procurement Team | Transparent procurement |
| GRM Establishment | Month 18 | All stakeholders | Engagement Team | Operational GRM |
| Community Update Meetings | Quarterly | Local communities | Community Liaison Officers | Stakeholder informed |
| Resettlement Consultations | Month 24-30 | Affected households | Social Development Team | Resettlement plans |

## 6.3 Phase 2: Implementation and Growth (2027-2030)

| Activity | Timeline | Stakeholders | Responsible | Expected Outcome |
| --- | --- | --- | --- | --- |
| Construction Kick-off | Month 30 | All stakeholders | Contractor/Project Manager | Stakeholder buy-in |
| Regular Community Updates | Monthly | Local communities | Community Liaison Officers | Stakeholder informed |
| Safety Awareness Campaigns | Continuous | General public | Safety Officer | Safety awareness |
| Access Management Communication | Continuous | Affected communities | Contractor | Access maintained |
| GRM Operation | Continuous | All stakeholders | GRM Team | Issues resolved |
| Construction Progress Meetings | Quarterly | Government, key stakeholders | Project Manager | Progress transparent |
| Local Employment/Job Fairs | Annually | Communities, youth | Economic Development Officer | Local employment |
| Community Benefit Programs | Annual | Local communities | Engagement Team | Community benefits |

## 6.4 Phase 3: Consolidation and Operations (2030-2035+)

| Activity | Timeline | Stakeholders | Responsible | Expected Outcome |
| --- | --- | --- | --- | --- |
| Operational Launch Events | Month 60+ | All stakeholders | City Administration | Successful launch |
| Customer Feedback Systems | Continuous | Service users, communities | Operators | Operational feedback |
| Community Benefit Programs | Continuous | Local communities | Operator/Community Liaison | Community benefits |
| Performance Reporting | Quarterly/Annually | All stakeholders | Project Manager | Transparency |
| Annual Stakeholder Forums | Annual | All stakeholders | City Administration | Stakeholder engagement |
| Social and Economic Impact Monitoring | Annual | All stakeholders | Monitoring Team | Impact assessment |
| Stakeholder Satisfaction Surveys | Annual | All stakeholders | Engagement Team | Satisfaction measurement |

## 7. RESOURCES AND BUDGET

## 7.1 Engagement Team

| Position | Responsibility | Required Experience | Quantity | Salary (USD/year) | Salary (Birr/year)* |
| --- | --- | --- | --- | --- | --- |
| Stakeholder Engagement Manager | Overall coordination of engagement activities | 7+ years in community engagement | 1 | 30,000 | 4,800,957 |
| Community Liaison Officers | Day-to-day community engagement in different areas | 5+ years in community relations | 3 | 20,000 each | 3,200,638 each |
| Social Development Specialist | Gender and social inclusion | 5+ years in social development | 1 | 25,000 | 4,000,798 |
| Communications Specialist | Information dissemination and media relations | 5+ years in communications | 1 | 25,000 | 4,000,798 |
| GRM Officer | Grievance handling and reporting | 5+ years in complaints handling | 1 | 20,000 | 3,200,638 |
| Administrative Support | Administrative and logistical support | 3+ years in administration | 2 | 10,000 each | 1,600,319 each |
| TOTAL PERSONNEL COSTS | - | - | 9 | 160,000 | 25,605,104 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 7.2 Budget Estimate

| Item | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Personnel | Engagement team salaries | 160,000 | 25,605,104 |
| Community Engagement | Consultations, workshops, meetings | 150,000 | 24,004,785 |
| - Public meetings (12 @ USD 5,000) | Venue, facilitation, materials | 60,000 | 9,601,914 |
| - Community consultations (20 @ USD 3,000) | Facilitation, translation, materials | 60,000 | 9,601,914 |
| - Focus group discussions (15 @ USD 2,000) | Facilitation, translation, materials | 30,000 | 4,800,957 |
| Communications | Materials, media, website | 100,000 | 16,003,190 |
| - Print materials (brochures, posters, newsletters) | Design, printing, distribution | 30,000 | 4,800,957 |
| - Radio and media | Broadcasting, production | 25,000 | 4,000,798 |
| - Website and social media | Development, maintenance, content | 20,000 | 3,200,638 |
| - Information boards | Production, installation | 25,000 | 4,000,798 |
| GRM | Hotline, systems, reporting | 65,000 | 10,402,073 |
| - GRM staff | Salaries | 35,000 | 5,601,117 |
| - Hotline and systems | Setup, maintenance | 15,000 | 2,400,479 |
| - Training and materials | Capacity building | 15,000 | 2,400,479 |
| Monitoring | Follow-up and evaluation | 50,000 | 8,001,595 |
| - Surveys and assessments | Design, implementation, analysis | 30,000 | 4,800,957 |
| - Reporting | Documentation, distribution | 20,000 | 3,200,638 |
| Contingency | 10% of total | 52,500 | 8,401,675 |
| TOTAL | - | 577,500 | 92,418,422 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 8. MONITORING AND EVALUATION

## 8.1 Engagement Performance Indicators

| Indicator | Target | Measurement Method | Frequency | Responsible |
| --- | --- | --- | --- | --- |
| Stakeholder Satisfaction | >75% satisfied | Surveys; interviews | Annual | Engagement Manager |
| Participation Rate | >60% of target stakeholders | Participation logs | Each event | Engagement Manager |
| Grievance Resolution Time | <14 days (95% resolved) | GRM database | Monthly | GRM Officer |
| Grievance Resolution Rate | >90% resolved | GRM database | Monthly | GRM Officer |
| Community Awareness | >80% awareness | Surveys; focus groups | Annual | Engagement Manager |
| Representation | 50% women at events | Participation logs | Each event | Engagement Manager |
| Information Reach | Reaching all affected communities | Coverage mapping | Quarterly | Communications Specialist |
| Trust in Project | >70% trust rating | Surveys | Annual | Engagement Manager |
| Perceived Transparency | >70% transparency rating | Surveys | Annual | Engagement Manager |
| Local Employment | % of jobs to local communities | Employment records | Quarterly | Economic Development Officer |

## 8.2 Evaluation Plan

| Activity | Frequency | Responsibility | Purpose |
| --- | --- | --- | --- |
| Activity Reporting | Each activity | Engagement Team | Track engagement activities |
| Monthly Progress Review | Monthly | Engagement Manager | Monitor progress against plan |
| Quarterly Reporting | Quarterly | Engagement Team | Reporting to project management |
| Annual Evaluation | Annual | External Evaluator | Evaluate engagement effectiveness |
| Mid-Term Review | Mid-term | Project Manager | Review and adjust approach |
| End-Term Evaluation | Project end | External Evaluator | Overall evaluation |

## 8.3 Feedback Loop

### 8.3.1 Process Flow

text

┌─────────────────────────────────────┐

│ Stakeholder Feedback │

│ (Input, Concerns, Complaints) │

└────────────────┬────────────────────┘

│

▼

┌─────────────────────────────────────┐

│ Feedback Collection │

│ (Meetings, Surveys, Complaints) │

└────────────────┬────────────────────┘

│

▼

┌─────────────────────────────────────┐

│ Analysis & Evaluation │

│ (Identify Themes, Issues, Priorities)│

└────────────────┬────────────────────┘

│

▼

┌─────────────────────────────────────┐

│ Response Development │

│ (Action Plan, Communications) │

└────────────────┬────────────────────┘

│

▼

┌─────────────────────────────────────┐

│ Response Implementation │

│ (Actions, Changes, Improvements) │

└────────────────┬────────────────────┘

│

▼

┌─────────────────────────────────────┐

│ Communication of Response │

│ to Stakeholders │

└─────────────────────────────────────┘

### 8.3.2 Response Timeframes

| Type of Feedback | Timeframe | Communication Method |
| --- | --- | --- |
| Individual Concerns | Within 7 days | Direct communication to individual |
| Community Concerns | Within 14 days | Community meeting; written communication |
| General Feedback | Within 30 days | Newsletter; website; public meeting |
| Major Issues | Within 30 days | Special meeting; written communication |

## 9. COMMUNICATION MATERIALS PLAN

## 9.1 Materials to be Developed

| Material | Purpose | Format | Target Audience | Timing | Responsible |
| --- | --- | --- | --- | --- | --- |
| Project Brief | Overview of the project | PDF, Print | All stakeholders | Phase 0 | Communications Specialist |
| Fact Sheets | Specific topics (FTZ, benefits, timeline) | PDF, Print | General public | Phase 0-1 | Communications Specialist |
| Newsletter | Regular project updates | Digital, Print | All stakeholders | Quarterly | Communications Specialist |
| Posters | Public awareness | Print | General public | All phases | Communications Specialist |
| Brochures | Detailed project information | Print | All stakeholders | Phase 0 | Communications Specialist |
| Website | Comprehensive information | Digital | All stakeholders | Continuous | IT Team |
| Social Media | Updates and engagement | Digital | General public, youth | Continuous | Communications Specialist |
| Radio Spots | Public awareness | Audio | General public, rural communities | All phases | Communications Specialist |
| Presentation Materials | Meetings and workshops | Digital | Key stakeholders | As needed | Engagement Team |
| Information Boards | Local announcements | Physical | Local communities | All phases | Community Liaison Officers |
| Complaint Forms | Grievance submission | Physical, Digital | All stakeholders | Phase 1+ | GRM Officer |
| Satisfaction Surveys | Feedback collection | Physical, Digital | All stakeholders | Annual | Engagement Team |

## 9.2 Key Messages

| Message | Target Audience | Purpose |
| --- | --- | --- |
| "These projects will transform Tog-Wajaale into a regional economic hub" | General public | Benefits communication |
| "The FTZ will create 6,000+ jobs and attract investment" | Community, private sector | Economic benefits |
| "Urban expansion will provide 5,000+ new housing units" | Residents, communities | Housing benefits |
| "Solid waste management will create a clean, healthy city" | General public | Environmental benefits |
| "Youth Centre will train 5,000+ youth annually" | Youth, communities | Skills development |
| "Reception Centre will provide dignified support for returnees" | Returnees, communities | Social protection |
| "Your input matters - participate in consultations" | All stakeholders | Participation encouragement |
| "We address concerns through our grievance mechanism" | Affected communities | Trust building |
| "The projects are part of Tog-Wajaale's 2055 vision" | All stakeholders | Strategic alignment |
| "We are committed to fair and transparent processes" | All stakeholders | Trust building |

## 9.3 Communication Schedule

| Communication Activity | Frequency | Target Audience | Responsible |
| --- | --- | --- | --- |
| Project Website Updates | Weekly | All stakeholders | IT Team |
| Social Media Posts | Weekly | General public, youth | Communications Specialist |
| Radio Announcements | Monthly | General public, rural communities | Communications Specialist |
| Community Newsletter | Quarterly | All stakeholders | Communications Specialist |
| Stakeholder Briefing | Quarterly | Key stakeholders | Project Manager |
| Public Meeting | Annually | General public | Engagement Team |
| Annual Report | Annually | All stakeholders | Project Manager |

## 10. ANNEXES

## 10.1 Annex A: Stakeholder Contact List

| Name | Organization | Role | Contact | Engagement Preference |
| --- | --- | --- | --- | --- |
| Mahamud Yusuf Adan | Tog-Wajaale City Administration | Mayor | +251 915 330528 | Meetings; Briefings |
| Abdikarim Hassen Yusuf | Tog-Wajaale City Administration | City Manager | +251 915 074535 | Meetings; Briefings |
| Additional contacts to be developed during engagement |  |  |  |  |

## 10.2 Annex B: Engagement Activity Template

| Element | Details |
| --- | --- |
| Activity Name | [Name of activity] |
| Date | [Date of activity] |
| Time | [Start and end time] |
| Location | [Venue and address] |
| Purpose | [Purpose of activity] |
| Target Participants | [Number and types of participants] |
| Actual Participants | [Number and types of participants] |
| Agenda | [Key agenda items] |
| Facilitators | [Names and roles] |
| Key Issues Raised | [Summary of issues raised] |
| Recommendations | [Recommendations from participants] |
| Actions Taken | [Actions in response] |
| Follow-up | [Planned follow-up] |
| Feedback | [Participant feedback] |
| Lessons Learned | [Key lessons learned] |

## 10.3 Annex C: Grievance Registration Form

| Field | Details |
| --- | --- |
| Complaint Reference Number | [Auto-generated] |
| Date Received | [Date] |
| Complainant Name | [Name] |
| Contact Information | [Phone/Email/Address] |
| Location | [Kebele/Area] |
| Complainant Category | [Individual/Community/Business/Other] |
| Gender | [Male/Female/Other] |
| Complaint Category | [Level 1/2/3/4] |
| Complaint Description | [Detailed description] |
| Location of Issue | [Specific location] |
| Date of Incident | [Date] |
| Witnesses | [Names and contacts] |
| Desired Outcome | [What does complainant want?] |
| Received By | [Name] |
| Date of Acknowledgment | [Date] |
| Assigned To | [Name] |
| Investigation Summary | [Summary of findings] |
| Resolution | [Resolution details] |
| Resolution Date | [Date] |
| Complainant Satisfaction | [Satisfied/Partially Satisfied/Not Satisfied] |
| Follow-up Required | [Yes/No] |

# APPENDIX E: MONITORING AND EVALUATION FRAMEWORK

- Introduction

  - 1.1 Purpose

  - 1.2 Objectives

  - 1.3 Guiding Principles

- Monitoring and Evaluation Framework Overview

  - 2.1 M&E Framework Structure

  - 2.2 Logical Framework

  - 2.3 Theory of Change

- Performance Indicators

  - 3.1 Input Indicators

  - 3.2 Activity Indicators

  - 3.3 Output Indicators

  - 3.4 Outcome Indicators

  - 3.5 Impact Indicators

  - 3.6 Environmental and Social Indicators

  - 3.7 Financial Indicators

- Data Collection Methods and Tools

  - 4.1 Quantitative Methods

  - 4.2 Qualitative Methods

  - 4.3 Data Sources

  - 4.4 Data Collection Schedule

- Monitoring and Evaluation Plan

  - 5.1 Implementation Monitoring

  - 5.2 Performance Monitoring

  - 5.3 Financial Monitoring

  - 5.4 Environmental and Social Monitoring

  - 5.5 Stakeholder Engagement Monitoring

- Reporting Framework

  - 6.1 Reporting Structure

  - 6.2 Report Types and Frequency

  - 6.3 Reporting Templates

- Evaluation Plan

  - 7.1 Mid-Term Evaluation

  - 7.2 End-Term Evaluation

  - 7.3 Thematic Evaluations

  - 7.4 Evaluation Methodology

- M&E Roles and Responsibilities

  - 8.1 M&E Team Structure

  - 8.2 Responsibilities by Role

  - 8.3 Training and Capacity Building

- M&E Budget and Resources

  - 9.1 Budget Estimate

  - 9.2 Required Resources

- Data Management and Quality Assurance

  - 10.1 Data Collection Protocols

  - 10.2 Data Quality Assurance

  - 10.3 Data Storage and Security

  - 10.4 Data Analysis and Use

- Annexes

  - 11.1 Annex A: Indicator Tracking Table

  - 11.2 Annex B: Data Collection Tools

  - 11.3 Annex C: Reporting Templates

  - 11.4 Annex D: M&E Timeline

## 1. INTRODUCTION

## 1.1 Purpose

This Monitoring and Evaluation (M&E) Framework outlines the comprehensive approach for monitoring progress and evaluating the outcomes and impacts of the Tog-Wajaale EACC Priority Investment Project. The framework provides the structure, processes, and tools for systematic data collection, analysis, and reporting to ensure project accountability, effectiveness, and learning.

The M&E Framework is designed to:

- Track project progress against established targets and milestones

- Measure project outcomes and impacts across all six priority projects

- Ensure accountability to stakeholders and financiers

- Identify challenges and lessons learned for adaptive management

- Provide evidence for decision-making and reporting

- Demonstrate project effectiveness and value for money

- Support the achievement of the Tog-Wajaale Urban Expansion Plan (TWUEP) 2025-2055

## 1.2 Objectives

| Objective | Description |
| --- | --- |
| Track Progress | Monitor implementation progress against work plans and budgets |
| Measure Performance | Assess project performance against established indicators and targets |
| Assess Outcomes | Evaluate the extent to which project objectives are being achieved |
| Measure Impact | Assess the long-term impacts of the project on the city and its residents |
| Ensure Accountability | Demonstrate accountability to stakeholders, financiers, and beneficiaries |
| Enable Learning | Capture lessons learned to inform decision-making and future projects |
| Promote Adaptive Management | Enable timely adjustments to project implementation based on evidence |
| Support Reporting | Provide evidence for project reporting to stakeholders and financiers |

## 1.3 Guiding Principles

| Principle | Description |
| --- | --- |
| Evidence-Based | All monitoring and evaluation should be based on credible, verifiable evidence |
| Participatory | Involve stakeholders in M&E processes to ensure relevance and ownership |
| Transparent | Share M&E findings openly with all stakeholders |
| Timely | Provide timely information for decision-making |
| Utilization-Focused | Ensure M&E findings are used for learning and improvement |
| Gender-Responsive | Ensure M&E captures differential impacts on women, men, and vulnerable groups |
| Cost-Effective | Ensure M&E activities are proportionate and cost-effective |

## 2. MONITORING AND EVALUATION FRAMEWORK OVERVIEW

## 2.1 M&E Framework Structure

| Level | Description | Key Questions |
| --- | --- | --- |
| Impact | Long-term project impacts on the city and its residents | What changes have occurred? What lasting effects has the project had? |
| Outcome | Medium-term results of project activities | What changes in behavior, capacity, or conditions have occurred? |
| Output | Immediate products of project activities | What has been produced or delivered? |
| Activities | Project activities and processes | What is being done? How? |
| Inputs | Resources invested in the project | What resources are being invested? |

## 2.2 Logical Framework

| Level | Description | Indicators | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
| Impact | Sustainable urban development and economic growth in Tog-Wajaale | Population served; economic growth; quality of life | Census data; economic data; household surveys | Policies remain supportive; regional stability maintained |
| Outcome | Improved urban mobility, economic activity, environmental sustainability, social inclusion | Mode share change; jobs created; waste collection coverage; youth trained | Traffic surveys; employment records; service records; training records | Behavioral change occurs; services maintained |
| Output | Infrastructure and services delivered | BRT length; road length; FTZ area; waste facilities; centres built | Project reports; physical verification; commissioning reports | Construction completed on time; quality standards met |
| Activities | Project activities and processes | Milestone completion; budget utilization | Project management reports; financial reports | Resources available; stakeholders engaged |
| Inputs | Financial resources; human resources; technical expertise | Budget disbursement; staff recruitment; contracts awarded | Financial reports; HR records; procurement records | Funding secured; qualified staff available |

## 2.3 Theory of Change

### 2.3.1 Theory of Change Framework

text

┌─────────────────────────────────────────────────────────────────────────────┐

│ THEORY OF CHANGE │

├─────────────────────────────────────────────────────────────────────────────┤

│ │

│ INPUTS OUTPUTS OUTCOMES │

│ │

│ • Financial • 5,000+ housing units • Reduced │

│ Resources • 20 km upgraded roads unplanned sprawl │

│ │

│ • Technical • 50 ha FTZ & Logistics • Increased trade │

│ Expertise Hub (USD 500M+) │

│ │

│ • Human Resources • Citywide waste • 6,000+ jobs │

│ management system created │

│ • Political Will │

│ • Youth Skills Centre • 5,000+ youth │

│ • Community • Reception Centre trained annually │

│ Support │

│ • Urban Expansion • Returnees │

│ framework supported │

│ • Environmental │

│ benefits │

│ • Improved │

│ quality of life │

│ │

│ IMPACTS │

│ │

│ • Sustainable urban development │

│ • Regional economic integration │

│ • Improved quality of life │

│ • Climate-resilient city │

│ │

└─────────────────────────────────────────────────────────────────────────────┘

### 2.3.2 Causal Pathways

| Pathway | Description | Key Assumptions |
| --- | --- | --- |
| Pathway 1: Foundation | Urban Expansion creates serviced land and framework for all other investments | Land is acquired; infrastructure is built; people use the land |
| Pathway 2: Connectivity | Road upgrades provide access to FTZ, urban expansion, and trade corridor | Roads are built to quality standards; people use the roads |
| Pathway 3: Economic | FTZ drives growth and job creation | Investors are attracted; businesses establish operations |
| Pathway 4: Environmental | Solid waste management improves environmental sustainability | People use waste services; recycling systems function |
| Pathway 5: Human Capital | Youth Centre develops workforce for FTZ and other opportunities | Youth participate in training; jobs are available |
| Pathway 6: Social Protection | Reception Centre supports vulnerable returnees | Returnees access services; reintegration is successful |

## 3. PERFORMANCE INDICATORS

## 3.1 Input Indicators

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Budget Disbursement Rate | Percentage of budget disbursed | 0% | 100% by 2035 | Financial reports | Quarterly | Finance Officer |
| Staff Recruitment Rate | Percentage of planned positions filled | 0% | 100% by 2025 | HR records | Quarterly | HR Officer |
| Contract Award Rate | Percentage of planned contracts awarded | 0% | 100% by 2027 | Procurement records | Quarterly | Procurement Officer |
| Government Contribution | Government counterpart funding disbursed | 0% | 100% by 2035 | Financial reports | Quarterly | Finance Officer |

## 3.2 Activity Indicators

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Feasibility Studies Completed | Number of feasibility studies completed | 0 | 6 by 2025 | Consultant reports | Milestone | Project Manager |
| Environmental Assessments Completed | Number of EIAs completed | 0 | 6 by 2025 | EIA reports; approvals | Milestone | Environmental Specialist |
| Detailed Designs Completed | Number of detailed designs completed | 0 | 6 by 2026 | Design reports | Milestone | Design Consultant |
| Land Acquisition Completed | Land acquisition completed | 0 | 100% by 2027 | Land acquisition records | Milestone | Legal Team |
| Construction Milestones | Key construction milestones met | 0 | As per plan | Construction reports | Monthly | Contractor |

## 3.3 Output Indicators

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Priority 01: Urban Expansion |  |  |  |  |  |  |
| - Housing Units Built | Number of new housing units | 0 | 5,000+ by 2030 | Project reports | Annual | Construction Manager |
| - Water Access | % of population with water access | 0% | 100% by 2030 | Utility data | Annual | Construction Manager |
| - Sanitation Coverage | % of population with sanitation | 0% | 80%+ by 2030 | Utility data | Annual | Construction Manager |
| - Green Spaces | % of urban area as green space | 0% | 15%+ by 2030 | GIS mapping | Annual | Planning Department |
| Priority 02: Corridor Roads |  |  |  |  |  |  |
| - Road Length Upgraded | Length of roads upgraded | 0 km | 20 km by 2029 | Project reports | Milestone | Construction Manager |
| - Drainage Systems | Drainage systems installed | 0 | 20 km by 2029 | Project reports | Milestone | Construction Manager |
| - Pedestrian Facilities | Sidewalks and crossings built | 0 | 20 km by 2029 | Project reports | Milestone | Construction Manager |
| Priority 03: FTZ & Logistics |  |  |  |  |  |  |
| - FTZ Area Developed | Area of FTZ developed | 0 ha | 50 ha by 2035 | Project reports | Annual | Construction Manager |
| - Companies Established | Number of companies in FTZ | 0 | 100+ by 2035 | FTZ records | Annual | FTZ Manager |
| - Trade Volume | Value of trade through FTZ | 0 | USD 500M+ by 2035 | Customs records | Annual | FTZ Manager |
| Priority 04: Solid Waste |  |  |  |  |  |  |
| - Waste Collection Coverage | % of households with collection | 0% | 90%+ by 2028 | Service records | Annual | Municipal Services |
| - Recycling Rate | % of waste recycled | 0% | 30%+ by 2028 | Facility records | Annual | Municipal Services |
| - Landfill Operational | Landfill operational | No | Yes by 2028 | Project reports | Milestone | Municipal Services |
| Priority 05: Youth Centre |  |  |  |  |  |  |
| - Youth Trained | Number of youth trained annually | 0 | 5,000+ by 2030 | Training records | Annual | Youth Centre Manager |
| - Businesses Incubated | Number of businesses incubated | 0 | 50+ per year | Incubation records | Annual | Youth Centre Manager |
| - Youth Placed in Jobs | Number of youth placed in jobs | 0 | 1,000+ per year | Placement records | Annual | Youth Centre Manager |
| Priority 06: Reception Centre |  |  |  |  |  |  |
| - Returnees Served | Number of returnees served annually | 0 | To be determined | Service records | Annual | Reception Centre Manager |
| - Reintegration Success | % of returnees successfully reintegrated | 0% | 80%+ by 2030 | Follow-up surveys | Annual | Reception Centre Manager |

## 3.4 Outcome Indicators

### 3.4.1 Urban Development Outcomes

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Population Served | Urban population with access to services | 82,064 | 119,000+ by 2030 | Census data | Annual | M&E Officer |
| Urban Area | Planned urban area | 711 ha | 1,450 ha by 2030 | GIS mapping | Annual | M&E Officer |
| Density Management | Population density | 115.42 p/ha | 82.07 p/ha by 2030 | Population/area analysis | Annual | M&E Officer |

### 3.4.2 Economic Outcomes

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Jobs Created | Direct and indirect jobs created | 0 | 7,000+ by 2035 | Employment records | Annual | M&E Officer |
| Trade Volume | Value of trade through FTZ | 0 | USD 500M+ by 2035 | Customs records | Annual | M&E Officer |
| Tax Revenue | Tax revenue generated | 0 | USD 50M+ by 2035 | Revenue records | Annual | M&E Officer |
| Economic Growth | Contribution to city GDP | 0% | 5%+ by 2035 | Economic analysis | Every 5 years | M&E Officer |
| Logistics Cost Reduction | Reduction in logistics costs | 0% | 30% by 2035 | Logistics surveys | Annual | M&E Officer |

### 3.4.3 Social Outcomes

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Youth Trained | Youth trained annually | 0 | 5,000+ by 2030 | Training records | Annual | M&E Officer |
| Youth Employed | Youth placed in jobs | 0 | 1,000+ per year | Placement records | Annual | M&E Officer |
| Returnees Supported | Returnees receiving support | 0 | To be determined | Service records | Annual | M&E Officer |
| Community Satisfaction | Community satisfaction rating | To be established | >70% satisfied | Community surveys | Annual | M&E Officer |
| Beneficiaries | Women/youth/displaced/host communities | 0% | 40% by 2035 | Beneficiary records | Annual | M&E Officer |

### 3.4.4 Environmental Outcomes

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Waste Collection Coverage | % of households with collection | 0% | 90%+ by 2028 | Service records | Annual | M&E Officer |
| Recycling Rate | % of waste recycled | 0% | 30%+ by 2028 | Facility records | Annual | M&E Officer |
| CO₂ Emissions | Annual CO₂ emissions from transport | To be established | 25% reduction by 2040 | Vehicle counts; emissions factors | Annual | M&E Officer |
| Green Spaces | % of urban area as green space | 0% | 15%+ by 2030 | GIS mapping | Annual | M&E Officer |

## 3.5 Impact Indicators

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Urban Development Index | Composite index of urban development | To be established | 30% improvement by 2055 | Multiple sources | Every 5 years | M&E Officer |
| Economic Growth | GDP growth attributable to project | To be established | To be determined | Economic modeling; national data | Every 5 years | M&E Officer |
| Quality of Life | Quality of life indicators | To be established | 20% improvement by 2055 | Household surveys | Every 5 years | M&E Officer |
| Regional Integration | Trade volumes with Somaliland | To be established | 30% increase by 2055 | Trade data; customs records | Annual | M&E Officer |

## 3.6 Environmental and Social Indicators

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Land Acquisition | Number of households affected | 0 | To be determined | Land acquisition records | As needed | Social Development Specialist |
| Resettlement Completion | % of resettlement completed | 0% | 100% by 2027 | Resettlement records | Quarterly | Social Development Specialist |
| Grievance Resolution | % of grievances resolved | 0% | >90% resolved | GRM database | Monthly | GRM Officer |
| Community Satisfaction | Community satisfaction rating | To be established | >70% satisfied | Community surveys | Annual | M&E Officer |
| Gender Inclusion | % of women in project activities | To be established | >30% | Project records; training records | Annual | Gender Specialist |
| Safety Incidents | Number of safety incidents | 0 | Zero incidents | Safety records | Monthly | Safety Officer |

## 3.7 Financial Indicators

| Indicator | Description | Baseline | Target | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Cost Performance Index | Ratio of earned value to actual cost | 1.0 | >0.9 | Financial reports; EVM | Quarterly | Project Manager |
| Schedule Performance Index | Ratio of earned value to planned value | 1.0 | >0.9 | Project reports; EVM | Quarterly | Project Manager |
| Cost Variance | Difference between budgeted and actual cost | 0 | <10% | Financial reports | Quarterly | Project Manager |
| Financial Leverage | Ratio of private to public funding | 0 | 50:50 by 2030 | Financial reports | Annual | Project Manager |
| Revenue Generation | Revenue generated | 0 | To be determined | Revenue reports | Monthly | Finance Officer |

## 4. DATA COLLECTION METHODS AND TOOLS

## 4.1 Quantitative Methods

| Method | Description | Purpose | Indicators | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- |
| Household Surveys | Structured surveys of households in project area | Mode share; accessibility; satisfaction; quality of life | Mode share; satisfaction; accessibility | Annual | M&E Officer |
| Traffic Counts | Manual or automatic traffic counting | Traffic volumes; mode share | Traffic volumes; private vehicle use | Quarterly/Annual | M&E Officer |
| Travel Time Surveys | Time-motion studies along corridor | Travel time savings | Average travel time | Annual | M&E Officer |
| BRT Operations Data | Automatic passenger counts; fare data | Ridership; revenue | Ridership; revenue | Monthly | Operator |
| Air Quality Monitoring | Stationary or mobile air quality monitoring | Environmental impact | PM2.5; NOx | Quarterly | Environmental Specialist |
| Economic Surveys | Business and logistics surveys | Economic impact | Logistics costs; business growth | Annual | M&E Officer |
| Financial Reports | Budget and expenditure tracking | Financial performance | Budget utilization; cost variance | Monthly/Quarterly | Finance Officer |
| Waste Composition Studies | Analysis of waste composition | Recycling potential; waste management | Waste composition; recycling rate | Annual | Environmental Specialist |

## 4.2 Qualitative Methods

| Method | Description | Purpose | Indicators | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- |
| Key Informant Interviews | Semi-structured interviews with key stakeholders | In-depth understanding; stakeholder perceptions | Satisfaction; perceptions | Annual | M&E Officer |
| Focus Group Discussions | Group discussions with stakeholder groups | Community perspectives; social impacts | Social impacts; community satisfaction | Annual | Social Development Specialist |
| Community Consultations | Open meetings with communities | Community feedback; grievances | Community satisfaction; grievances | Quarterly | Community Liaison Officers |
| Observation | Structured observation of project activities | Implementation quality; user behavior | Implementation quality; behavior change | Ongoing | M&E Officer |
| Case Studies | In-depth studies of specific issues | Lessons learned; impacts | Impacts; lessons learned | As needed | M&E Officer |
| Grievance Analysis | Analysis of grievance data | Effectiveness of GRM | Grievance resolution; satisfaction | Monthly | GRM Officer |
| Success Stories | Documentation of positive outcomes | Communication; learning | Project impacts | Quarterly | Communications Specialist |

## 4.3 Data Sources

| Data Source | Description | Data Type | Access Method | Frequency |
| --- | --- | --- | --- | --- |
| Primary Data | Data collected directly for M&E | Quantitative/Qualitative | Surveys; interviews; observations | Ongoing |
| Project Records | Project documents; progress reports | Quantitative/Qualitative | Project files | Ongoing |
| Financial Records | Budgets; financial reports; payment records | Quantitative | Finance department | Monthly/Quarterly |
| Operational Data | FTZ operations; ridership; revenue | Quantitative | Operators | Monthly |
| Government Data | Census; economic data; traffic data | Quantitative | CSA; Government departments | Annual |
| GIS Data | Spatial data on infrastructure; land use | Quantitative | GIS system | Annual |
| Media Reports | News coverage; stakeholder communications | Qualitative | Media monitoring | Ongoing |
| Satellite Imagery | Earth observation data | Quantitative | Satellite imagery providers | Annual |

## 4.4 Data Collection Schedule

| Data Collection Activity | Baseline | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Annual Thereafter |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Household Survey | X |  |  |  |  | X | Every 5 years |
| Traffic Counts | X | X | X | X | X | X | Annual |
| Travel Time Survey | X |  |  | X |  |  | Every 2-3 years |
| BRT Operations Data |  | X | X | X | X | X | Monthly |
| Air Quality Monitoring | X | X | X | X | X | X | Quarterly |
| Economic Survey | X |  |  |  |  | X | Every 5 years |
| Key Informant Interviews | X |  |  | X |  | X | Every 2-3 years |
| Focus Group Discussions | X |  |  | X |  | X | Every 2-3 years |
| Community Consultations | X | X | X | X | X | X | Quarterly |
| Grievance Data |  | X | X | X | X | X | Monthly |
| Financial Reports |  | X | X | X | X | X | Monthly/Quarterly |
| Waste Composition Study | X |  | X |  | X |  | Every 2 years |
| FTZ Operations Data |  |  | X | X | X | X | Monthly |

## 5. MONITORING AND EVALUATION PLAN

## 5.1 Implementation Monitoring

| Element | Description | Frequency | Responsible |
| --- | --- | --- | --- |
| Activity Tracking | Track completion of planned activities against work plan | Monthly | Project Manager |
| Milestone Tracking | Track completion of key milestones | As per milestones | Project Manager |
| Budget Utilization | Track budget utilization against plan | Monthly | Finance Officer |
| Procurement Monitoring | Track procurement progress | Monthly | Procurement Officer |
| Contract Management | Monitor contractor performance | Monthly | Contract Manager |
| Risk Monitoring | Monitor and update risk register | Monthly | Project Manager |

## 5.2 Performance Monitoring

| Element | Description | Frequency | Responsible |
| --- | --- | --- | --- |
| Output Monitoring | Track output indicators for all six projects | Quarterly | M&E Officer |
| Outcome Monitoring | Track outcome indicators | Annual | M&E Officer |
| Service Delivery Monitoring | Monitor service delivery across all projects | Monthly | Project Managers |
| Customer Satisfaction | Monitor user satisfaction across all services | Quarterly/Annual | M&E Officer |
| Stakeholder Satisfaction | Monitor stakeholder satisfaction | Annual | M&E Officer |

## 5.3 Financial Monitoring

| Element | Description | Frequency | Responsible |
| --- | --- | --- | --- |
| Budget Tracking | Track budget vs actual expenditure | Monthly | Finance Officer |
| Cost Monitoring | Monitor project costs | Monthly | Finance Officer |
| Revenue Tracking | Track revenue generation | Monthly | Operator/Finance Officer |
| Financial Reporting | Prepare financial reports | Quarterly/Annual | Finance Officer |
| Audit | Internal and external audits | Annual | Audit Team |

## 5.4 Environmental and Social Monitoring

| Element | Description | Frequency | Responsible |
| --- | --- | --- | --- |
| Environmental Compliance | Monitor compliance with environmental standards | Quarterly | Environmental Specialist |
| Environmental Impact Monitoring | Monitor environmental impacts | Annual | Environmental Specialist |
| Social Impact Monitoring | Monitor social impacts | Annual | Social Development Specialist |
| GRM Monitoring | Monitor grievance handling | Monthly | GRM Officer |
| Resettlement Monitoring | Monitor resettlement implementation | Quarterly | Social Development Specialist |
| Community Satisfaction | Monitor community satisfaction | Annual | M&E Officer |

## 5.5 Stakeholder Engagement Monitoring

| Element | Description | Frequency | Responsible |
| --- | --- | --- | --- |
| Engagement Tracking | Track stakeholder engagement activities | Monthly | Engagement Manager |
| Participation Monitoring | Monitor participation rates | Per event | Engagement Manager |
| Feedback Analysis | Analyze stakeholder feedback | Quarterly | Engagement Manager |
| GRM Analysis | Analyze grievance data | Monthly | GRM Officer |

## 6. REPORTING FRAMEWORK

## 6.1 Reporting Structure

text

┌─────────────────────────────────────────────────────────────────────────────┐

│ REPORTING STRUCTURE │

├─────────────────────────────────────────────────────────────────────────────┤

│ │

│ ┌──────────────────────┐ │

│ │ ANNUAL REPORT │ │

│ │ (All Stakeholders) │ │

│ └──────────┬───────────┘ │

│ │ │

│ ┌──────────┴───────────┐ │

│ │ QUARTERLY REPORTS │ │

│ │ (Financiers, Partners)│ │

│ └──────────┬───────────┘ │

│ │ │

│ ┌──────────┴───────────┐ │

│ │ MONTHLY REPORTS │ │

│ │ (Project Team) │ │

│ └──────────┬───────────┘ │

│ │ │

│ ┌──────────┴───────────┐ │

│ │ WEEKLY UPDATES │ │

│ │ (Management) │ │

│ └──────────────────────┘ │

│ │

└─────────────────────────────────────────────────────────────────────────────┘

## 6.2 Report Types and Frequency

| Report Type | Purpose | Audience | Frequency | Responsible |
| --- | --- | --- | --- | --- |
| Weekly Update | Status updates; issues; decisions | Project Team; Management | Weekly | Project Manager |
| Monthly Report | Progress against plan; challenges; next steps | Project Team; City Administration | Monthly | Project Manager |
| Quarterly Report | Progress; financial; performance; risks | Financiers; Partners; Government | Quarterly | Project Manager |
| Annual Report | Comprehensive progress; outcomes; impacts; lessons | All stakeholders | Annually | Project Manager |
| Financial Report | Budget utilization; financial performance | Financiers; Government | Quarterly/Annual | Finance Officer |
| Environmental Report | Environmental compliance; impacts | Environmental authorities; stakeholders | Quarterly/Annual | Environmental Specialist |
| Social Report | Social impacts; GRM; community engagement | Social authorities; stakeholders | Quarterly/Annual | Social Development Specialist |
| Evaluation Reports | Evaluation findings; recommendations | All stakeholders | Mid-term; End-term | Evaluation Team |
| Ad Hoc Reports | Specific issues; requests | Requesting party | As needed | Project Manager |

## 6.3 Reporting Templates

### 6.3.1 Monthly Report Template

| Section | Content |
| --- | --- |
| Executive Summary | Key achievements; challenges; next steps |
| Progress Update | Activities completed; milestones achieved |
| Performance Summary | Indicator progress; targets vs actual |
| Financial Summary | Budget utilization; variance analysis |
| Risk Update | Risk status; mitigation actions |
| Issues and Challenges | Current issues; actions taken; support needed |
| Next Steps | Planned activities for next period |
| Annexes | Detailed data; supporting documents |

### 6.3.2 Quarterly Report Template

| Section | Content |
| --- | --- |
| Executive Summary | Key achievements; challenges; next steps |
| Project Progress | Activities; milestones; outputs |
| Performance Monitoring | Output and outcome indicators |
| Financial Report | Budget utilization; variance; forecasts |
| Environmental and Social | E&S compliance; impacts; GRM |
| Stakeholder Engagement | Engagement activities; feedback |
| Risk Management | Risk status; mitigation |
| Lessons Learned | Key lessons; good practices |
| Next Quarter Plan | Planned activities; targets |
| Annexes | Detailed data; supporting documents |

### 6.3.3 Annual Report Template

| Section | Content |
| --- | --- |
| Executive Summary | Key achievements; impacts; lessons |
| Project Overview | Project description; objectives; stakeholders |
| Implementation Progress | Activities; milestones; outputs |
| Performance Results | Output and outcome indicators; targets |
| Financial Summary | Budget utilization; financial performance |
| Environmental and Social | E&S compliance; impacts; GRM |
| Stakeholder Engagement | Engagement activities; feedback; satisfaction |
| Evaluation Findings | Evaluation results; recommendations |
| Lessons Learned | Key lessons; good practices |
| Next Year Plan | Planned activities; targets |
| Annexes | Detailed data; supporting documents |

## 7. EVALUATION PLAN

## 7.1 Mid-Term Evaluation

| Element | Description |
| --- | --- |
| Timing | Mid-point of implementation (approximately 2027-2028) |
| Purpose | Assess progress; identify challenges; recommend adjustments |
| Scope | All project components; outcomes to date; financial performance |
| Methodology | Mixed methods (document review; interviews; surveys; site visits) |
| Team | External evaluators with relevant expertise |
| Key Questions | Is project on track? What challenges are faced? What adjustments are needed? |
| Outputs | Mid-term evaluation report; recommendations; action plan |

## 7.2 End-Term Evaluation

| Element | Description |
| --- | --- |
| Timing | End of implementation (approximately 2035) |
| Purpose | Assess outcomes and impacts; document lessons; guide future projects |
| Scope | All project components; outcomes; impacts; sustainability |
| Methodology | Mixed methods (document review; interviews; surveys; site visits; analysis) |
| Team | External evaluators with relevant expertise |
| Key Questions | What were the outcomes and impacts? What factors contributed to success? What lessons can be learned? |
| Outputs | End-term evaluation report; lessons document; recommendations |

## 7.3 Thematic Evaluations

| Theme | Timing | Purpose |
| --- | --- | --- |
| Economic Impact | Post-implementation | Assess economic impacts and benefits across all projects |
| Environmental Impact | Post-implementation | Assess environmental impacts and mitigation effectiveness |
| Social Impact | Post-implementation | Assess social impacts and inclusion |
| Sustainability | Post-implementation | Assess sustainability of project outcomes |
| Gender and Inclusion | Post-implementation | Assess gender and inclusion outcomes |
| GRM Effectiveness | Ongoing | Assess effectiveness of grievance mechanism |
| Migration Impact | Post-implementation | Assess impacts on migration patterns and returnee reintegration |

## 7.4 Evaluation Methodology

| Element | Description |
| --- | --- |
| Evaluation Design | Mixed methods; quasi-experimental where possible |
| Data Collection | Document review; surveys; interviews; focus groups; site visits; observations |
| Data Analysis | Quantitative (statistical analysis); Qualitative (thematic analysis) |
| Evaluation Criteria | Relevance; effectiveness; efficiency; impact; sustainability |
| Evaluation Standards | OECD-DAC evaluation criteria |
| Quality Assurance | Peer review; stakeholder validation |

## 8. M&E ROLES AND RESPONSIBILITIES

## 8.1 M&E Team Structure

| Position | Responsibility | Quantity |
| --- | --- | --- |
| M&E Manager | Overall M&E leadership; coordination; reporting | 1 |
| M&E Officers | Data collection; analysis; reporting | 2 |
| Data Analyst | Data management; analysis; visualization | 1 |
| GIS Specialist | Spatial data; mapping; analysis | 1 |
| Social Development Specialist | Social monitoring; inclusion; GRM | 1 |
| Environmental Specialist | Environmental monitoring; compliance | 1 |
| Finance Officer | Financial monitoring; reporting | 1 |

## 8.2 Responsibilities by Role

| Role | Responsibilities |
| --- | --- |
| M&E Manager | Lead M&E framework development; coordinate M&E activities; oversee reporting; ensure quality; capacity building |
| M&E Officers | Implement M&E activities; data collection; analysis; report preparation; indicator tracking |
| Data Analyst | Manage M&E database; data analysis; visualization; statistical analysis |
| GIS Specialist | GIS data management; spatial analysis; map production; land use monitoring |
| Social Development Specialist | Social monitoring; inclusion monitoring; GRM oversight; community engagement monitoring |
| Environmental Specialist | Environmental monitoring; compliance monitoring; environmental reporting |
| Finance Officer | Financial monitoring; budget tracking; financial reporting |
| Project Manager | Overall M&E oversight; ensure M&E integration in project management; decision-making |
| Stakeholder Engagement Manager | Engagement monitoring; feedback analysis; stakeholder satisfaction |
| Operator | Operational data provision; service quality monitoring; customer feedback |

## 8.3 Training and Capacity Building

| Training Topic | Audience | Frequency | Responsible |
| --- | --- | --- | --- |
| M&E Fundamentals | Project team | At project start | M&E Manager |
| Data Collection Methods | M&E team; Community Liaison Officers | Annually | M&E Manager |
| Data Analysis | M&E team | Annually | M&E Manager |
| Reporting | M&E team; Project team | Annually | M&E Manager |
| GRM Management | GRM team; Community Liaison Officers | Annually | GRM Officer |
| Environmental Monitoring | Environmental team | Annually | Environmental Specialist |
| Social Monitoring | Social team | Annually | Social Development Specialist |
| GIS and Mapping | M&E team; GIS Specialist | Annually | GIS Specialist |

## 9. M&E BUDGET AND RESOURCES

## 9.1 Budget Estimate

| Item | Description | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- |
| Personnel | M&E team salaries | 300,000 | 48,009,570 |
| - M&E Manager | Full-time, 10 years | 100,000 | 16,003,190 |
| - M&E Officers (2) | Full-time, 10 years | 120,000 | 19,203,828 |
| - Data Analyst | Full-time, 10 years | 40,000 | 6,401,276 |
| - GIS Specialist | Full-time, 10 years | 40,000 | 6,401,276 |
| Data Collection | Surveys; monitoring; data collection | 200,000 | 32,006,380 |
| - Household Surveys | 5 surveys | 80,000 | 12,802,552 |
| - Traffic Counts | Annual | 40,000 | 6,401,276 |
| - Focus Groups/Interviews | Periodic | 30,000 | 4,800,957 |
| - Environmental Monitoring | Quarterly | 30,000 | 4,800,957 |
| - Social Monitoring | Annual | 20,000 | 3,200,638 |
| Equipment and Systems | M&E software; equipment | 70,000 | 11,202,233 |
| - M&E Software | Database; analysis tools | 30,000 | 4,800,957 |
| - GIS Software and Hardware | GIS systems | 20,000 | 3,200,638 |
| - Survey Equipment | Tablets; GPS; etc. | 20,000 | 3,200,638 |
| Evaluations | Mid-term; end-term; thematic | 200,000 | 32,006,380 |
| - Mid-term Evaluation | External evaluation | 60,000 | 9,601,914 |
| - End-term Evaluation | External evaluation | 90,000 | 14,402,871 |
| - Thematic Evaluations | Periodic | 50,000 | 8,001,595 |
| Training and Capacity | M&E training | 40,000 | 6,401,276 |
| Reporting | Report production; dissemination | 50,000 | 8,001,595 |
| Contingency | 10% of total | 86,000 | 13,762,743 |
| TOTAL | - | 946,000 | 151,390,177 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 9.2 Required Resources

| Resource | Description | Quantity | Estimated Cost (USD) | Estimated Cost (Birr)* |
| --- | --- | --- | --- | --- |
| Human Resources | M&E team | 7 staff | 300,000/year | 48,009,570/year |
| Vehicles | For field monitoring | 2 vehicles | 60,000 | 9,601,914 |
| Computers/Laptops | For M&E team | 7 units | 21,000 | 3,360,670 |
| Tablets | For data collection | 5 units | 7,500 | 1,200,239 |
| GPS Devices | For field mapping | 3 units | 4,500 | 720,144 |
| Survey Equipment | Traffic counters; etc. | Various | 15,000 | 2,400,479 |
| M&E Software | Database; analysis | Various | 30,000 | 4,800,957 |
| GIS Software | ArcGIS or QGIS | 3 licenses | 20,000 | 3,200,638 |
| Office Space | For M&E team | 1 office | 15,000 | 2,400,479 |

*Based on exchange rate of 1 USD = 160.0319 Birr (August 2026)

## 10. DATA MANAGEMENT AND QUALITY ASSURANCE

## 10.1 Data Collection Protocols

| Protocol | Description |
| --- | --- |
| Standardized Tools | Use standardized data collection tools and templates |
| Trained Enumerators | Ensure enumerators are trained on tools and protocols |
| Pre-testing | Pre-test tools before full implementation |
| Sampling | Use appropriate sampling methods for surveys |
| Informed Consent | Obtain informed consent from respondents |
| Confidentiality | Ensure confidentiality of respondent data |
| Data Validation | Validate data during collection and entry |
| Data Entry | Double-entry or validation checks for data entry |

## 10.2 Data Quality Assurance

| Element | Description |
| --- | --- |
| Data Quality Standards | Define data quality standards (accuracy; completeness; timeliness; consistency) |
| Quality Checks | Regular quality checks during data collection and entry |
| Data Audits | Periodic data audits to verify quality |
| Data Verification | Cross-check data from multiple sources |
| Peer Review | Peer review of data analysis and reports |
| External Validation | External validation of key findings |

## 10.3 Data Storage and Security

| Element | Description |
| --- | --- |
| Data Storage | Secure storage (physical and digital) |
| Database | Central M&E database for all data |
| Backup | Regular backups of all data |
| Access Control | Controlled access to data (role-based) |
| Confidentiality | Ensure confidentiality of sensitive data |
| Data Protection | Compliance with data protection standards |
| Retention Policy | Clear data retention and disposal policy |

## 10.4 Data Analysis and Use

| Element | Description |
| --- | --- |
| Data Analysis | Quantitative (statistical); Qualitative (thematic) |
| Data Visualization | Charts; graphs; maps for communication |
| Data Use | Use data for decision-making; learning; reporting |
| Feedback | Share findings with stakeholders |
| Learning | Use findings for adaptive management |
| Knowledge Management | Document and share lessons learned |

## 11. ANNEXES

## 11.1 Annex A: Indicator Tracking Table

| Priority | Indicator | Baseline | Target | Actual | Progress | Data Source | Frequency | Responsible |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 01 | Housing Units Built | 0 | 5,000+ |  | % | Project reports | Annual | Construction Manager |
| 01 | Water Access (%) | 0% | 100% |  | % | Utility data | Annual | Construction Manager |
| 02 | Road Length Upgraded (km) | 0 | 20 |  | % | Project reports | Milestone | Construction Manager |
| 03 | Jobs Created | 0 | 6,000+ |  | % | Employment records | Annual | FTZ Manager |
| 03 | Trade Volume (USD M) | 0 | 500+ |  | % | Customs records | Annual | FTZ Manager |
| 04 | Waste Collection (%) | 0% | 90%+ |  | % | Service records | Annual | Municipal Services |
| 05 | Youth Trained (annually) | 0 | 5,000+ |  | % | Training records | Annual | Youth Centre Manager |
| 06 | Returnees Served | 0 | TBD |  | % | Service records | Annual | Reception Manager |

## 11.2 Annex B: Data Collection Tools

| Tool | Description | Purpose | Format |
| --- | --- | --- | --- |
| Household Survey | Structured questionnaire for households | Mode share; satisfaction; accessibility | Paper; electronic |
| Traffic Count Sheet | Manual traffic counting form | Traffic volumes | Paper; electronic |
| Travel Time Survey | Time-motion study form | Travel time measurement | Paper; electronic |
| Key Informant Interview Guide | Semi-structured interview guide | Stakeholder perceptions | Paper; electronic |
| Focus Group Discussion Guide | Focus group discussion guide | Community perspectives | Paper; electronic |
| Observation Checklist | Structured observation form | Implementation quality; behavior | Paper; electronic |
| Grievance Registration Form | Complaint registration form | GRM tracking | Paper; electronic |
| Satisfaction Survey | Customer satisfaction questionnaire | Service satisfaction | Paper; electronic |
| Waste Composition Form | Waste analysis form | Waste composition | Paper; electronic |
| Economic Impact Survey | Business and logistics survey | Economic impact | Paper; electronic |
| Youth Training Record | Training participant form | Youth training tracking | Electronic |
| Returnee Registration Form | Returnee intake form | Returnee tracking | Paper; electronic |
| FTZ Tenant Registration | Tenant registration form | FTZ tenant tracking | Electronic |
| Construction Progress Form | Construction progress tracking | Construction monitoring | Paper; electronic |
| Community Consultation Record | Community meeting form | Stakeholder engagement | Paper; electronic |

## 11.3 Annex C: Reporting Templates

| Template | Description | Format |
| --- | --- | --- |
| Monthly Report Template | Monthly progress report | Word; PDF |
| Quarterly Report Template | Quarterly progress report | Word; PDF |
| Annual Report Template | Annual progress report | Word; PDF |
| Indicator Tracking Template | Indicator tracking | Excel |
| Financial Report Template | Financial performance report | Excel; Word |
| Environmental Report Template | Environmental compliance report | Word; PDF |
| Social Report Template | Social impact report | Word; PDF |
| Evaluation Report Template | Evaluation findings report | Word; PDF |
| Risk Register Template | Risk tracking | Excel |
| Stakeholder Engagement Log | Engagement tracking | Excel |

## 11.4 Annex D: M&E Timeline

| Year | Q1 | Q2 | Q3 | Q4 | Key M&E Activities |
| --- | --- | --- | --- | --- | --- |
| 2024 |  |  |  | X | Baseline surveys; M&E framework development |
| 2025 | X | X | X | X | Ongoing monitoring; annual report |
| 2026 | X | X | X | X | Ongoing monitoring; annual report |
| 2027 | X | X | X | X | Mid-term evaluation; ongoing monitoring |
| 2028 | X | X | X | X | Ongoing monitoring; annual report |
| 2029 | X | X | X | X | Ongoing monitoring; annual report |
| 2030 | X | X | X | X | Mid-term review; ongoing monitoring |
| 2031 | X | X | X | X | Ongoing monitoring; annual report |
| 2032 | X | X | X | X | Ongoing monitoring; annual report |
| 2033 | X | X | X | X | Thematic evaluations; ongoing monitoring |
| 2034 | X | X | X | X | Ongoing monitoring; annual report |
| 2035 | X | X | X | X | End-term evaluation; final report |

SUMMARY TABLE: M&E FRAMEWORK COMPONENTS

| Component | Description | Key Elements |
| --- | --- | --- |
| Indicators | Measures of project progress and performance | Input; Activity; Output; Outcome; Impact; E&S; Financial |
| Data Collection | Methods and tools for data gathering | Quantitative; Qualitative; Surveys; Interviews; Monitoring |
| Monitoring | Ongoing tracking of project implementation | Implementation; Performance; Financial; E&S; Stakeholder |
| Evaluation | Periodic assessment of project outcomes and impacts | Mid-term; End-term; Thematic; Participatory |
| Reporting | Communication of M&E findings | Weekly; Monthly; Quarterly; Annual; Ad hoc |
| Roles | Responsibilities for M&E activities | M&E Manager; Officers; Specialists; Project Manager |
| Budget | Resources for M&E activities | Personnel; Data collection; Evaluations; Equipment |
| Quality Assurance | Ensuring data quality and reliability | Protocols; Standards; Audits; Verification |

End of Appendix E